## RWASH_Activity_20240815
Instance ID | Country Name | Site Name | Image Description | Image Path | Image Date | Longitude | Latitude | Activity Status | Comments | Project Description | Completion Percentage | Username | Device ID | Created At | Status
uuid:d7683147-d500-4624-9bf4-041ad5446c48 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_d7683147-d500-4624-9bf4-041ad5446c48/1753610378362.jpg | 2025-07-27 | 43.1214 | 9.6457 | VIP latrine with shower | In Progress | It will be finished | 95 | N/A | collect:LlPkDyliAl9Qhmgg | 2025-07-29 17:14:08 | N/A
uuid:a0fac435-12f7-4d16-a26e-95d24a9db02f | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_a0fac435-12f7-4d16-a26e-95d24a9db02f/1753610181624.jpg | 2025-07-27 | 43.1214 | 9.6459 | Guard house ,shedder booster | Completed | Guard house at Shedder booster | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-07-29 17:14:02 | N/A
uuid:a720cfbf-ea26-441c-b2bb-1578fffe3295 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_a720cfbf-ea26-441c-b2bb-1578fffe3295/1753519036801.jpg | 2025-07-26 | 43.2249 | 9.8013 | Awubare booster station | Completed | Guard house at Booster station | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-07-29 17:13:56 | N/A
uuid:8811fea6-e3f0-42aa-998a-5af7dd4a780e | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_8811fea6-e3f0-42aa-998a-5af7dd4a780e/1753517171010.jpg | 2025-07-26 | 43.2199 | 9.8106 | Awubare BH | In Progress | The construction of VIP latrine with shower is about to be completed | 98 | N/A | collect:LlPkDyliAl9Qhmgg | 2025-07-29 17:13:49 | N/A
uuid:b65898de-bdd9-48dc-8ff1-5d886594239c | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_b65898de-bdd9-48dc-8ff1-5d886594239c/1753517066218.jpg | 2025-07-26 | 43.2199 | 9.8105 | Awubare BH | Completed | The construction of Guard House has been completed | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-07-28 13:47:34 | N/A
uuid:ab026642-0825-420d-a875-fd7915cd2384 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_ab026642-0825-420d-a875-fd7915cd2384/1753516382621.jpg | 2025-07-26 | 43.2182 | 9.8115 | Solar borehole | Completed | Completed | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-07-28 13:47:22 | N/A
uuid:86591463-6b2d-4b95-abbb-337fe777319d | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_86591463-6b2d-4b95-abbb-337fe777319d/1751445371239.jpg | 2025-07-02 | 43.1021 | 9.0599 | Booster station | In Progress | The VIP latrine with shower is being constructed | 50 | N/A | collect:LlPkDyliAl9Qhmgg | 2025-07-02 08:48:40 | N/A
uuid:7a68cd8d-177a-419c-a423-0bb5d948649b | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_7a68cd8d-177a-419c-a423-0bb5d948649b/1751445203270.jpg | 2025-07-02 | 43.1023 | 9.06 | Booster station | In Progress | One vertical surface pump with capacity of 75kw is being installed | 95 | N/A | collect:LlPkDyliAl9Qhmgg | 2025-07-02 08:48:11 | N/A
uuid:a8a5cd07-3196-409c-b743-9e8c09feb5ec | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_a8a5cd07-3196-409c-b743-9e8c09feb5ec/1751444218847.jpg | 2025-07-02 | 43.0188 | 9.0092 | Water treatment center | In Progress | The VIP latrine with shower is in progress | 50 | N/A | collect:LlPkDyliAl9Qhmgg | 2025-07-02 08:47:40 | N/A
uuid:17c27d05-c018-454b-b00a-b975cb0a6863 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_17c27d05-c018-454b-b00a-b975cb0a6863/1751444064373.jpg | 2025-07-02 | 43.0185 | 9.0092 | Water treatment center | In Progress | Two vertical surface pumps are being installed in Pump house | 90 | N/A | collect:LlPkDyliAl9Qhmgg | 2025-07-02 08:47:01 | N/A
uuid:0485f5e9-929a-428d-9419-f9d226f09377 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_0485f5e9-929a-428d-9419-f9d226f09377/1751443556661.jpg | 2025-07-02 | 43.008 | 9.02 | EB1 | In Progress | It is under progress | 65 | N/A | collect:LlPkDyliAl9Qhmgg | 2025-07-02 08:46:42 | N/A
uuid:38ea9334-eb45-458f-8fd3-697f556aa0d1 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_38ea9334-eb45-458f-8fd3-697f556aa0d1/1751442629812.jpg | 2025-07-02 | 43.0183 | 9.0035 | EB3(Fish BH) | In Progress | This solar system is under installation | 75 | N/A | collect:LlPkDyliAl9Qhmgg | 2025-07-02 08:46:19 | N/A
uuid:736a32a4-cec2-4488-9202-948a8dff8395 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_736a32a4-cec2-4488-9202-948a8dff8395/1740649509344.jpg | 2025-02-27 | 43.1026 | 9.0598 | Booster station | In Progress | Waiting for instllation surface pump with capcity of 75kw | 90 | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-27 10:05:43 | N/A
uuid:c3ea7c7b-f0c1-4e8f-aa47-acdab12b0c4d | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_c3ea7c7b-f0c1-4e8f-aa47-acdab12b0c4d/1740648093909.jpg | 2025-02-27 | 43.013 | 9.0138 | PB2 -borehole site | Completed | Perkin Generator with capacity of 45KVA instlled. | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-27 10:05:24 | N/A
uuid:3fa05809-e132-4aaa-bfbc-7088ea494dd2 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_3fa05809-e132-4aaa-bfbc-7088ea494dd2/1740647514397.jpg | 2025-02-27 | 43.0079 | 9.0201 | NBH3 -borehole site | Completed | Perkin Generator with capacity of 60KVA installed | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-27 10:05:10 | N/A
uuid:36fbd555-f99c-4d64-a6d6-81dedfaebb01 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_36fbd555-f99c-4d64-a6d6-81dedfaebb01/1740646665692.jpg | 2025-02-27 | 43.0185 | 9.0093 | Kebribeyah water treatment center | In Progress | Surface pump with capacity of 75kw is being installed | 95 | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-27 10:05:00 | N/A
uuid:85699211-462b-4cf9-9372-9450cde23c6d | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_85699211-462b-4cf9-9372-9450cde23c6d/1740646389015.jpg | 2025-02-27 | 43.0182 | 9.0095 | Kebribeyah water treatment center | In Progress | Installtion of surface pump with capacigy of 75kw is remaining activity | 90 | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-27 10:04:50 | N/A
uuid:8378764d-ec8d-469a-887b-8d65a5c0f452 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_8378764d-ec8d-469a-887b-8d65a5c0f452/1740568828275.jpg | 2025-02-26 | 43.2205 | 9.8101 | Solar system @BH#4 | Completed | Started operation | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 12:11:31 | N/A
uuid:7dec15a1-13ac-4652-9525-4ff1a3c2ba57 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_7dec15a1-13ac-4652-9525-4ff1a3c2ba57/1740570145885.jpg | 2025-02-26 | 43.2253 | 9.801 | Booster station (165 KVA Generator) | Completed | Completed and started operation | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:59:17 | N/A
uuid:850f6e08-313a-4e82-8deb-b9aac563bc88 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_850f6e08-313a-4e82-8deb-b9aac563bc88/1740570028806.jpg | 2025-02-26 | 43.2254 | 9.801 | Booster station(vertical pump) | Completed | Installed and started operation | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:59:06 | N/A
uuid:0c7eebce-7861-4bb1-8f2a-1acb53a6fbd4 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_0c7eebce-7861-4bb1-8f2a-1acb53a6fbd4/1740569855266.jpg | 2025-02-26 | 43.2246 | 9.801 | Booster station (Solarization) | Completed | Started operation | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:58:57 | N/A
uuid:27f538cf-84c3-4c12-be72-ac2163664358 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_27f538cf-84c3-4c12-be72-ac2163664358/1740569184284.jpg | 2025-02-26 | 43.2194 | 9.8102 | BH#1(solar system) | Completed | Started operation | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:58:23 | N/A
uuid:b2a5d4de-4c40-443f-bf1a-68e4a996fac5 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_b2a5d4de-4c40-443f-bf1a-68e4a996fac5/1740569029164.jpg | 2025-02-26 | 43.2201 | 9.8106 | 60KVA generator @between two boreholes | Completed | Installed and started operation | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:58:02 | N/A
uuid:60f1391e-5ab9-495e-b525-988d9c2ca8ac | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_60f1391e-5ab9-495e-b525-988d9c2ca8ac/1740564282611.jpg | 2025-02-26 | 43.1189 | 9.6433 | BH#2(construction of Guard house) | Completed | Completed and providing service | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:56:58 | N/A
uuid:fda4e269-9224-4553-b719-ae5ad1d4ddd9 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_fda4e269-9224-4553-b719-ae5ad1d4ddd9/1740564162998.jpg | 2025-02-26 | 43.119 | 9.6433 | BH#2( Construction of Generator house) | Completed | Completed and started providing service | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:56:46 | N/A
uuid:36a49725-ae51-45a4-b385-53db8eac6c72 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_36a49725-ae51-45a4-b385-53db8eac6c72/1740563658034.jpg | 2025-02-26 | 43.1216 | 9.6456 | Solar system at booster station | Completed | Solar system installed and started operation | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:56:35 | N/A
uuid:12157b63-4b6b-4e2a-aa40-1dd9f3ec635d | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_12157b63-4b6b-4e2a-aa40-1dd9f3ec635d/1740563449145.jpg | 2025-02-26 | 43.1214 | 9.6458 | Booster station | Completed | 55kw surface pump was installed at booster station. | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:56:24 | N/A
uuid:a1075330-8d3f-4ee1-8263-4db9fb0237d5 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_a1075330-8d3f-4ee1-8263-4db9fb0237d5/1740563315176.jpg | 2025-02-26 | 43.1214 | 9.6459 | Booster station | Completed | 165KVA Generator installed at booster station | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:56:16 | N/A
uuid:5350b633-81a4-4f37-b860-07d45433bf09 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_5350b633-81a4-4f37-b860-07d45433bf09/1740562899241.jpg | 2025-02-26 | 43.1212 | 9.6493 | BH#1 | Completed | Completed and provide service | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:56:08 | N/A
uuid:b81a72bd-73ff-41c6-aad9-3f883d479edf | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_b81a72bd-73ff-41c6-aad9-3f883d479edf/1740562812607.jpg | 2025-02-26 | 43.1211 | 9.6493 | BH#1 | Completed | Completed and provide service | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:55:54 | N/A
uuid:5e7a71bd-64b9-482e-a3f5-e33d631cf3cb | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_5e7a71bd-64b9-482e-a3f5-e33d631cf3cb/1740562014828.jpg | 2025-02-26 | 43.1189 | 9.6433 | Construction of Guard house at BH#1 | Completed | Completed | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:55:41 | N/A
uuid:9f8a78e6-23c1-4a0d-9f17-90b1dcff881d | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_9f8a78e6-23c1-4a0d-9f17-90b1dcff881d/1740561832507.jpg | 2025-02-26 | 43.119 | 9.6433 | Construction of Generator house | Completed | Completed and started providing service | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:55:30 | N/A
uuid:debdd2f5-7adc-4d54-9544-5e25b53cecf2 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_debdd2f5-7adc-4d54-9544-5e25b53cecf2/1740560803015.jpg | 2025-02-26 | 43.1317 | 9.6982 | Supply of 55KW surface pump | Not Started | Surface pump with capacity serve as back up | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-26 11:55:17 | N/A
uuid:0a3f1796-ccea-4208-b04e-10cc6ef25de4 | Ethiopia | Aw Barre | Other – please specify | N/A | 2024-12-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-25 09:17:09 | N/A
uuid:d9de9db2-9be6-4b8d-bc13-06c81adac29e | Ethiopia | Aw Barre | Other – please specify | N/A | 2025-02-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-25 09:00:19 | N/A
uuid:b04e8383-ee45-4feb-b8b1-3f6af9de51c6 | Ethiopia | Aw Barre | Other – please specify | N/A | 2025-02-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-25 09:00:17 | N/A
uuid:933ea8d5-5270-4e2d-8a3e-f8848d75d957 | Ethiopia | Aw Barre | Other – please specify | N/A | 2024-12-25 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2025-02-25 08:50:09 | N/A
uuid:1df3deb2-2f84-42e3-8003-fb1bd321e382 | Ethiopia | Aw Barre | Other – please specify | N/A | 2024-11-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2024-11-14 13:44:33 | N/A
uuid:ea100689-5e76-4f5b-abc2-d11e4f99bb4f | Ethiopia | Aw Barre | Other – please specify | N/A | 2024-11-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2024-11-14 13:44:33 | N/A
uuid:2cc5fbf5-9606-471e-9f07-1c643e991c6f | Ethiopia | Aw Barre | Other – please specify | N/A | 2024-11-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:LlPkDyliAl9Qhmgg | 2024-11-14 13:44:32 | N/A
uuid:e9c30f04-0050-4e8a-8e65-d945e4f35d01 | Ethiopia | Aw Barre | Capacity Building | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_e9c30f04-0050-4e8a-8e65-d945e4f35d01/1727720470070.jpg | 2024-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:FfyI7UDxwgFUoQi0 | 2024-09-30 18:21:45 | N/A
uuid:7b0e3269-f874-406b-a7d9-c5e5cdc5de2b | Ethiopia | Shedder | Capacity Building | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_7b0e3269-f874-406b-a7d9-c5e5cdc5de2b/1727720273593.jpg | 2024-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:FfyI7UDxwgFUoQi0 | 2024-09-30 18:18:31 | N/A
uuid:d280b85a-2a0d-4574-95e9-cc1be372ba04 | Ethiopia | Kebribeyah | Capacity Building | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_d280b85a-2a0d-4574-95e9-cc1be372ba04/1727719782848.jpg | 2024-09-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:FfyI7UDxwgFUoQi0 | 2024-09-30 18:11:49 | N/A
uuid:7b874756-bc56-48ad-9b10-8d9e8942ae6c | Ethiopia | Kebribeyah | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_7b874756-bc56-48ad-9b10-8d9e8942ae6c/1723967999122.heic | 2024-08-14 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:WKSXUb6YJoFm1wAK | 2024-08-19 05:18:51 | N/A
uuid:b61e73a3-585d-460b-be30-7ec7096a2f07 | Ethiopia | Kebribeyah | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_b61e73a3-585d-460b-be30-7ec7096a2f07/1723965313382.jpg | 2024-08-18 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:WKSXUb6YJoFm1wAK | 2024-08-19 05:18:47 | N/A
uuid:a8734381-a201-4bb0-aa5f-c27614ed9697 | Ethiopia | Kebribeyah | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_a8734381-a201-4bb0-aa5f-c27614ed9697/1723893241459.heic | 2024-08-17 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:WKSXUb6YJoFm1wAK | 2024-08-19 05:18:43 | N/A
uuid:8520c631-6c07-48b8-96f1-aa401f827a04 | Ethiopia | Kebribeyah | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_8520c631-6c07-48b8-96f1-aa401f827a04/1723893162241.heic | 2024-08-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:WKSXUb6YJoFm1wAK | 2024-08-19 05:18:39 | N/A
uuid:08f6b944-2cf4-47ff-9f53-a475ae17e6c4 | Ethiopia | Kebribeyah | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/5/RWASH_Activity_20240815/uuid_08f6b944-2cf4-47ff-9f53-a475ae17e6c4/1723892972121.heic | 2024-08-15 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:WKSXUb6YJoFm1wAK | 2024-08-19 05:18:36 | N/A
uuid:a3162cf3-c279-47fc-a1c9-17e97ffdc002 | Ethiopia | Kebribeyah | Other – please specify | N/A | 2024-08-16 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:d8A8ykmwSZHGcowv | 2024-08-16 10:55:30 | N/A