## RWASH_Activity_20250831
Instance ID | Country Name | Site Name | Image Description | Image Path | Image Date | Longitude | Latitude | Activity Status | Comments | Project Description | Completion Percentage | Username | Device ID | Created At | Status
uuid:3b104736-6724-480a-8d0d-4c749a6f1746 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_3b104736-6724-480a-8d0d-4c749a6f1746/IMG_5002-14_12_39.jpeg | 2026-04-30 | 43.0084 | 8.9946 | Kbps01 backwash tank | In Progress | Backwash tank the major civil works upto the top roof slab work completed and remaining works underway | 16 | robelw@msconsultancyet.com | N/A | 2026-05-04 11:14:24 | N/A
uuid:05d90f6f-3d59-4259-b751-cf7443e2ab73 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_05d90f6f-3d59-4259-b751-cf7443e2ab73/IMG_5004-14_8_28.jpeg | 2026-04-18 | 43.0116 | 9.0006 | Kbps-01, pumping station | In Progress | Kbps01, pumping station wall work plastering and bituminous painting underground part | 16 | robelw@msconsultancyet.com | N/A | 2026-05-04 11:09:32 | N/A
uuid:26bb7a70-38c9-42e5-9f83-29695931227d | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_26bb7a70-38c9-42e5-9f83-29695931227d/IMG_5003-13_59_3.jpeg | 2026-04-26 | 43.0128 | 9.0006 | Kbos01- sedimentation unit | In Progress | Sedimentaion treatment plant unit excavation and compaction work | 16 | robelw@msconsultancyet.com | N/A | 2026-05-04 11:00:13 | N/A
uuid:81869e3c-586b-4ce1-88cb-b9f542692b6a | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_81869e3c-586b-4ce1-88cb-b9f542692b6a/IMG_4998-13_54_20.jpeg | 2026-05-03 | 43.0103 | 8.9995 | Booster pumping station no:1 | In Progress | Aerator water treatment unit works underway | 16 | robelw@msconsultancyet.com | N/A | 2026-05-04 10:55:47 | N/A
uuid:81663d53-908d-412a-b6c8-17c15fbfd8f5 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_81663d53-908d-412a-b6c8-17c15fbfd8f5/IMG_4821-13_50_58.jpeg | 2026-05-01 | 43.1673 | 9.1097 | Elevated reservoirs | In Progress | Major civil works for the elevated reservoirs finalized | 16 | robelw@msconsultancyet.com | N/A | 2026-05-04 10:51:47 | N/A
uuid:ad63a976-8561-431b-aeef-25ceb169dfd6 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ad63a976-8561-431b-aeef-25ceb169dfd6/IMG_4971-13_47_52.jpeg | 2026-05-03 | 43.1674 | 9.1086 | Overall site | In Progress | ESHS MEETING | 16 | robelw@msconsultancyet.com | N/A | 2026-05-04 10:49:41 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ad63a976-8561-431b-aeef-25ceb169dfd6/IMG_4966-13_48_13.jpeg
uuid:f405823a-2907-45c7-b304-f408746d4b16 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f405823a-2907-45c7-b304-f408746d4b16/1777559642185.jpg | 2026-04-30 | 43.2191 | 9.8103 | Boreholes Auxiliary Buildings | Stalled | The activities currently stalled due to shortages of labor | 45 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-04-30 14:45:36 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f405823a-2907-45c7-b304-f408746d4b16/1777559651765.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f405823a-2907-45c7-b304-f408746d4b16/1777559665319.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f405823a-2907-45c7-b304-f408746d4b16/1777559681565.jpg
uuid:29961280-3a2f-4e35-b081-151d34950cee | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_29961280-3a2f-4e35-b081-151d34950cee/1777554994000.jpg | 2026-04-30 | 43.1282 | 9.6806 | Village water point | In Progress | Good progress | 75 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-04-30 14:45:23 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_29961280-3a2f-4e35-b081-151d34950cee/1777555011930.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_29961280-3a2f-4e35-b081-151d34950cee/1777555040412.jpg
uuid:c77b8077-caf5-4b84-82c0-68dfff7969de | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c77b8077-caf5-4b84-82c0-68dfff7969de/1777554335420.jpg | 2026-04-30 | 43.1318 | 9.6856 | Shedder utility office | In Progress | Slow progress | 50 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-04-30 13:07:28 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c77b8077-caf5-4b84-82c0-68dfff7969de/1777554348556.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c77b8077-caf5-4b84-82c0-68dfff7969de/1777554371097.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c77b8077-caf5-4b84-82c0-68dfff7969de/1777554415715.jpg
uuid:518fa9b1-aa10-4593-9fd7-d344e4b3ed19 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_518fa9b1-aa10-4593-9fd7-d344e4b3ed19/1777554133791.jpg | 2026-04-30 | 43.1317 | 9.6853 | 100m3 service Resrvoir | Stalled | The activities stopped due to the contractor's crew left the site | 50 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-04-30 13:04:07 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_518fa9b1-aa10-4593-9fd7-d344e4b3ed19/1777554154403.jpg
uuid:cd2d3a82-7dcd-4f73-a693-f8f71160b72e | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_cd2d3a82-7dcd-4f73-a693-f8f71160b72e/1777553937622.jpg | 2026-04-30 | 43.1315 | 9.6854 | 250m3 service reservior | In Progress | Slow progress | 70 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-04-30 13:01:25 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_cd2d3a82-7dcd-4f73-a693-f8f71160b72e/1777553981781.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_cd2d3a82-7dcd-4f73-a693-f8f71160b72e/1777554013772.jpg
uuid:f069a17d-9dcb-41a2-a479-0ba95407c2cf | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f069a17d-9dcb-41a2-a479-0ba95407c2cf/1777551948181.jpg | 2026-04-30 | 43.2146 | 9.7757 | AW-Barre utility office | In Progress | Slow progress | 55 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-04-30 13:01:18 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f069a17d-9dcb-41a2-a479-0ba95407c2cf/1777551975168.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f069a17d-9dcb-41a2-a479-0ba95407c2cf/1777551995402.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f069a17d-9dcb-41a2-a479-0ba95407c2cf/1777552035704.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f069a17d-9dcb-41a2-a479-0ba95407c2cf/1777552113701.jpg
uuid:d25dbd24-b9b0-4290-966b-4ca5f4afbe6f | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d25dbd24-b9b0-4290-966b-4ca5f4afbe6f/1777551549027.jpg | 2026-04-30 | 43.2115 | 9.7831 | 400m3 service Reservior | In Progress | Slow progress | 70 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-04-30 12:29:05 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d25dbd24-b9b0-4290-966b-4ca5f4afbe6f/1777551575003.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d25dbd24-b9b0-4290-966b-4ca5f4afbe6f/1777551605995.jpg
uuid:20f5765b-44e3-4413-82aa-8af21a86beba | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_20f5765b-44e3-4413-82aa-8af21a86beba/1777535892844.jpg | 2026-03-22 | 43.2221 | 9.7842 | Distribution pipeline installations for town | In Progress | Slow progress | 50 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-04-30 12:28:58 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_20f5765b-44e3-4413-82aa-8af21a86beba/1777535986327.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_20f5765b-44e3-4413-82aa-8af21a86beba/1777536025173.jpg
uuid:cf13b835-924b-4f3c-94af-35b5b8dae2a7 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_cf13b835-924b-4f3c-94af-35b5b8dae2a7/1774860777824.jpg | 2026-03-30 | 43.1271 | 9.6306 | New Borehole Auxiliary buildings | In Progress | Very slow | 15 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-30 08:54:56 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_cf13b835-924b-4f3c-94af-35b5b8dae2a7/1774860796929.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_cf13b835-924b-4f3c-94af-35b5b8dae2a7/1774860816949.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_cf13b835-924b-4f3c-94af-35b5b8dae2a7/1774860845088.jpg
uuid:90240e12-3718-415d-9ef8-28ce04ba209e | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_90240e12-3718-415d-9ef8-28ce04ba209e/1774859941983.jpg | 2026-03-30 | 43.1326 | 9.6302 | Public water points at rural village | Stalled | Four public water point commenced and currently at same ststus. | 60 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-30 08:54:44 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_90240e12-3718-415d-9ef8-28ce04ba209e/1774859965709.jpg
uuid:8ef5dbe4-1c07-40a5-803b-52a2c4592dab | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8ef5dbe4-1c07-40a5-803b-52a2c4592dab/1774859210624.jpg | 2026-03-30 | 43.124 | 9.6463 | Local Borehole Auxiliary buildings | In Progress | Slow progress | 20 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-30 08:29:39 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8ef5dbe4-1c07-40a5-803b-52a2c4592dab/1774859249527.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8ef5dbe4-1c07-40a5-803b-52a2c4592dab/1774859265032.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8ef5dbe4-1c07-40a5-803b-52a2c4592dab/1774859311138.jpg
uuid:d0c89890-2627-4058-b9fa-efd18928efc9 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d0c89890-2627-4058-b9fa-efd18928efc9/1774858537753.jpg | 2026-03-30 | 43.1266 | 9.6557 | Rural village Distribution pipeline installation | In Progress | Good progress | 25 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-30 08:19:23 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d0c89890-2627-4058-b9fa-efd18928efc9/1774858555465.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d0c89890-2627-4058-b9fa-efd18928efc9/1774858570810.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d0c89890-2627-4058-b9fa-efd18928efc9/1774858695095.jpg
uuid:dfa7ebef-9b6c-4688-8574-3ee7c579f36c | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dfa7ebef-9b6c-4688-8574-3ee7c579f36c/1774856647151.jpg | 2026-03-30 | 43.1318 | 9.6857 | Utility office | In Progress | Slow progress | 45 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-30 07:55:23 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dfa7ebef-9b6c-4688-8574-3ee7c579f36c/1774856714284.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dfa7ebef-9b6c-4688-8574-3ee7c579f36c/1774857101755.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dfa7ebef-9b6c-4688-8574-3ee7c579f36c/1774857121288.jpg
uuid:9352fdfe-01d6-4dc9-b2d5-53b85a7c29ac | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_9352fdfe-01d6-4dc9-b2d5-53b85a7c29ac/1774855707252.jpg | 2026-03-30 | 43.1316 | 9.6851 | 100m3 elevated service Reservoir | In Progress | Slow progress | 20 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-30 07:30:30 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_9352fdfe-01d6-4dc9-b2d5-53b85a7c29ac/1774855738729.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_9352fdfe-01d6-4dc9-b2d5-53b85a7c29ac/1774855767382.jpg
uuid:5ef4368c-78e1-4e7c-9721-3f4cc748ccdf | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_5ef4368c-78e1-4e7c-9721-3f4cc748ccdf/1774855298926.jpg | 2026-03-30 | 43.1312 | 9.6852 | 250m3 service Reservoir | In Progress | Good progress the civil work will be completed upcoming reporting month(April ) | 75 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-30 07:26:46 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_5ef4368c-78e1-4e7c-9721-3f4cc748ccdf/1774855309770.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_5ef4368c-78e1-4e7c-9721-3f4cc748ccdf/1774855467771.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_5ef4368c-78e1-4e7c-9721-3f4cc748ccdf/1774855479698.jpg
uuid:018aacad-f540-472c-a498-d7f5d400187d | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_018aacad-f540-472c-a498-d7f5d400187d/1774854371903.jpg | 2026-03-30 | 43.132 | 9.696 | Refuge pipeline installation | In Progress | Good progress | 15 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-30 07:11:14 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_018aacad-f540-472c-a498-d7f5d400187d/1774854382763.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_018aacad-f540-472c-a498-d7f5d400187d/1774854418608.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_018aacad-f540-472c-a498-d7f5d400187d/1774854604838.jpg
uuid:c95142b8-a38e-4016-87fc-c6c7c28b5c46 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c95142b8-a38e-4016-87fc-c6c7c28b5c46/1774852454799.jpg | 2026-03-30 | 43.2145 | 9.7754 | Utility Office | In Progress | Good progress | 65 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-30 06:38:22 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c95142b8-a38e-4016-87fc-c6c7c28b5c46/1774852580921.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c95142b8-a38e-4016-87fc-c6c7c28b5c46/1774852612734.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c95142b8-a38e-4016-87fc-c6c7c28b5c46/1774852630208.jpg
uuid:a900b823-e7e3-4ec6-bd13-18da73b44d7b | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a900b823-e7e3-4ec6-bd13-18da73b44d7b/1774851655066.jpg | 2026-03-30 | 43.2118 | 9.7834 | 400m3 service Reservoir | In Progress | Good progress | 60 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-30 06:28:12 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a900b823-e7e3-4ec6-bd13-18da73b44d7b/1774851789323.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a900b823-e7e3-4ec6-bd13-18da73b44d7b/1774851962329.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a900b823-e7e3-4ec6-bd13-18da73b44d7b/1774852020494.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a900b823-e7e3-4ec6-bd13-18da73b44d7b/1774852040073.jpg
uuid:a07576b9-158c-4f5f-91bd-f3ba766bf57c | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a07576b9-158c-4f5f-91bd-f3ba766bf57c/1774850483647.jpg | 2026-03-30 | 43.2205 | 9.7878 | Town distribution pipe line installations | In Progress | Good progress | 30 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-30 06:08:15 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a07576b9-158c-4f5f-91bd-f3ba766bf57c/1774850645330.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a07576b9-158c-4f5f-91bd-f3ba766bf57c/1774850697492.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a07576b9-158c-4f5f-91bd-f3ba766bf57c/1774850773106.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a07576b9-158c-4f5f-91bd-f3ba766bf57c/1774850813532.jpg
uuid:58c03394-7060-4c2b-9cfc-12f6e9f977f3 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_58c03394-7060-4c2b-9cfc-12f6e9f977f3/1774848337852.jpg | 2026-03-30 | 43.2172 | 9.8141 | Auxiliary buildings at Borehole | In Progress | All boreholes at similar status | 50 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-30 05:57:13 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_58c03394-7060-4c2b-9cfc-12f6e9f977f3/1774848352658.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_58c03394-7060-4c2b-9cfc-12f6e9f977f3/1774848387522.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_58c03394-7060-4c2b-9cfc-12f6e9f977f3/1774848403419.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_58c03394-7060-4c2b-9cfc-12f6e9f977f3/1774848448960.jpg
uuid:fc66da44-37b0-485b-aeaa-753f06405452 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_fc66da44-37b0-485b-aeaa-753f06405452/IMG_3540-18_10_49.jpeg | 2026-03-23 | 43.1673 | 9.1095 | Service reservoir site | In Progress | March 23, 2026 His Excellency Mustafe Mohammed Omer, the somali regional president along with his delegates, SRSWB representative’s visited the R-WASH Water Supply Construction Project site to review the ongoing works and assess progress. | 14 | robelw@msconsultancyet.com | N/A | 2026-03-23 15:12:23 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_fc66da44-37b0-485b-aeaa-753f06405452/IMG_3536-18_11_2.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_fc66da44-37b0-485b-aeaa-753f06405452/IMG_3533-18_11_13.jpeg
uuid:0a02b543-a96d-4fbd-88cb-537599c5dc3d | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0a02b543-a96d-4fbd-88cb-537599c5dc3d/IMG_3384-11_23_22.png | 2026-03-19 | 43.1673 | 9.1088 | All project site | In Progress | Dear All, The ongoing fuel shortage has begun to adversely impact the progress of the KEB R-WASH Water Supply Construction works. The Contractor is therefore advised to explore and secure alternative fuel supply arrangements to mitigate further delays. At the same time, the Employer is requested to extend support and coordinate with local and regional government authorities to facilitate fuel allocation for the project. Thank you. | 14 | robelw@msconsultancyet.com | N/A | 2026-03-19 08:23:56 | N/A
uuid:64d84f36-8ff3-49b5-889e-2c5e0c6d57ec | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_64d84f36-8ff3-49b5-889e-2c5e0c6d57ec/1773671219663.jpg | 2026-03-16 | 43.1315 | 9.6855 | Utility office | In Progress | Slow progress due to workforce shortage | 45 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-16 14:29:27 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_64d84f36-8ff3-49b5-889e-2c5e0c6d57ec/1773671257210.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_64d84f36-8ff3-49b5-889e-2c5e0c6d57ec/1773671289442.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_64d84f36-8ff3-49b5-889e-2c5e0c6d57ec/1773671301379.jpg
uuid:060e5840-729c-4304-9907-a46a36f3e67b | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_060e5840-729c-4304-9907-a46a36f3e67b/1773670931361.jpg | 2026-03-16 | 43.1317 | 9.6853 | 100m3 elevated service Reservoir | Stalled | Stopped since start of march due to manpower shortage | 20 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-16 14:24:35 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_060e5840-729c-4304-9907-a46a36f3e67b/1773670992427.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_060e5840-729c-4304-9907-a46a36f3e67b/1773671013192.jpg
uuid:043e98b4-d1af-41dd-a62a-7f0b85810207 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_043e98b4-d1af-41dd-a62a-7f0b85810207/1773670670847.jpg | 2026-03-16 | 43.1314 | 9.6852 | 250m3 service Reservoir | In Progress | Good progress | 53 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-16 14:20:33 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_043e98b4-d1af-41dd-a62a-7f0b85810207/1773670684376.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_043e98b4-d1af-41dd-a62a-7f0b85810207/1773670774087.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_043e98b4-d1af-41dd-a62a-7f0b85810207/1773670786054.jpg
uuid:6f4396e9-bb8f-4922-9667-e558fc80a16c | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_6f4396e9-bb8f-4922-9667-e558fc80a16c/1773669650649.jpg | 2026-03-16 | 43.1307 | 9.6494 | Rural village Water point | In Progress | Three water points at the same status, and slow progress | 55 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-16 14:20:27 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_6f4396e9-bb8f-4922-9667-e558fc80a16c/1773669667199.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_6f4396e9-bb8f-4922-9667-e558fc80a16c/1773669693140.jpg
uuid:3996130f-cb11-467e-a2ce-d1a61fb46fcf | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_3996130f-cb11-467e-a2ce-d1a61fb46fcf/1773669207912.jpg | 2026-03-16 | 43.124 | 9.6462 | Borehole Auxiliary buildings(generator house, conteol room and Guard House) at New BH and local BH. | Stalled | The actuvities stopped due to manpower shortage, at both boreholes and similar status. | 8 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-16 14:20:24 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_3996130f-cb11-467e-a2ce-d1a61fb46fcf/1773669229748.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_3996130f-cb11-467e-a2ce-d1a61fb46fcf/1773669256077.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_3996130f-cb11-467e-a2ce-d1a61fb46fcf/1773669273167.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_3996130f-cb11-467e-a2ce-d1a61fb46fcf/1773669366515.jpg
uuid:3f38e9dd-bfab-496a-b2fc-ebba034ee460 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_3f38e9dd-bfab-496a-b2fc-ebba034ee460/1773667720597.jpg | 2026-03-16 | 43.1258 | 9.6664 | Rural village distribution pipeline | In Progress | Good progress | 10 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-16 13:37:14 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_3f38e9dd-bfab-496a-b2fc-ebba034ee460/1773667731220.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_3f38e9dd-bfab-496a-b2fc-ebba034ee460/1773668170483.jpg
uuid:f4901e8a-01d8-4d48-9bb3-a3dd2c484c01 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f4901e8a-01d8-4d48-9bb3-a3dd2c484c01/1773650696770.jpg | 2026-03-16 | 43.2191 | 9.8103 | BH Guard House | In Progress | All Boreholes(BH 1,BH 4, BH new) Guard house has the same status. | 30 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-16 13:27:01 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f4901e8a-01d8-4d48-9bb3-a3dd2c484c01/1773650725476.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f4901e8a-01d8-4d48-9bb3-a3dd2c484c01/1773650749985.jpg
uuid:90e074d2-de8d-4ec7-82a7-40500081c6d6 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_90e074d2-de8d-4ec7-82a7-40500081c6d6/1773650330751.jpg | 2026-03-16 | 43.219 | 9.8103 | BH control rooms | In Progress | All Boreholes(BH new, BH 4, and BH 5) control room status are rhe same. | 35 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-16 09:04:51 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_90e074d2-de8d-4ec7-82a7-40500081c6d6/1773650362519.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_90e074d2-de8d-4ec7-82a7-40500081c6d6/1773650386693.jpg
uuid:10cf7f02-535e-494f-bdc0-cf7da1ce4a83 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_10cf7f02-535e-494f-bdc0-cf7da1ce4a83/1773649188755.jpg | 2026-03-16 | 43.2147 | 9.7754 | Utility Office | In Progress | Slow progess | 45 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-16 08:20:34 | N/A
uuid:98d99b39-cf40-40cf-84d0-d891d5bd147f | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_98d99b39-cf40-40cf-84d0-d891d5bd147f/1773648802056.jpg | 2026-03-16 | 43.2119 | 9.7834 | Transmission pipe line | Completed | Transmission pipeline installation completed except pressure test and fitting installation | N/A | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-16 08:15:29 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_98d99b39-cf40-40cf-84d0-d891d5bd147f/1773648727680.jpg
uuid:7c63dd29-2181-4b87-b974-759aa88f4f3e | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7c63dd29-2181-4b87-b974-759aa88f4f3e/1773647948029.jpg | 2026-03-16 | 43.2202 | 9.7815 | 400 service Reservoir | In Progress | Slow progress | 40 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-16 08:07:42 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7c63dd29-2181-4b87-b974-759aa88f4f3e/1773647959404.jpg
uuid:65cd0900-64ce-48af-99df-71d4b3631cf1 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_65cd0900-64ce-48af-99df-71d4b3631cf1/1773563925288.jpg | 2026-03-15 | 43.2236 | 9.7844 | Town Distribution pipeline installation | In Progress | Good progress | 15 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-15 08:40:46 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_65cd0900-64ce-48af-99df-71d4b3631cf1/1773563968051.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_65cd0900-64ce-48af-99df-71d4b3631cf1/1773563995595.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_65cd0900-64ce-48af-99df-71d4b3631cf1/1773564011818.jpg
uuid:549266c4-c768-44c8-b66c-259c79c04529 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_549266c4-c768-44c8-b66c-259c79c04529/IMG_3014-22_12_51.jpeg | 2026-03-03 | 43.0077 | 8.9973 | Kbps-01 | In Progress | Elevated backwash tank 50m3, 4th ring beam construction | 13 | robelw@msconsultancyet.com | N/A | 2026-03-08 19:15:04 | N/A
uuid:033d1669-5714-4164-b476-65c4db07a2d2 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_033d1669-5714-4164-b476-65c4db07a2d2/IMG_3066-22_10_11.jpeg | 2026-03-02 | 43.0096 | 9.0011 | Kbps-01 | In Progress | clear water pump station | 13 | robelw@msconsultancyet.com | N/A | 2026-03-08 19:11:28 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_033d1669-5714-4164-b476-65c4db07a2d2/IMG_2897-22_10_36.jpeg
uuid:8aec40a0-a4bf-4afd-8417-a94254f05398 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8aec40a0-a4bf-4afd-8417-a94254f05398/IMG_3065-22_8_30.jpeg | 2026-03-01 | 43.0997 | 9.0601 | Kbps-02 | In Progress | 100m3 reservoir pavement work | 13 | robelw@msconsultancyet.com | N/A | 2026-03-08 19:09:01 | N/A
uuid:8668a760-bb01-473b-a4b4-a068ca228675 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8668a760-bb01-473b-a4b4-a068ca228675/1772204450293.jpg | 2026-02-27 | 43.2172 | 9.814 | Guard house at New Borehole | In Progress | Good progress | 30 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-03 12:43:12 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8668a760-bb01-473b-a4b4-a068ca228675/1772204471394.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8668a760-bb01-473b-a4b4-a068ca228675/1772204498474.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8668a760-bb01-473b-a4b4-a068ca228675/1772204523019.jpg
uuid:348516db-19b0-440a-9906-66d879703aa7 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_348516db-19b0-440a-9906-66d879703aa7/1772204260398.jpg | 2026-02-27 | 43.2171 | 9.814 | Generator house at New Borehole | In Progress | Good progress | 35 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-03-03 12:43:10 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_348516db-19b0-440a-9906-66d879703aa7/1772204285779.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_348516db-19b0-440a-9906-66d879703aa7/1772204313269.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_348516db-19b0-440a-9906-66d879703aa7/1772204344537.jpg
uuid:dfe615e9-be5a-477e-8267-c6c42ee32bdb | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dfe615e9-be5a-477e-8267-c6c42ee32bdb/1772204063001.jpg | 2026-02-27 | 43.2171 | 9.8141 | Control room at New Borehole | In Progress | Good progress | 20 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-27 15:01:31 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dfe615e9-be5a-477e-8267-c6c42ee32bdb/1772204087756.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dfe615e9-be5a-477e-8267-c6c42ee32bdb/1772204125712.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dfe615e9-be5a-477e-8267-c6c42ee32bdb/1772204150657.jpg
uuid:d142c26b-7771-42c8-8027-262fc0920dfc | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d142c26b-7771-42c8-8027-262fc0920dfc/1772202579031.jpg | 2026-02-27 | 43.2143 | 9.7756 | Utility Office | In Progress | Good progress | 45 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-27 14:32:27 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d142c26b-7771-42c8-8027-262fc0920dfc/1772202616237.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d142c26b-7771-42c8-8027-262fc0920dfc/1772202661987.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d142c26b-7771-42c8-8027-262fc0920dfc/1772202680388.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d142c26b-7771-42c8-8027-262fc0920dfc/1772202707607.jpg
uuid:e8ccf297-6e35-4a64-8b98-8675de507f25 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e8ccf297-6e35-4a64-8b98-8675de507f25/1772198253154.jpg | 2026-02-27 | 43.2118 | 9.7834 | 400m3 service Reservoir | In Progress | Slow progress | 35 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-27 13:21:35 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e8ccf297-6e35-4a64-8b98-8675de507f25/1772198322549.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e8ccf297-6e35-4a64-8b98-8675de507f25/1772198427278.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e8ccf297-6e35-4a64-8b98-8675de507f25/1772198444552.jpg
uuid:a7aeab5b-6a5c-41e2-9616-a8ac51253cc2 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a7aeab5b-6a5c-41e2-9616-a8ac51253cc2/1772179910692.jpg | 2026-02-27 | 43.1273 | 9.6308 | Generator house at New Borehole | In Progress | Commenced today February 27/2026, good progress. | 10 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-27 13:12:20 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a7aeab5b-6a5c-41e2-9616-a8ac51253cc2/1772179943051.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a7aeab5b-6a5c-41e2-9616-a8ac51253cc2/1772179955405.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a7aeab5b-6a5c-41e2-9616-a8ac51253cc2/1772179962908.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a7aeab5b-6a5c-41e2-9616-a8ac51253cc2/1772179985139.jpg
uuid:dff34e77-4886-488d-9f1c-f612dd6e9617 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dff34e77-4886-488d-9f1c-f612dd6e9617/1772178968524.jpg | 2026-02-27 | 43.1343 | 9.6405 | Rural village water points | In Progress | Good progress | 45 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-27 08:07:48 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dff34e77-4886-488d-9f1c-f612dd6e9617/1772178979075.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dff34e77-4886-488d-9f1c-f612dd6e9617/1772179001531.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dff34e77-4886-488d-9f1c-f612dd6e9617/1772179019333.jpg
uuid:ee354ae5-3b12-4a85-8ddc-3bab51c49b98 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ee354ae5-3b12-4a85-8ddc-3bab51c49b98/1772177573314.jpg | 2026-02-27 | 43.1269 | 9.6708 | Transmission and collector pipelines and fitting installation | Stalled | The pipeline work has been stopping since February 10 because of machine broken onsite. | 34 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-27 07:39:44 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ee354ae5-3b12-4a85-8ddc-3bab51c49b98/1772177581439.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ee354ae5-3b12-4a85-8ddc-3bab51c49b98/1772177588871.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ee354ae5-3b12-4a85-8ddc-3bab51c49b98/1772177753441.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ee354ae5-3b12-4a85-8ddc-3bab51c49b98/1772177769593.jpg
uuid:0b84f27b-7d0b-4bdf-8fa2-f57733862641 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0b84f27b-7d0b-4bdf-8fa2-f57733862641/1772176079975.jpg | 2026-02-27 | 43.1314 | 9.6852 | 250m3 Service Reservoir | In Progress | Slow progress, shortage of manpower(carpenter) | 40 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-27 07:10:50 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0b84f27b-7d0b-4bdf-8fa2-f57733862641/1772176092238.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0b84f27b-7d0b-4bdf-8fa2-f57733862641/1772176118973.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0b84f27b-7d0b-4bdf-8fa2-f57733862641/1772176162364.jpg
uuid:7e50bb44-a220-4416-8442-b53a93840761 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7e50bb44-a220-4416-8442-b53a93840761/1772175464656.jpg | 2026-02-27 | 43.1317 | 9.6853 | 100m3 | In Progress | Very very slow progress, almost stoped | 16 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-27 06:59:40 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7e50bb44-a220-4416-8442-b53a93840761/1772175486465.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7e50bb44-a220-4416-8442-b53a93840761/1772175505960.jpg
uuid:f581f152-648e-492b-8a52-a63c8138231e | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f581f152-648e-492b-8a52-a63c8138231e/1772175235106.jpg | 2026-02-27 | 43.132 | 9.6855 | Utility office | Stalled | The progress halted since October month due to manpower and material shortage | 35 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-27 06:55:48 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f581f152-648e-492b-8a52-a63c8138231e/1772175245432.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f581f152-648e-492b-8a52-a63c8138231e/1772175268487.jpg
uuid:78c98610-8246-4737-b472-32ed6a24a4b2 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_78c98610-8246-4737-b472-32ed6a24a4b2/cefcce618fbf8a50752612d54c7963be-15_13_14.jpeg | 2026-02-25 | 43.1674 | 9.1097 | All sites under the project | In Progress | DAILY SITE REPORT Date: 25/02/2026 Reference: MoM No. 08 Following the rejection of previous work requests, ESHS compliance and PPE use on site have improved. Remaining checklist items are being implemented as per the MoM No. 08 action plan. Supervision will continue until full compliance is achieved. | 13 | robelw@msconsultancyet.com | N/A | 2026-02-25 12:20:51 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_78c98610-8246-4737-b472-32ed6a24a4b2/IMG_2702-15_15_15.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_78c98610-8246-4737-b472-32ed6a24a4b2/CamScanner%202-21-26%2015.07_1-15_20_7.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_78c98610-8246-4737-b472-32ed6a24a4b2/CamScanner%202-21-26%2015.07_2-15_20_15.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_78c98610-8246-4737-b472-32ed6a24a4b2/e5426e547810daccd7a7f2785a3e9bb4-15_20_41.jpeg
uuid:0992cb9b-3ee8-40f6-9cc4-58e022ba4e6b | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0992cb9b-3ee8-40f6-9cc4-58e022ba4e6b/IMG_2553-15_7_42.jpeg | 2026-02-20 | 43.1675 | 9.1096 | All project sites | In Progress | Date: 21 February 2026 Reference: Site Investigation (20 February 2026) and MoM No. 08 A site investigation was conducted to verify the Contractor’s submissions against actual field conditions. Non compliance was observed in ESHS implementation, PPE availability, Right of Way preparation, and site housekeeping. Photographic and video evidence were recorded. During MoM No. 08, the findings were formally presented. The Contractor was instructed to immediately fulfill all ESHS requirements, provide adequate PPE to all workers, properly prepare the Right of Way, and correct discrepancies without delay. Continued non compliance will result in contractual measures | 13 | robelw@msconsultancyet.com | N/A | 2026-02-25 12:12:12 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0992cb9b-3ee8-40f6-9cc4-58e022ba4e6b/IMG_2555-15_8_24.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0992cb9b-3ee8-40f6-9cc4-58e022ba4e6b/IMG_2582-15_8_46.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0992cb9b-3ee8-40f6-9cc4-58e022ba4e6b/IMG_2602-15_9_14.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0992cb9b-3ee8-40f6-9cc4-58e022ba4e6b/IMG_2595-15_9_34.jpeg
uuid:bb1452e2-3de1-45ba-89f7-6d776397996d | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bb1452e2-3de1-45ba-89f7-6d776397996d/IMG_2468-9_27_25.jpeg | 2026-02-20 | 43.0204 | 9.0099 | Kbps01 | In Progress | 150m3 reservoir internal and external wall plastering and rendering work underwork progress | 13 | robelw@msconsultancyet.com | N/A | 2026-02-20 06:29:06 | N/A
uuid:f9e1d989-4457-457a-bfc0-1d77946c70d9 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f9e1d989-4457-457a-bfc0-1d77946c70d9/IMG_2479-9_23_5.jpeg | 2026-02-13 | 43.0867 | 9.0475 | Kbps02 | In Progress | 100m3 reservoir works remains reservoir pipe connection and and preparation work for the pavement work is under progress | 13 | robelw@msconsultancyet.com | N/A | 2026-02-20 06:24:34 | N/A
uuid:b6a7a2d5-4106-458d-8348-7ca895680294 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b6a7a2d5-4106-458d-8348-7ca895680294/IMG_2465-9_20_18.jpeg | 2026-02-19 | 43.0183 | 9.0102 | Kbps-01 | In Progress | clear water pumping station floor slab rebar and formwork installation and concrete fence post concrete casting | 13 | robelw@msconsultancyet.com | N/A | 2026-02-20 06:21:49 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b6a7a2d5-4106-458d-8348-7ca895680294/IMG_2466-9_20_46.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b6a7a2d5-4106-458d-8348-7ca895680294/IMG_2458-9_21_43.jpeg
uuid:873c872a-9dc4-4d46-844a-7d63d11fab15 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_873c872a-9dc4-4d46-844a-7d63d11fab15/IMG_2474-9_17_32.jpeg | 2026-02-16 | 43.1674 | 9.1084 | Service reservoir | In Progress | utility office external pavement concrete work and rehabilitation walkway around the utility office | 13 | robelw@msconsultancyet.com | N/A | 2026-02-20 06:19:13 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_873c872a-9dc4-4d46-844a-7d63d11fab15/IMG_2437-9_18_0.jpeg
uuid:68a1b963-1f4f-423b-ab66-aefd9235bd27 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_68a1b963-1f4f-423b-ab66-aefd9235bd27/IMG_2443-9_15_9.jpeg | 2026-02-19 | 43.1674 | 9.1097 | Service reservoir | In Progress | Elevated reservoirs top tanker rebar form work and concrete works underway | 13 | robelw@msconsultancyet.com | N/A | 2026-02-20 06:16:25 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_68a1b963-1f4f-423b-ab66-aefd9235bd27/IMG_2473-9_15_26.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_68a1b963-1f4f-423b-ab66-aefd9235bd27/IMG_2475-9_15_43.jpeg
uuid:221d3908-b669-400e-90a7-1ab1b07b085f | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_221d3908-b669-400e-90a7-1ab1b07b085f/IMG_2461-9_12_5.jpeg | 2026-02-18 | 43.0183 | 9.0092 | Kbps-01 | In Progress | Backwash tank 50m3 | 13 | robelw@msconsultancyet.com | N/A | 2026-02-20 06:13:47 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_221d3908-b669-400e-90a7-1ab1b07b085f/IMG_2459-9_12_32.jpeg
uuid:7d56431d-4e9f-4960-9930-ad8e232d646e | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7d56431d-4e9f-4960-9930-ad8e232d646e/1771405070238.jpg | 2026-02-18 | 43.1267 | 9.6706 | Transmission pipe and fitting installations | In Progress | Slow progress | 34 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-18 09:04:50 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7d56431d-4e9f-4960-9930-ad8e232d646e/1771405438695.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7d56431d-4e9f-4960-9930-ad8e232d646e/1771405228543.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7d56431d-4e9f-4960-9930-ad8e232d646e/1771405114477.jpg
uuid:32899ee8-1319-45a6-aa98-b8ba79560b96 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_32899ee8-1319-45a6-aa98-b8ba79560b96/1771403245939.jpg | 2026-02-18 | 43.1314 | 9.6859 | Supply pipe and fittings | Stalled | Pipelines pipe and fittings already supplied during September month but not completed yet. | 95 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-18 08:35:22 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_32899ee8-1319-45a6-aa98-b8ba79560b96/1771403261871.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_32899ee8-1319-45a6-aa98-b8ba79560b96/1771403345180.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_32899ee8-1319-45a6-aa98-b8ba79560b96/1771403564994.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_32899ee8-1319-45a6-aa98-b8ba79560b96/1771403621996.jpg
uuid:f4e85330-c38f-4cd6-8f76-6bfa2d76d9ee | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f4e85330-c38f-4cd6-8f76-6bfa2d76d9ee/1771401886445.jpg | 2026-02-18 | 43.1315 | 9.6853 | 250m3 ground Service Reservoir | In Progress | Currently under construction of re-bar fixing and formwork for the wall. | 24 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-18 08:08:09 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f4e85330-c38f-4cd6-8f76-6bfa2d76d9ee/1771401910577.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f4e85330-c38f-4cd6-8f76-6bfa2d76d9ee/1771401927898.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f4e85330-c38f-4cd6-8f76-6bfa2d76d9ee/1771401961342.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f4e85330-c38f-4cd6-8f76-6bfa2d76d9ee/1771401994266.jpg
uuid:76ac96fc-442e-4195-a9c4-13d331a27562 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_76ac96fc-442e-4195-a9c4-13d331a27562/1771401626607.jpg | 2026-02-18 | 43.1317 | 9.6853 | 100m3 Elevated service Reservior | In Progress | Slow progress | 16 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-18 08:03:10 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_76ac96fc-442e-4195-a9c4-13d331a27562/1771401655064.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_76ac96fc-442e-4195-a9c4-13d331a27562/1771401677714.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_76ac96fc-442e-4195-a9c4-13d331a27562/1771401720159.jpg
uuid:f6a0dec4-7ee4-43cf-a7dc-e6a9da0156d6 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f6a0dec4-7ee4-43cf-a7dc-e6a9da0156d6/1771401194355.jpg | 2026-02-18 | 43.1318 | 9.6857 | Utility office | Stalled | Since October month, the activity already stopped with unknown reasons | 32 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-18 07:58:46 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f6a0dec4-7ee4-43cf-a7dc-e6a9da0156d6/1771401242180.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f6a0dec4-7ee4-43cf-a7dc-e6a9da0156d6/1771401256372.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f6a0dec4-7ee4-43cf-a7dc-e6a9da0156d6/1771401292501.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f6a0dec4-7ee4-43cf-a7dc-e6a9da0156d6/1771401418750.jpg
uuid:655f1cfa-c504-435f-b81d-d4a671b37335 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_655f1cfa-c504-435f-b81d-d4a671b37335/1771398731205.jpg | 2026-02-17 | 43.2147 | 9.7757 | Utility office | In Progress | Slow progress | 36 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-18 07:18:51 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_655f1cfa-c504-435f-b81d-d4a671b37335/1771398765051.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_655f1cfa-c504-435f-b81d-d4a671b37335/1771398810203.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_655f1cfa-c504-435f-b81d-d4a671b37335/1771398999803.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_655f1cfa-c504-435f-b81d-d4a671b37335/1771399031393.jpg
uuid:0776550c-8621-45d8-861d-4f4652e10690 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0776550c-8621-45d8-861d-4f4652e10690/1771398095273.jpg | 2026-02-17 | 43.2115 | 9.7828 | Pipe and fitting supply | Stalled | Pipe and fittings for pipline alread supplied on September month, but not completed yet. | 94 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-18 07:07:08 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0776550c-8621-45d8-861d-4f4652e10690/1771398111605.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0776550c-8621-45d8-861d-4f4652e10690/1771398129006.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0776550c-8621-45d8-861d-4f4652e10690/1771398153643.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0776550c-8621-45d8-861d-4f4652e10690/1771398266313.jpg
uuid:4dd88988-503d-4afa-bfd0-78f210f85d4c | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_4dd88988-503d-4afa-bfd0-78f210f85d4c/1771397825858.jpg | 2026-02-17 | 43.2118 | 9.7833 | 400m3 Service Reservoir | In Progress | Slow progress, all slab re-bar completed and ready for concrete. | 22 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-18 07:00:19 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_4dd88988-503d-4afa-bfd0-78f210f85d4c/1771397844220.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_4dd88988-503d-4afa-bfd0-78f210f85d4c/1771397859720.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_4dd88988-503d-4afa-bfd0-78f210f85d4c/1771397901135.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_4dd88988-503d-4afa-bfd0-78f210f85d4c/1771397923604.jpg
uuid:ddb80214-44d7-45fa-b0fa-dac2a8b409f9 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ddb80214-44d7-45fa-b0fa-dac2a8b409f9/1771396700046.jpg | 2026-02-17 | 43.217 | 9.814 | Control room at New Borehole | In Progress | This activity commenced in February month, currently it is slow progress. | 1 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-18 06:56:21 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ddb80214-44d7-45fa-b0fa-dac2a8b409f9/1771396715479.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ddb80214-44d7-45fa-b0fa-dac2a8b409f9/1771396731488.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ddb80214-44d7-45fa-b0fa-dac2a8b409f9/1771396754222.jpg
uuid:ab96dfd8-e732-491f-92e3-e04a4faca7b7 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ab96dfd8-e732-491f-92e3-e04a4faca7b7/1771396413735.jpg | 2026-02-17 | 43.2171 | 9.8141 | Generator house at New Borehole | In Progress | This activity commenced in February month, it is very slow progress | 1 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-18 06:39:54 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ab96dfd8-e732-491f-92e3-e04a4faca7b7/1771396437166.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ab96dfd8-e732-491f-92e3-e04a4faca7b7/1771396466622.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ab96dfd8-e732-491f-92e3-e04a4faca7b7/1771396498115.jpg
uuid:6cf52b64-a2ca-4804-94fc-f06bdae6c9b4 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_6cf52b64-a2ca-4804-94fc-f06bdae6c9b4/1771395704172.jpg | 2026-02-17 | 43.2156 | 9.8064 | Transmission and transfer pipelines | In Progress | Slow progress, currently the the activity status reacched on 24% | 24 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-18 06:33:07 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_6cf52b64-a2ca-4804-94fc-f06bdae6c9b4/1771395759313.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_6cf52b64-a2ca-4804-94fc-f06bdae6c9b4/1771395792810.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_6cf52b64-a2ca-4804-94fc-f06bdae6c9b4/1771395823847.jpg
uuid:428ee79e-3cf2-4159-ab9f-1a34850be63d | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_428ee79e-3cf2-4159-ab9f-1a34850be63d/1771335955029.jpg | 2026-02-17 | 43.2147 | 9.7756 | Utility office | In Progress | Very slow | 28 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-17 13:50:32 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_428ee79e-3cf2-4159-ab9f-1a34850be63d/1771335977910.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_428ee79e-3cf2-4159-ab9f-1a34850be63d/1771335991081.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_428ee79e-3cf2-4159-ab9f-1a34850be63d/1771336047900.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_428ee79e-3cf2-4159-ab9f-1a34850be63d/1771336171409.jpg
uuid:bdc30a8c-de7a-432f-bf96-a0a8f1eb9535 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bdc30a8c-de7a-432f-bf96-a0a8f1eb9535/1771334759968.jpg | 2026-02-17 | 43.2127 | 9.7831 | 400m3 service Reservoir | In Progress | Very slow | 28 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-17 13:28:00 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bdc30a8c-de7a-432f-bf96-a0a8f1eb9535/1771334788356.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bdc30a8c-de7a-432f-bf96-a0a8f1eb9535/1771334817298.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bdc30a8c-de7a-432f-bf96-a0a8f1eb9535/1771334837822.jpg
uuid:80723bb7-846f-499f-8e62-7e3dac92437d | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_80723bb7-846f-499f-8e62-7e3dac92437d/1771333390456.jpg | 2026-02-17 | 43.217 | 9.8142 | New Borehole Generator house, control room and guard house building constructions | In Progress | Slow progress | 28 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-17 13:24:57 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_80723bb7-846f-499f-8e62-7e3dac92437d/1771333412702.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_80723bb7-846f-499f-8e62-7e3dac92437d/1771333483390.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_80723bb7-846f-499f-8e62-7e3dac92437d/1771333507718.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_80723bb7-846f-499f-8e62-7e3dac92437d/1771333539065.jpg
uuid:9ff8d20f-f93d-4761-838a-7fb204d0bede | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_9ff8d20f-f93d-4761-838a-7fb204d0bede/1771332879457.jpg | 2026-02-17 | 43.2151 | 9.806 | Transmission pipeline | In Progress | The progress is slow | 28 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-02-17 13:24:55 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_9ff8d20f-f93d-4761-838a-7fb204d0bede/1771332947641.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_9ff8d20f-f93d-4761-838a-7fb204d0bede/1771332986888.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_9ff8d20f-f93d-4761-838a-7fb204d0bede/1771332999289.jpg
uuid:e36d8741-6f7b-45c3-abf3-6b570e3c4892 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e36d8741-6f7b-45c3-abf3-6b570e3c4892/IMG_2306-10_29_9.jpeg | 2026-02-11 | 43.1676 | 9.1095 | Elevated reservoirs | In Progress | Elevated reservoirs •elevated reservoir no:1 top tanker wall and roof slab concrete casted the seconds elevated reservoir top tanker slab and wall rebar and form work underway | 12 | robelw@msconsultancyet.com | N/A | 2026-02-13 07:33:04 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e36d8741-6f7b-45c3-abf3-6b570e3c4892/IMG_2307-10_29_16.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e36d8741-6f7b-45c3-abf3-6b570e3c4892/IMG_2299-10_29_27.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e36d8741-6f7b-45c3-abf3-6b570e3c4892/IMG_2176-10_30_41.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e36d8741-6f7b-45c3-abf3-6b570e3c4892/IMG_2310-10_32_9.jpeg
uuid:cb0e6f40-850f-404d-845f-70f4fc89f635 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_cb0e6f40-850f-404d-845f-70f4fc89f635/IMG_2292-10_22_48.jpeg | 2026-02-12 | 43.1674 | 9.1084 | Utility office | In Progress | utility office external pavement work/ walkway | 12 | robelw@msconsultancyet.com | N/A | 2026-02-13 07:25:29 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_cb0e6f40-850f-404d-845f-70f4fc89f635/IMG_2295-10_22_58.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_cb0e6f40-850f-404d-845f-70f4fc89f635/IMG_2298-10_24_51.jpeg
uuid:746c3d23-b62c-4b80-a297-93bffce45d3e | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_746c3d23-b62c-4b80-a297-93bffce45d3e/IMG_1689-7_10_59.jpeg | 2026-01-26 | 43.0354 | 8.9731 | Borholes | In Progress | Borhole civil works under way at all borholes #4 | 10 | robelw@msconsultancyet.com | N/A | 2026-01-29 04:11:41 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_746c3d23-b62c-4b80-a297-93bffce45d3e/IMG_1688-7_11_5.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_746c3d23-b62c-4b80-a297-93bffce45d3e/IMG_1687-7_11_10.jpeg
uuid:c2ac44d6-b676-48d3-b65b-e8ab6d6aee7e | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c2ac44d6-b676-48d3-b65b-e8ab6d6aee7e/IMG_1684-7_5_27.jpeg | 2026-01-20 | 43.0944 | 9.0524 | Booster pump station number two-KBPS-02 | In Progress | kBPS-02, 100m3 tanker base sale and first lift wall rebar form work and concrete work | 10 | robelw@msconsultancyet.com | N/A | 2026-01-29 04:06:42 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c2ac44d6-b676-48d3-b65b-e8ab6d6aee7e/IMG_1685-7_5_32.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c2ac44d6-b676-48d3-b65b-e8ab6d6aee7e/IMG_1683-7_5_38.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c2ac44d6-b676-48d3-b65b-e8ab6d6aee7e/IMG_1686-7_5_44.jpeg
uuid:0cc8441b-a6e5-442b-9c65-ec9308f12c7f | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0cc8441b-a6e5-442b-9c65-ec9308f12c7f/IMG_1680-6_59_57.jpeg | 2026-01-27 | 43.1672 | 9.1086 | Utility office | In Progress | utility office wall work painting and finishing works underway | 10 | robelw@msconsultancyet.com | N/A | 2026-01-29 04:01:09 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0cc8441b-a6e5-442b-9c65-ec9308f12c7f/IMG_1679-7_0_5.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0cc8441b-a6e5-442b-9c65-ec9308f12c7f/IMG_1682-7_0_13.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0cc8441b-a6e5-442b-9c65-ec9308f12c7f/IMG_1681-7_0_18.jpeg
uuid:8d74a0e2-21a1-49d9-b845-bd77e3e8d835 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8d74a0e2-21a1-49d9-b845-bd77e3e8d835/IMG_1585-6_54_34.jpeg | 2026-01-28 | 43.1675 | 9.1098 | Elevated reservoir | In Progress | the two elevated reservoirs The shaft wall is completed 18m and the above tanker rebar form work and concrete work is underway | 10 | robelw@msconsultancyet.com | N/A | 2026-01-29 03:56:44 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8d74a0e2-21a1-49d9-b845-bd77e3e8d835/IMG_1676-6_54_41.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8d74a0e2-21a1-49d9-b845-bd77e3e8d835/IMG_1673-6_54_52.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8d74a0e2-21a1-49d9-b845-bd77e3e8d835/IMG_1675-6_55_5.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8d74a0e2-21a1-49d9-b845-bd77e3e8d835/IMG_1672-6_55_15.jpeg
uuid:59455d90-32b4-4bcc-a001-98082aa12081 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_59455d90-32b4-4bcc-a001-98082aa12081/1769502022602.jpg | 2026-01-27 | 43.123 | 9.6543 | Shedder transmission pipeline | In Progress | Good progress | 32 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-01-27 08:24:06 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_59455d90-32b4-4bcc-a001-98082aa12081/1769502053164.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_59455d90-32b4-4bcc-a001-98082aa12081/1769502068506.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_59455d90-32b4-4bcc-a001-98082aa12081/1769502147690.jpg
uuid:0edd4dd6-8419-49d6-91c4-f1f9e5054689 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0edd4dd6-8419-49d6-91c4-f1f9e5054689/1769499642071.jpg | 2026-01-27 | 43.1318 | 9.6855 | Utility office | In Progress | Slow progress due to unskilled and skilled manpower | 32 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-01-27 07:42:05 | N/A
uuid:126f17e0-3ecd-40a2-8cad-dbc9b9cf6b51 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_126f17e0-3ecd-40a2-8cad-dbc9b9cf6b51/1769499252451.jpg | 2026-01-27 | 43.1316 | 9.6852 | Service reservoir | In Progress | Slow progress | 32 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-01-27 07:38:02 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_126f17e0-3ecd-40a2-8cad-dbc9b9cf6b51/1769499275354.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_126f17e0-3ecd-40a2-8cad-dbc9b9cf6b51/1769499298073.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_126f17e0-3ecd-40a2-8cad-dbc9b9cf6b51/1769499321522.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_126f17e0-3ecd-40a2-8cad-dbc9b9cf6b51/1769499449669.jpg
uuid:3afd8d19-e056-4602-afe5-5151d713d9b1 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_3afd8d19-e056-4602-afe5-5151d713d9b1/1769496638394.jpg | 2026-01-26 | 43.2119 | 9.7833 | 400m3 service reservoir | In Progress | Very slow progress | 27 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-01-27 06:52:14 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_3afd8d19-e056-4602-afe5-5151d713d9b1/1769496651970.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_3afd8d19-e056-4602-afe5-5151d713d9b1/1769496674510.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_3afd8d19-e056-4602-afe5-5151d713d9b1/1769496694430.jpg
uuid:b61abb2e-5b27-471f-9f03-f67181a80b3b | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b61abb2e-5b27-471f-9f03-f67181a80b3b/1769495415306.jpg | 2026-01-27 | 43.2177 | 9.8092 | Transmission pipeline | In Progress | Very slow progress | 27 | N/A | collect:G2pcZJtXH1x4Swyk | 2026-01-27 06:48:52 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b61abb2e-5b27-471f-9f03-f67181a80b3b/1769495460796.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b61abb2e-5b27-471f-9f03-f67181a80b3b/1769495505872.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b61abb2e-5b27-471f-9f03-f67181a80b3b/1769495640199.jpg
uuid:d1b808e3-3c2d-4304-8b1e-e491aba321fc | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d1b808e3-3c2d-4304-8b1e-e491aba321fc/1767075088307.jpg | 2025-12-30 | 43.2147 | 9.7756 | Utility office | In Progress | The progress is very slow due to construction material, and machinery shortage. | 31 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-12-30 06:14:02 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d1b808e3-3c2d-4304-8b1e-e491aba321fc/1767075100417.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d1b808e3-3c2d-4304-8b1e-e491aba321fc/1767075115676.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d1b808e3-3c2d-4304-8b1e-e491aba321fc/1767075132671.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d1b808e3-3c2d-4304-8b1e-e491aba321fc/1767075144339.jpg
uuid:8c4cc2c2-ab25-418c-9f6a-f4325b0c7f75 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8c4cc2c2-ab25-418c-9f6a-f4325b0c7f75/1767073935774.jpg | 2025-12-30 | 43.2117 | 9.7833 | Service Reservoir(400m3) | Stalled | Entire activities at Aw-Barre site is already halted due to machinery, manpower, and construction material shortage. | 31 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-12-30 05:59:43 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8c4cc2c2-ab25-418c-9f6a-f4325b0c7f75/1767073969424.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8c4cc2c2-ab25-418c-9f6a-f4325b0c7f75/1767074046182.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8c4cc2c2-ab25-418c-9f6a-f4325b0c7f75/1767074073280.jpg
uuid:26f51814-fe20-48b6-b8cc-9e6a33071701 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_26f51814-fe20-48b6-b8cc-9e6a33071701/1766991987791.jpg | 2025-12-29 | 43.1203 | 9.6439 | Transmission and collector pipline | In Progress | Commenced and currently on good progress | 27 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-12-30 05:49:57 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_26f51814-fe20-48b6-b8cc-9e6a33071701/1766992062964.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_26f51814-fe20-48b6-b8cc-9e6a33071701/1766992077700.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_26f51814-fe20-48b6-b8cc-9e6a33071701/1766992092233.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_26f51814-fe20-48b6-b8cc-9e6a33071701/1766992114032.jpg
uuid:d9a9a174-7eae-47fd-9b26-048afd30cd29 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d9a9a174-7eae-47fd-9b26-048afd30cd29/IMG_0480-21_15_52.jpeg | 2025-12-29 | 43.0187 | 9.0099 | Booster pump station no-01(KBPS-01) | In Progress | 150m3 reservoir T the WTP Work underway | 8 | robelw@msconsultancyet.com | N/A | 2025-12-29 18:16:55 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d9a9a174-7eae-47fd-9b26-048afd30cd29/b6223f5f175dbf7444843e2eb371a29e-21_16_16.jpeg
uuid:c740cc5a-1588-4fc5-91aa-2cce74ac5b8d | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c740cc5a-1588-4fc5-91aa-2cce74ac5b8d/IMG_0500-21_8_38.jpeg | 2025-12-29 | 43.0274 | 8.9744 | Boreholes | In Progress | Boreholes auxiliary building works under progress | 8 | robelw@msconsultancyet.com | N/A | 2025-12-29 18:10:47 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c740cc5a-1588-4fc5-91aa-2cce74ac5b8d/IMG_0489-21_9_52.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c740cc5a-1588-4fc5-91aa-2cce74ac5b8d/IMG_0498-21_10_21.jpeg
uuid:22611ed8-334d-496f-953c-907c3b637825 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_22611ed8-334d-496f-953c-907c3b637825/e08c29c14a9c75aa835ddcc2ecd7a1b1-21_6_25.jpeg | 2025-12-29 | 43.1222 | 9.0762 | Booster pump station no2 ( KBPS-02) | In Progress | Kbps-02Site clearance and preparation work to commence 100m3 reservoir and reinforcement of the temporary fence | 8 | robelw@msconsultancyet.com | N/A | 2025-12-29 18:07:22 | N/A
uuid:aea55097-f83f-4cb5-b17a-3374dc7b2432 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_aea55097-f83f-4cb5-b17a-3374dc7b2432/de5b99808fe58f34161499f6cb70e38c-20_55_6.jpeg | 2025-12-29 | 43.1675 | 9.1082 | Utility office | In Progress | Utility office roof work | 8 | robelw@msconsultancyet.com | N/A | 2025-12-29 17:56:44 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_aea55097-f83f-4cb5-b17a-3374dc7b2432/IMG_0599-20_56_26.jpeg
uuid:44f0bf7d-c2b1-46cd-bf43-9e4c6d6c581f | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_44f0bf7d-c2b1-46cd-bf43-9e4c6d6c581f/IMG_0590-20_52_40.jpeg | 2025-12-29 | 43.1674 | 9.1098 | Elevated reservoirs | In Progress | elevated reservoirs shaft wall concrete casting | 8 | robelw@msconsultancyet.com | N/A | 2025-12-29 17:53:35 | N/A
uuid:a57c7d14-a322-42bb-978a-1089fdd960bf | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a57c7d14-a322-42bb-978a-1089fdd960bf/1766989593624.jpg | 2025-12-29 | 43.1317 | 9.6854 | Utility office | Stalled | The utility office construction is already stopped, due to construction materials shortage. | 27 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-12-29 06:30:10 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a57c7d14-a322-42bb-978a-1089fdd960bf/1766989613810.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a57c7d14-a322-42bb-978a-1089fdd960bf/1766989637592.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a57c7d14-a322-42bb-978a-1089fdd960bf/1766989655128.jpg
uuid:10a7414c-64c6-4cda-b5f1-ea2f80507831 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_10a7414c-64c6-4cda-b5f1-ea2f80507831/1766989080163.jpg | 2025-12-29 | 43.1315 | 9.6852 | Sevice Reservoir | In Progress | Sluggish progress, NB. The progress percentage is financial of total project. | 27 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-12-29 06:25:28 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_10a7414c-64c6-4cda-b5f1-ea2f80507831/1766989103593.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_10a7414c-64c6-4cda-b5f1-ea2f80507831/1766989331329.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_10a7414c-64c6-4cda-b5f1-ea2f80507831/1766989375655.jpg
uuid:d946f627-1438-4c83-886a-b59f259f7381 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d946f627-1438-4c83-886a-b59f259f7381/IMG_0316-20_40_35.jpeg | 2025-12-24 | 43.0176 | 9.0092 | Booster pump station no-01 | In Progress | Daily Report – 24/12/2025 150 m³ Tanker at WTP • Installation of ground slab reinforcement and formwork is underway. | 7 | robelw@msconsultancyet.com | N/A | 2025-12-24 17:43:28 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d946f627-1438-4c83-886a-b59f259f7381/IMG_0313-20_41_0.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_d946f627-1438-4c83-886a-b59f259f7381/IMG_0200-20_42_56.jpeg
uuid:cd5b6603-f452-4e5f-89f5-752a9a5e59e1 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_cd5b6603-f452-4e5f-89f5-752a9a5e59e1/IMG_0359-20_36_47.jpeg | 2025-12-24 | 43.1674 | 9.1098 | Utility office | In Progress | Daily Report – 24/12/2025 Utility Office • Roof construction work continued. | 7 | robelw@msconsultancyet.com | N/A | 2025-12-24 17:37:37 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_cd5b6603-f452-4e5f-89f5-752a9a5e59e1/IMG_0208-20_37_9.jpeg
uuid:b8a1a4e9-d94c-4ec8-8174-bb55486f0752 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b8a1a4e9-d94c-4ec8-8174-bb55486f0752/IMG_0369-20_34_8.jpeg | 2025-12-24 | 43.1674 | 9.1096 | Elevated reservoir | In Progress | Date: 24/12/2025 Elevated Reservoirs – Progress Update Elevated Reservoir No. 1 • The ninth and final lift of the shaft wall concrete was successfully cast, reaching an elevation of 17.6 m. Elevated Reservoir No. 2 • The second lift of the shaft wall concrete was successfully cast. General Works for Both Reservoirs • Scaffolding erection, reinforcement installation, formwork fixing, and concrete works are continuing in line with the approved construction sequence. | 7 | robelw@msconsultancyet.com | N/A | 2025-12-24 17:35:29 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b8a1a4e9-d94c-4ec8-8174-bb55486f0752/IMG_0360-20_34_23.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b8a1a4e9-d94c-4ec8-8174-bb55486f0752/IMG_0250-20_34_48.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b8a1a4e9-d94c-4ec8-8174-bb55486f0752/IMG_0363-20_35_2.jpeg
uuid:159a2917-34b3-458c-a2c3-6dbd907099fa | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_159a2917-34b3-458c-a2c3-6dbd907099fa/IMG_0303-11_4_53.jpeg | 2025-12-24 | 43.0513 | 8.9377 | Borholes | In Progress | Daily Report – 24/12/2025 Boreholes – BH01, BH02, BH03, BH04 • Civil works are ongoing for the boreholes, including the control room, generator room, guard house, and dry pit latrine. • Both substructure and superstructure works are in progress. • Overall, the civil works are advancin | 7 | robelw@msconsultancyet.com | N/A | 2025-12-24 08:05:58 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_159a2917-34b3-458c-a2c3-6dbd907099fa/IMG_0307-11_5_2.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_159a2917-34b3-458c-a2c3-6dbd907099fa/IMG_0308-11_5_8.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_159a2917-34b3-458c-a2c3-6dbd907099fa/IMG_0305-11_5_34.jpeg
uuid:eadb0569-d207-48b4-965c-bac0088a75a8 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_eadb0569-d207-48b4-965c-bac0088a75a8/IMG_0250-12_5_15.jpeg | 2025-12-23 | 43.1674 | 9.1097 | Elevated reservoirs | In Progress | Date: 23/12/2025 Elevated Reservoirs Progress Update Elevated Reservoir No. 1 The final ninth lift of the shaft wall concrete was successfully cast, reaching an elevation of 17.6 m. Elevated Reservoir No. 2 The second lift of the shaft wall concrete was successfully cast. For both elevated reservoirs, scaffolding erection, reinforcement installation, formwork fixing, and concrete works are ongoing as per the approved construction sequence. | 7 | robelw@msconsultancyet.com | N/A | 2025-12-23 09:06:06 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_eadb0569-d207-48b4-965c-bac0088a75a8/IMG_0209-12_5_30.jpeg
uuid:effe7685-1799-4ab7-98dd-fef1bf74f292 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_effe7685-1799-4ab7-98dd-fef1bf74f292/IMG_0099-15_3_12.jpeg | 2025-12-18 | 43.0451 | 8.9492 | Boreholes | In Progress | Borhole civil works underway for sub structures and cattle troughs | 7 | robelw@msconsultancyet.com | N/A | 2025-12-19 12:05:27 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_effe7685-1799-4ab7-98dd-fef1bf74f292/af681dc5c3d8802d81519c69b1b24783-15_5_9.jpeg
uuid:9219a093-faab-4732-9770-00bd40468d6b | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_9219a093-faab-4732-9770-00bd40468d6b/IMG_0094-15_1_18.jpeg | 2025-12-19 | 43.1674 | 9.1084 | Utility office | In Progress | 19/12/2025 Utility office HCB wall, top tier beam & plastering and rendering work | 7 | robelw@msconsultancyet.com | N/A | 2025-12-19 12:01:40 | N/A
uuid:ab357f31-7e3e-4a55-9d26-823940e205c7 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ab357f31-7e3e-4a55-9d26-823940e205c7/IMG_0093-14_59_48.jpeg | 2025-12-19 | 43.1675 | 9.1095 | Elevated reservoirs | In Progress | 19/12/2025 Elevated reservoirs Elevated reservoir no:1 8th lift shat wall concrete casted | 7 | robelw@msconsultancyet.com | N/A | 2025-12-19 12:00:18 | N/A
uuid:801894e0-3df2-4427-93b2-e4be938a447f | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_801894e0-3df2-4427-93b2-e4be938a447f/0f2999e3f22f31aa98fe12ebd3d0ce81-19_27_43.jpeg | 2025-12-18 | 43.1674 | 9.1096 | Elevated reservoir, utility office, boreholes , KBOS-01, cattle trough | In Progress | Work is progressing elevated reservoir, utility office , cattle trough , boreholes work resumed , cattle trough | 6 | robelw@msconsultancyet.com | N/A | 2025-12-18 16:30:06 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_801894e0-3df2-4427-93b2-e4be938a447f/d4e536bf6663977195e43caf1723dde5-19_27_49.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_801894e0-3df2-4427-93b2-e4be938a447f/68d04c4adfb079856d51a1139bcadb97-19_27_55.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_801894e0-3df2-4427-93b2-e4be938a447f/9b77ad6806ae9c90aafdde3e26105581-19_28_2.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_801894e0-3df2-4427-93b2-e4be938a447f/e2b68a2575f0482425f57a77755baa2a-19_28_12.jpeg
uuid:cd00e044-974b-4a4f-9d63-5cd2a05a60ed | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_cd00e044-974b-4a4f-9d63-5cd2a05a60ed/IMG_9979-18_56_15.jpeg | 2025-12-15 | 43.1675 | 9.1083 | Service reservoir site | In Progress | utility office HCB WALL AND TOP TIE BEAM CONCRETE CASTING AND PLAN FOR PLASTERING WORK | 6 | robelw@msconsultancyet.com | N/A | 2025-12-15 15:57:20 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_cd00e044-974b-4a4f-9d63-5cd2a05a60ed/IMG_9941-18_56_22.jpeg
uuid:bd8772bb-e8ea-402a-93c5-8adf42a7268f | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bd8772bb-e8ea-402a-93c5-8adf42a7268f/IMG_9980-18_53_27.jpeg | 2025-12-15 | 43.1674 | 9.1096 | Service reservoir site | In Progress | Elevated reservoir no:1 shaft wall 6th lift 12 m concrete casted | 6 | robelw@msconsultancyet.com | N/A | 2025-12-15 15:54:53 | N/A
uuid:33980f20-c955-4e63-b770-6a1b0d977477 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_33980f20-c955-4e63-b770-6a1b0d977477/IMG_9926-17_51_8.jpeg | 2025-12-12 | 43.1675 | 9.1097 | Elevated reservoirs | In Progress | HSE Updates: HDPE nylon has been installed horizontally and vertically on the scaffolding to provide continuous protection on both elevated reservoirs. This measure enhances fall prevention and improves overall site safety. | 6 | robelw@msconsultancyet.com | N/A | 2025-12-12 14:53:00 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_33980f20-c955-4e63-b770-6a1b0d977477/5260dbc429d6a3cb52cf8370a5b567e2-17_51_19.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_33980f20-c955-4e63-b770-6a1b0d977477/f18c10f4de2e7f239290b15cd341f925-17_51_28.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_33980f20-c955-4e63-b770-6a1b0d977477/IMG_9925-17_52_52.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_33980f20-c955-4e63-b770-6a1b0d977477/IMG_9872-17_51_57.jpeg
uuid:c3c6fea8-825e-4b65-9a49-93c6ced7f0f7 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c3c6fea8-825e-4b65-9a49-93c6ced7f0f7/1765285744322.jpg | 2025-12-09 | 43.1315 | 9.6852 | Shedder service Reservoir | In Progress | New proposed 250m3 and 100m3 elevated service reservoir foundations excavations has commenced. | 30 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-12-10 13:21:27 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c3c6fea8-825e-4b65-9a49-93c6ced7f0f7/1765285762000.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c3c6fea8-825e-4b65-9a49-93c6ced7f0f7/1765285806348.jpg
uuid:1422e2dc-0941-4647-9c0f-7aad5275a9f5 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_1422e2dc-0941-4647-9c0f-7aad5275a9f5/IMG_9845-20_4_10.jpeg | 2025-12-09 | 43.1675 | 9.1083 | Utility office | In Progress | Date: 09/12/2025 Location: Utility Office Building Construction • HCB wall construction is being finalized. • Top tie beam rebar installation, formwork, and scaffolding works are underway. | 6 | robelw@msconsultancyet.com | N/A | 2025-12-09 17:06:15 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_1422e2dc-0941-4647-9c0f-7aad5275a9f5/IMG_9838-20_4_21.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_1422e2dc-0941-4647-9c0f-7aad5275a9f5/IMG_9841-20_5_9.jpeg
uuid:7e0a2339-a690-4a2d-9a92-a274d622d057 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7e0a2339-a690-4a2d-9a92-a274d622d057/IMG_9823-19_59_1.jpeg | 2025-12-09 | 43.1674 | 9.1097 | Elevated reservoirs | In Progress | Date: 09/12/2015 Location: Service Reservoir Site – Elevated Reservoirs Elevated Reservoir No. 1: • Fifth lift shaft wall rebar installation, formwork, and concrete works are in progress. • Fourth lift concrete has been cast. Elevated Reservoir No. 2: • Second lift shaft wall rebar installation and formwork are underway. • Scaffolding installation is in progress. Note: •Safety Enforced Safety belts, safety net blankets, and walkway ladder reinforcement nets were implemented and inspected for the elevated reservoir construction activities. All height work areas were secured, and all workers used full body harnesses. No safety issues were recorded. | 6 | robelw@msconsultancyet.com | N/A | 2025-12-09 17:00:38 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7e0a2339-a690-4a2d-9a92-a274d622d057/e104f06d669588cb39f9eff3b874dc8b-19_59_16.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7e0a2339-a690-4a2d-9a92-a274d622d057/IMG_9828-19_59_37.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7e0a2339-a690-4a2d-9a92-a274d622d057/IMG_9830-19_59_49.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7e0a2339-a690-4a2d-9a92-a274d622d057/IMG_9832-20_0_3.jpeg
uuid:7f32f970-33b4-4b06-bda6-2f81d7d00a0a | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7f32f970-33b4-4b06-bda6-2f81d7d00a0a/1765283808525.jpg | 2025-12-09 | 43.1317 | 9.6852 | Shedder site utility office | In Progress | The utility office at shedder site commenced before a month ago and currently the sub-structures almost completed. Moreover, excavations of new reservoirs commenced in this reporting month. | 30 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-12-09 12:41:58 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7f32f970-33b4-4b06-bda6-2f81d7d00a0a/1765283822511.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7f32f970-33b4-4b06-bda6-2f81d7d00a0a/1765283877693.jpg
uuid:5ba991a4-580d-469e-89bd-e471b2f275ff | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_5ba991a4-580d-469e-89bd-e471b2f275ff/1765281058334.jpg | 2025-12-09 | 43.2147 | 9.7757 | Aw-Barree utility office | In Progress | Currenty only utility office commenced and sub-structure completed. As well pipe supply completed and planed next month to initiate the installations | 25 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-12-09 11:54:47 | N/A
uuid:5d8fd517-da62-46a3-a715-5b058fd534fc | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_5d8fd517-da62-46a3-a715-5b058fd534fc/9b7e7ffecfb1691468fe9cfa7e35b1e9-11_2_29.jpeg | 2025-12-09 | 43.1675 | 9.1084 | Utility office | In Progress | utility office office | 6 | robelw@msconsultancyet.com | N/A | 2025-12-09 08:03:21 | N/A
uuid:7d603215-aee3-4ff8-b8a6-c63ba8008978 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7d603215-aee3-4ff8-b8a6-c63ba8008978/IMG_9764-10_49_26.png | 2025-12-08 | 43.036 | 8.957 | Borholes bh01,02,03,04 | Stalled | Here is a corrected and polished version, keeping it concise and formal: DAILY REPORT Date: 08 December 2025 Location: BH-2 Subject: ROW Obstruction and Security Incident During mobilization at Borehole BH-2, local individuals armed with a gun forced our workers to leave the area. This created a direct and serious threat to life. All activities were halted immediately for safety. The incident arose from unresolved Right-of-Way issues that continue to hinder progress despite earlier notifications. Employer Intervention Required • Engage Somali Regional State authorities • Provide security and ensure permanent ROW clearance • Contractor is submitting the incident and related claims • Issue direction on safe resumption of work Work at the Borehole sites remains suspended until full security assurance is provided. The work stoped at the borholes areas completely | 6 | robelw@msconsultancyet.com | N/A | 2025-12-09 07:51:44 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7d603215-aee3-4ff8-b8a6-c63ba8008978/IMG_9758-10_49_34.jpeg
https://odk-middleman.onrender.com/api/submission/uuid%3A7d603215-aee3-4ff8-b8a6-c63ba8008978/attachment/IMG_9757-10_49_45.png?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A7d603215-aee3-4ff8-b8a6-c63ba8008978/attachment/IMG_9760-10_49_56.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A7d603215-aee3-4ff8-b8a6-c63ba8008978/attachment/IMG_9758-10_50_18.jpeg?project_id=26&form_id=RWASH_Activity_20250831
uuid:61f38f66-5391-4561-9f90-c90a2ee59dea | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A61f38f66-5391-4561-9f90-c90a2ee59dea/attachment/3e42796fe953eabe687beae7541510e5-10_44_13.jpeg?project_id=26&form_id=RWASH_Activity_20250831 | 2025-12-09 | 43.1674 | 9.1099 | Elevated reservoirs consteuction | In Progress | Daily Report 09 December 2025 Safety belts, safety net blankets and walkway ladder reinforcement nets were implemented and checked for the elevated reservoirs construction. All height work areas were secured and all workers used full body harnesses. No safety issues were recorded. | 6 | robelw@msconsultancyet.com | N/A | 2025-12-09 07:45:10 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A61f38f66-5391-4561-9f90-c90a2ee59dea/attachment/d1fe356c9914a4d48214afbdf48e28bc-10_44_22.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A61f38f66-5391-4561-9f90-c90a2ee59dea/attachment/eddf07237bc3740f1f1331cdf143cd96-10_44_30.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A61f38f66-5391-4561-9f90-c90a2ee59dea/attachment/89c75fc96ac20aaeb709c16c3890d8cf-10_44_37.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A61f38f66-5391-4561-9f90-c90a2ee59dea/attachment/IMG_9791-10_44_56.jpeg?project_id=26&form_id=RWASH_Activity_20250831
uuid:4a86831e-5a90-4147-9fa3-c14b52f62a16 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A4a86831e-5a90-4147-9fa3-c14b52f62a16/attachment/IMG_9754-14_57_12.jpeg?project_id=26&form_id=RWASH_Activity_20250831 | 2025-12-08 | 43.0262 | 8.9809 | Boreholes | In Progress | Monday, 08/2025 Boreholes BH01, BH02, BH03, and BH04 Work is underway on all four borehole sites. The current activities include earthwork operations, substructure construction, and grade beam works. | 6 | robelw@msconsultancyet.com | N/A | 2025-12-08 12:00:25 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A4a86831e-5a90-4147-9fa3-c14b52f62a16/attachment/IMG_9753-14_57_18.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A4a86831e-5a90-4147-9fa3-c14b52f62a16/attachment/IMG_9752-14_57_23.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A4a86831e-5a90-4147-9fa3-c14b52f62a16/attachment/IMG_9755-15_0_6.jpeg?project_id=26&form_id=RWASH_Activity_20250831
uuid:3b5140c3-f6cc-4580-a95e-c6a670ce17dd | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A3b5140c3-f6cc-4580-a95e-c6a670ce17dd/attachment/4efa0fcacb8ff4a2a756089ea400a091-14_53_4.jpeg?project_id=26&form_id=RWASH_Activity_20250831 | 2025-12-08 | 43.1674 | 9.1082 | Utility office | In Progress | utility office wall HCB Work | 6 | robelw@msconsultancyet.com | N/A | 2025-12-08 11:54:55 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A3b5140c3-f6cc-4580-a95e-c6a670ce17dd/attachment/IMG_9621-14_53_50.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A3b5140c3-f6cc-4580-a95e-c6a670ce17dd/attachment/8618c7adb3b780e72d26fda6d227b7da-14_54_1.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A3b5140c3-f6cc-4580-a95e-c6a670ce17dd/attachment/de6a60ee77166bcfa861e356c525c0f4-14_54_11.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A3b5140c3-f6cc-4580-a95e-c6a670ce17dd/attachment/IMG_9570-14_54_34.jpeg?project_id=26&form_id=RWASH_Activity_20250831
uuid:e556d8cb-23f8-4f5f-94f1-3bed73a02a21 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3Ae556d8cb-23f8-4f5f-94f1-3bed73a02a21/attachment/f15a6af1e4ee70b4381203358104e620-14_50_40.jpeg?project_id=26&form_id=RWASH_Activity_20250831 | 2025-12-08 | 43.1675 | 9.1098 | Elevated reservoirs (2*250m3) | In Progress | Date: 08/12/2015 Location: Service Reservoir Site – Elevated Reservoirs Elevated Reservoir No. 1: • Fourth lift shaft wall rebar installation, formwork, and concrete works are in progress. Elevated Reservoir No. 2: • Second lift shaft wall rebar installation and formwork are underway. | 6 | robelw@msconsultancyet.com | N/A | 2025-12-08 11:52:05 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3Ae556d8cb-23f8-4f5f-94f1-3bed73a02a21/attachment/6b039db6dc792a016c25fa76649fc63d-14_50_46.jpeg?project_id=26&form_id=RWASH_Activity_20250831
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e556d8cb-23f8-4f5f-94f1-3bed73a02a21/7df06a60b3e58d6bb41a032379be6feb-14_51_4.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e556d8cb-23f8-4f5f-94f1-3bed73a02a21/IMG_9687-14_51_19.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e556d8cb-23f8-4f5f-94f1-3bed73a02a21/7659f1e5817db6938b5ded83692ffdf0-14_51_35.jpeg
uuid:fda884b1-fdf6-4024-9f68-f8d7d1da0e76 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_fda884b1-fdf6-4024-9f68-f8d7d1da0e76/2ea0db27d61314a3453a961ebd7252c0-14_47_41.jpeg | 2025-12-08 | 43.1674 | 9.1097 | Elevated reservoir, contractors camp, boreholes, meeting and site visiting | In Progress | Minutes of Meeting – 07 to 08 December 2025 Subject: Environmental, Social, Health, and Safety (ESHS) Issues A site visit and site meeting were conducted to review ESHS matters. The discussion covered environmental mitigation measures, community-related concerns, and compliance with health and safety requirements. Assigned personnel will monitor all actions, supported by weekly inspections and continuous updates to the ESHS checklists. All activities will be evaluated for compliance, and any required follow-up actions will be handled in accordance with contractual provisions. Hard copies of the minutes will be distributed. | 6 | robelw@msconsultancyet.com | N/A | 2025-12-08 11:49:18 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_fda884b1-fdf6-4024-9f68-f8d7d1da0e76/IMG_9690-14_48_8.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_fda884b1-fdf6-4024-9f68-f8d7d1da0e76/IMG_9726-14_48_21.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_fda884b1-fdf6-4024-9f68-f8d7d1da0e76/IMG_9721-14_48_35.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_fda884b1-fdf6-4024-9f68-f8d7d1da0e76/8397feb7c13a85f5f5f1e8c60e84777e-14_48_50.jpeg
uuid:a9fd2def-4dd1-455d-8941-3ff076c1ec43 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a9fd2def-4dd1-455d-8941-3ff076c1ec43/d7097986a0397fbd1c4d3dff59bd7ad1-14_43_9.jpeg | 2025-12-08 | 43.1675 | 9.1097 | Elevated reservoirs-service reservoir site | In Progress | Date: 08/12/2025 • A total of 300 pieces of landing walkway timber have been mobilized for the HES to provide safety walkways on the elevated reservoir scaffolding works. | 6 | robelw@msconsultancyet.com | N/A | 2025-12-08 11:45:23 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a9fd2def-4dd1-455d-8941-3ff076c1ec43/7659f1e5817db6938b5ded83692ffdf0-14_44_29.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a9fd2def-4dd1-455d-8941-3ff076c1ec43/6b039db6dc792a016c25fa76649fc63d-14_43_21.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a9fd2def-4dd1-455d-8941-3ff076c1ec43/496e6c368e130199174f37b4273f598b-14_43_29.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a9fd2def-4dd1-455d-8941-3ff076c1ec43/f15a6af1e4ee70b4381203358104e620-14_44_0.jpeg
uuid:8b269892-c11f-4f62-9651-808518a0c89a | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8b269892-c11f-4f62-9651-808518a0c89a/222eda64cb9f756967e2338aa1cd7fa7-10_37_6.jpeg | 2025-12-07 | 43.1674 | 9.1098 | Service reservoir site | In Progress | Daily Report – 12 December 2025 • Elevated Reservoir: The reservoir height has reached 10 meters as of 12 July 2025. Scaffolding works are ongoing, and all workers are required to wear safety belts. Fall protection measures are under active implementation. All personnel on the scaffolding and surrounding work zones are equipped with safety shoes, gloves, safety vests, safety belts and helmets. • Service Reservoir Site: Water sprinkling has been carried out to control dust pollution. • Utility Office: Hollow Concrete Block (HCB) works are in progress, and curing activities are ongoing | 6 | robelw@msconsultancyet.com | N/A | 2025-12-07 07:40:07 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8b269892-c11f-4f62-9651-808518a0c89a/1f1aad5ea94b83f935fb3845d9942d4f-10_37_19.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8b269892-c11f-4f62-9651-808518a0c89a/c2f7c263e9bba453389054eba6a97f82-10_37_30.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8b269892-c11f-4f62-9651-808518a0c89a/e895eec2a6df203839531b0d4a5c093d-10_38_32.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8b269892-c11f-4f62-9651-808518a0c89a/71902a76a2933bcdb7b692518dba40f0-10_37_51.jpeg
uuid:8d74e43f-2fd9-4750-a18c-cd15663e12eb | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8d74e43f-2fd9-4750-a18c-cd15663e12eb/IMG_9385-20_14_7.jpeg | 2025-11-30 | 43.0901 | 9.0496 | Kbps-01 & kbps-02 | In Progress | Cattle trough, water fountain works underway | 5 | robelw@msconsultancyet.com | N/A | 2025-12-01 17:16:10 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8d74e43f-2fd9-4750-a18c-cd15663e12eb/IMG_9383-20_14_16.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8d74e43f-2fd9-4750-a18c-cd15663e12eb/IMG_9386-20_14_24.jpeg
uuid:bbdfe24f-34e5-405d-bcbe-9f242534a597 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bbdfe24f-34e5-405d-bcbe-9f242534a597/IMG_9337-20_8_26.jpeg | 2025-11-30 | 43.1674 | 9.1097 | Elevated reservoirs | In Progress | elevated reservoir shat wall first lift rebar and form work installation and concrete casting | 5 | robelw@msconsultancyet.com | N/A | 2025-12-01 17:12:25 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bbdfe24f-34e5-405d-bcbe-9f242534a597/IMG_9315-20_10_25.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bbdfe24f-34e5-405d-bcbe-9f242534a597/IMG_9339-20_12_15.jpeg
uuid:ea983ded-5a18-4cee-a32b-7359e4ebe369 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ea983ded-5a18-4cee-a32b-7359e4ebe369/IMG_9368-20_5_28.jpeg | 2025-11-30 | 43.0231 | 8.9931 | Borhole no:1 & 2 | In Progress | Daily Report Date: 29 November 2025 Boreholes BH01 & BH02 Work activities executed at BH01 included the following: • Foundation excavation for the control room, generator house, guard house, and depot latrine • Lean concrete placement • Masonry work in progress Status All listed structures are currently under construction, and works are progressing… | 5 | robelw@msconsultancyet.com | N/A | 2025-12-01 17:06:53 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ea983ded-5a18-4cee-a32b-7359e4ebe369/IMG_9369-20_5_36.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ea983ded-5a18-4cee-a32b-7359e4ebe369/IMG_9370-20_5_42.jpeg
uuid:7aa6954f-f2c7-4399-850b-8078fa6a09c6 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_7aa6954f-f2c7-4399-850b-8078fa6a09c6/IMG_9313-20_0_30.jpeg | 2025-11-29 | 43.0342 | 8.9482 | Borhole site bh 01 | In Progress | Daily Report Date: 29 November 2025 Boreholes BH01 Work activities executed at BH01 included the following: • Foundation excavation for the control room, generator house, guard house, and depot latrine • Lean concrete placement • Masonry work in progress Status All listed structures are currently under construction, and works are progressing… | 5 | robelw@msconsultancyet.com | N/A | 2025-12-01 17:03:41 | N/A
uuid:ab1533c5-e46f-42af-ae92-38c5b8892ed9 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ab1533c5-e46f-42af-ae92-38c5b8892ed9/5c5308bb7153de6ee45942c47d01d8c8-5_12_26.jpeg | 2025-11-26 | 43.0281 | 8.9795 | Boreholes | In Progress | Daily Report Date: 28/11/2025 Boreholes • Persistent right of way challenges and restricted access to the borehole sites from 03 October to 25 November (total of 54 days) made it difficult to enter and continue the works. • With the employer’s intervention and support, the contractor has resumed earthworks at BH01. Earthworks for the generator room, control room, guard house, dry pit, as well as lean concrete and masonry work, have been requested and inspected for work progress. • Preparations are underway for the contractor to commence work at BH02. | 4 | robelw@msconsultancyet.com | N/A | 2025-11-29 02:23:28 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ab1533c5-e46f-42af-ae92-38c5b8892ed9/IMG_9204-5_12_42.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ab1533c5-e46f-42af-ae92-38c5b8892ed9/a324900b8250d54c83da15b8f2980abd-5_13_0.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ab1533c5-e46f-42af-ae92-38c5b8892ed9/IMG_9027-5_22_4.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ab1533c5-e46f-42af-ae92-38c5b8892ed9/IMG_9029-5_22_18.jpeg
uuid:104824b0-b0a7-4e5a-8b9c-3511bbdfaff5 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_104824b0-b0a7-4e5a-8b9c-3511bbdfaff5/IMG_9148-5_4_10.jpeg | 2025-11-28 | 43.1675 | 9.1098 | Existing service reservoir compound | In Progress | 28/11/2025 Elevated Reservoirs • Second lift scaffolding installation is in progress for both elevated reservoirs, and rebar installation work is underway. • The total shaft wall height is 18 m, and the total tank height is approximately 24.5 m. • The first lift wall concrete, with a height of 2 m, has already been completed. • Work on the second lift wall, also 2 m in height, is currently in progress. A total of four lifts will be cast. | 4 | robelw@msconsultancyet.com | N/A | 2025-11-29 02:10:36 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_104824b0-b0a7-4e5a-8b9c-3511bbdfaff5/IMG_9159-5_7_46.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_104824b0-b0a7-4e5a-8b9c-3511bbdfaff5/IMG_9282-5_9_5.png
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_104824b0-b0a7-4e5a-8b9c-3511bbdfaff5/IMG_9284-5_10_14.png
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_104824b0-b0a7-4e5a-8b9c-3511bbdfaff5/IMG_9283-5_10_20.jpeg
uuid:1fd224d6-bb15-4ea8-aff2-43e4a5a84059 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_1fd224d6-bb15-4ea8-aff2-43e4a5a84059/IMG_9237-5_0_14.jpeg | 2025-11-27 | 43.1675 | 9.1098 | Both elevated reservoirs at utility office compound | In Progress | 27/11/2025 Elevated Reservoirs No. 1 and No. 2 • First lift shaft wall concrete pouring, with a height of 2 m, has been completed for both Reservoir No. 1 and Reservoir No. 2. | 4 | robelw@msconsultancyet.com | N/A | 2025-11-29 02:01:21 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_1fd224d6-bb15-4ea8-aff2-43e4a5a84059/IMG_9238-5_0_20.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_1fd224d6-bb15-4ea8-aff2-43e4a5a84059/IMG_9280-5_0_26.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_1fd224d6-bb15-4ea8-aff2-43e4a5a84059/08b4a6a15abb3d4bf606b10e6adaedaf-5_0_48.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_1fd224d6-bb15-4ea8-aff2-43e4a5a84059/b1cd3fdbe494f55983911151a2e7d830-5_1_3.jpeg
uuid:68114c0a-4163-4abc-a309-b9caa21fffd3 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_68114c0a-4163-4abc-a309-b9caa21fffd3/IMG_9276-4_53_53.jpeg | 2025-11-21 | 43.1675 | 9.1098 | Elevated reservoir no:2 | In Progress | 21/11/2025 Elevated Reservoir • Footing pad concrete pouring for Reservoir No. 02 has been completed. The total concrete volume placed is approximately 154 m³. | 4 | robelw@msconsultancyet.com | N/A | 2025-11-29 01:55:21 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_68114c0a-4163-4abc-a309-b9caa21fffd3/IMG_9275-4_54_6.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_68114c0a-4163-4abc-a309-b9caa21fffd3/IMG_8995-4_54_34.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_68114c0a-4163-4abc-a309-b9caa21fffd3/IMG_9272-4_54_43.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_68114c0a-4163-4abc-a309-b9caa21fffd3/7af1c95e64b9871998d59497266080f1-4_54_57.jpeg
uuid:be1421f8-9096-48a1-ad8e-234089e73c79 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_be1421f8-9096-48a1-ad8e-234089e73c79/IMG_8830-4_48_22.jpeg | 2025-11-27 | 43.0087 | 9.0143 | Cattle trough | In Progress | 27/11/2025 Cattle Trough Points No. 1, 2, and 3 Location: KBPS 01 • Construction work on Cattle Trough Points No. 1, 2, and 3 is currently underway. | 4 | robelw@msconsultancyet.com | N/A | 2025-11-29 01:50:38 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_be1421f8-9096-48a1-ad8e-234089e73c79/IMG_8831-4_48_28.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_be1421f8-9096-48a1-ad8e-234089e73c79/8be5281f849ebac527d1177b589e7310-4_48_35.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_be1421f8-9096-48a1-ad8e-234089e73c79/c8737e6f8ccd76779b94028ad5cd3dfe-4_48_45.jpeg
uuid:1b9f228b-9a6a-4ae2-ba8b-074cf6e86502 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_1b9f228b-9a6a-4ae2-ba8b-074cf6e86502/IMG_9225-4_43_16.jpeg | 2025-11-20 | 43.017 | 9.0096 | Water point at kbps-01 | In Progress | 20/11/2025 Water Point No. 1 Location: KBPS 01 • Construction work on Water Point No. 1 is currently underway. | 4 | robelw@msconsultancyet.com | N/A | 2025-11-29 01:47:35 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_1b9f228b-9a6a-4ae2-ba8b-074cf6e86502/IMG_9252-4_43_25.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_1b9f228b-9a6a-4ae2-ba8b-074cf6e86502/IMG_8832-4_45_52.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_1b9f228b-9a6a-4ae2-ba8b-074cf6e86502/IMG_9251-4_46_9.jpeg
uuid:2fc285cb-6469-4472-b8ba-41b52b784c86 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_2fc285cb-6469-4472-b8ba-41b52b784c86/IMG_9249-4_39_27.jpeg | 2025-11-19 | 43.1674 | 9.1098 | Elevated reservoir | In Progress | Daily Report 19/11/2025 Elevated Reservoir • Footing pad concrete pouring for Reservoir No. 01 has been completed. The total concrete volume placed is approximately 154 m³. | 4 | robelw@msconsultancyet.com | N/A | 2025-11-29 01:40:40 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_2fc285cb-6469-4472-b8ba-41b52b784c86/IMG_9248-4_39_34.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_2fc285cb-6469-4472-b8ba-41b52b784c86/IMG_9246-4_39_50.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_2fc285cb-6469-4472-b8ba-41b52b784c86/IMG_8723-4_40_6.jpeg
uuid:644c0fc2-0208-4083-9804-8fe9cdff01c5 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_644c0fc2-0208-4083-9804-8fe9cdff01c5/ce4f4b52872c748903216d5ef84c7eae-20_12_5.jpeg | 2025-11-18 | 43.1675 | 9.1099 | Kebribeyah town water utility office compound elevated reservoir site | In Progress | Daily Report Date: November 18, 2025 Location: KEBRIBEYAH Existing Reservoir Site 🏗️ The site comprises two elevated reservoirs with a capacity of 250 m³ each. 🏗️ Construction activities progressed steadily. • Elevated Reservoir No. 01 🔨 Footing pad reinforced concrete works are underway. 📏 Total concrete requirement is 155 m³. 🚚 Approximately 60 m³ has been poured to date. 🧰 Concrete mixing, vibration, and casting operations continued. • Elevated Reservoir No. 02 🔧 Reinforcement installation continued. 🪚 Formwork assembly and tightening progressed. 🧵 Steel tying and formwork alignment proceeded smoothly. | 3 | robelw@msconsultancyet.com | N/A | 2025-11-18 17:14:55 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_644c0fc2-0208-4083-9804-8fe9cdff01c5/IMG_8712-20_12_13.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_644c0fc2-0208-4083-9804-8fe9cdff01c5/IMG_8713-20_12_18.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_644c0fc2-0208-4083-9804-8fe9cdff01c5/IMG_8714-20_12_32.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_644c0fc2-0208-4083-9804-8fe9cdff01c5/IMG_8685-20_13_4.jpeg
uuid:b430d498-352c-4eda-8ac1-64c45e6e8809 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b430d498-352c-4eda-8ac1-64c45e6e8809/IMG_8646-22_29_58.jpeg | 2025-11-16 | 43.1674 | 9.1099 | Elevated reservoir and KBOS01 water point and cattle troughs | In Progress | Daily Report Date: November 16, 2025 • Elevated reservoir footing pad reinforcement and formwork installation completed; ready for concrete pouring. • Water point at KBPS-02 and cattle trough works ongoing. | 3 | robelw@msconsultancyet.com | N/A | 2025-11-17 19:31:15 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b430d498-352c-4eda-8ac1-64c45e6e8809/IMG_8645-22_30_7.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b430d498-352c-4eda-8ac1-64c45e6e8809/IMG_8532-22_30_16.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b430d498-352c-4eda-8ac1-64c45e6e8809/IMG_8546-22_30_37.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b430d498-352c-4eda-8ac1-64c45e6e8809/IMG_8644-22_30_45.jpeg
uuid:6e20e3e2-8fdf-442e-bff5-99855324cfa6 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_6e20e3e2-8fdf-442e-bff5-99855324cfa6/IMG_8636-22_23_19.jpeg | 2025-11-15 | 43.1674 | 9.1098 | Elevated reservoir at the utility office compound | In Progress | Daily Report Date: November 15, 2025 • Elevated reservoir footing pad bottom and top reinforcement installation continued as planned. | 3 | robelw@msconsultancyet.com | N/A | 2025-11-17 19:25:08 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_6e20e3e2-8fdf-442e-bff5-99855324cfa6/IMG_8513-22_24_32.jpeg
uuid:496f75e3-7530-455f-95a5-63f2e8850f1e | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_496f75e3-7530-455f-95a5-63f2e8850f1e/IMG_8442-22_16_27.jpeg | 2025-11-14 | 43.1674 | 9.1098 | Elevated reservoir | In Progress | Daily Report November 14, 2025 • Elevated reservoir footing pad bottom reinforcement installation continued as planned. | 3 | robelw@msconsultancyet.com | N/A | 2025-11-17 19:17:34 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_496f75e3-7530-455f-95a5-63f2e8850f1e/IMG_8630-22_16_40.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_496f75e3-7530-455f-95a5-63f2e8850f1e/IMG_8442-22_16_54.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_496f75e3-7530-455f-95a5-63f2e8850f1e/IMG_8618-22_17_17.jpeg
uuid:e1b70a06-814a-41a2-8661-aabdb5f67f2f | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e1b70a06-814a-41a2-8661-aabdb5f67f2f/IMG_8619-22_13_12.jpeg | 2025-11-13 | 43.1675 | 9.1098 | Elevated reservoir and 3rd party lab testing dire dawa | In Progress | Daily Report November 13, 2025 • Laboratory testing conducted for concrete test cubes, HCB, and rebar samples. • Elevated reservoir lean concrete curing continued. | 3 | robelw@msconsultancyet.com | N/A | 2025-11-17 19:14:07 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e1b70a06-814a-41a2-8661-aabdb5f67f2f/IMG_8621-22_13_21.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e1b70a06-814a-41a2-8661-aabdb5f67f2f/IMG_8627-22_13_34.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e1b70a06-814a-41a2-8661-aabdb5f67f2f/IMG_8626-22_13_41.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e1b70a06-814a-41a2-8661-aabdb5f67f2f/IMG_8624-22_13_48.jpeg
uuid:fdd9a73c-f8fb-455b-8807-395d730c6541 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_fdd9a73c-f8fb-455b-8807-395d730c6541/IMG_8606-22_7_30.jpeg | 2025-11-12 | 43.1674 | 9.1097 | Elevated reservoir at the utility office compound office compound | In Progress | Daily Report November 12, 2025 • Elevated reservoir foundation lean concrete placed. • Water point setting out, site clearance, excavation, and hardcore placement carried out. • Rebar supply sampling completed and submitted for third-party laboratory testing. | 3 | robelw@msconsultancyet.com | N/A | 2025-11-17 19:08:44 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_fdd9a73c-f8fb-455b-8807-395d730c6541/IMG_8300-22_7_41.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_fdd9a73c-f8fb-455b-8807-395d730c6541/IMG_8298-22_7_55.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_fdd9a73c-f8fb-455b-8807-395d730c6541/IMG_8337-22_8_3.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_fdd9a73c-f8fb-455b-8807-395d730c6541/IMG_8614-22_8_9.jpeg
uuid:ccb8b932-4556-452c-8dc0-d1a567e1a9e1 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ccb8b932-4556-452c-8dc0-d1a567e1a9e1/IMG_8257-22_3_20.jpeg | 2025-11-11 | 43.1675 | 9.1098 | Elevated reservoirs existing reservoir sites at the town in the utility office compound | In Progress | Daily Report November 11, 2025 • Elevated reservoir foundation excavation was completed. • Foundation area compaction carried out. • Field Density Test (FDT) conducted to verify compaction quality. | 3 | robelw@msconsultancyet.com | N/A | 2025-11-17 19:03:40 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ccb8b932-4556-452c-8dc0-d1a567e1a9e1/IMG_8256-22_3_9.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ccb8b932-4556-452c-8dc0-d1a567e1a9e1/IMG_8592-22_2_59.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ccb8b932-4556-452c-8dc0-d1a567e1a9e1/IMG_8594-22_2_40.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ccb8b932-4556-452c-8dc0-d1a567e1a9e1/IMG_8260-22_2_25.jpeg
uuid:14b14edd-a993-4da1-9e1b-9628c925de06 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_14b14edd-a993-4da1-9e1b-9628c925de06/IMG_8091-21_55_35.jpeg | 2025-11-10 | 43.1673 | 9.1097 | Elevated reservoir at the utility office compound and contractors camp | In Progress | Daily Report November 10, 2025 • Elevated reservoir foundation excavation continued. • Rebar samples were collected and submitted for testing. • HCB production continued. • Utility office column works progressed as scheduled. | 3 | robelw@msconsultancyet.com | N/A | 2025-11-17 18:58:48 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_14b14edd-a993-4da1-9e1b-9628c925de06/IMG_8090-21_55_58.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_14b14edd-a993-4da1-9e1b-9628c925de06/324d846566a36bd495667cf5b74f6e33-21_56_44.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_14b14edd-a993-4da1-9e1b-9628c925de06/IMG_8088-21_57_16.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_14b14edd-a993-4da1-9e1b-9628c925de06/b9aa0bdb10480ee7d8bc52b3e14b33d7-21_57_30.jpeg
uuid:b55ac67f-7265-4b58-bbb1-b1a62fc1a342 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b55ac67f-7265-4b58-bbb1-b1a62fc1a342/IMG_8208-21_52_48.jpeg | 2025-11-09 | 43.1674 | 9.1098 | Elevated reservoir in the town existing reservoir site | In Progress | Daily Report November 09, 2025 • Elevated reservoir foundation bearing capacity testing was carried out on site. | 3 | robelw@msconsultancyet.com | N/A | 2025-11-17 18:53:35 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b55ac67f-7265-4b58-bbb1-b1a62fc1a342/IMG_8588-21_52_54.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b55ac67f-7265-4b58-bbb1-b1a62fc1a342/IMG_8587-21_53_5.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_b55ac67f-7265-4b58-bbb1-b1a62fc1a342/IMG_8590-21_53_11.jpeg
uuid:714e7b26-6b08-4ecd-b078-b9795df1e02c | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_714e7b26-6b08-4ecd-b078-b9795df1e02c/IMG_8585-21_47_51.jpeg | 2025-11-08 | 43.1659 | 9.1109 | Elevated reservoir | In Progress | Daily Report November 08, 2025 • Elevated reservoir foundation excavation continued as planned. | 3 | robelw@msconsultancyet.com | N/A | 2025-11-17 18:49:12 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_714e7b26-6b08-4ecd-b078-b9795df1e02c/IMG_8581-21_48_7.jpeg
uuid:217cd1a9-7834-4aad-8eb5-63103222ddfa | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_217cd1a9-7834-4aad-8eb5-63103222ddfa/IMG_8573-21_43_57.jpeg | 2025-11-07 | 43.1661 | 9.1105 | Utility office and elevated reservoir at the existing reservoir site at the town | In Progress | Daily Report November 07, 2025 • Utility office column work continued. • Setting out and site clearance commenced for the elevated reservoir. • Foundation excavation started as per the approved layout. | 3 | robelw@msconsultancyet.com | N/A | 2025-11-17 18:46:48 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_217cd1a9-7834-4aad-8eb5-63103222ddfa/IMG_8574-21_44_11.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_217cd1a9-7834-4aad-8eb5-63103222ddfa/IMG_8137-21_44_31.jpeg
uuid:bf5b2b1e-fa33-4e60-86d1-46487ea96af3 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bf5b2b1e-fa33-4e60-86d1-46487ea96af3/IMG_8565-21_38_3.jpeg | 2025-11-06 | 43.1676 | 9.109 | Utility office | In Progress | Daily Report November 06, 2025 • Utility office column reinforcement and formwork activities continued. • HCB production proceeded | 3 | robelw@msconsultancyet.com | N/A | 2025-11-17 18:39:56 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bf5b2b1e-fa33-4e60-86d1-46487ea96af3/IMG_8568-21_38_11.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bf5b2b1e-fa33-4e60-86d1-46487ea96af3/IMG_8560-21_38_24.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bf5b2b1e-fa33-4e60-86d1-46487ea96af3/IMG_8076-21_38_29.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bf5b2b1e-fa33-4e60-86d1-46487ea96af3/IMG_8569-21_38_55.jpeg
uuid:865312c8-a03a-4429-9608-8824fc6a0e88 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_865312c8-a03a-4429-9608-8824fc6a0e88/IMG_8558-21_32_53.jpeg | 2025-11-05 | 43.1673 | 9.109 | Utility office and third party lab | In Progress | Daily Report Concrete and HCB Testing • Seven-day concrete cube samples were tested for compressive strength. • HCB samples were also tested for strength compliance. | 3 | robelw@msconsultancyet.com | N/A | 2025-11-17 18:36:13 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_865312c8-a03a-4429-9608-8824fc6a0e88/IMG_8554-21_33_1.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_865312c8-a03a-4429-9608-8824fc6a0e88/IMG_8556-21_33_7.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_865312c8-a03a-4429-9608-8824fc6a0e88/IMG_8555-21_33_16.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_865312c8-a03a-4429-9608-8824fc6a0e88/IMG_8557-21_33_34.jpeg
uuid:2e3f80d5-37ba-4dcd-9b87-6aa922bffa1a | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_2e3f80d5-37ba-4dcd-9b87-6aa922bffa1a/IMG_8553-21_28_49.jpeg | 2025-11-04 | 43.1675 | 9.1084 | Utility office | In Progress | Column works | 3 | robelw@msconsultancyet.com | N/A | 2025-11-17 18:29:34 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_2e3f80d5-37ba-4dcd-9b87-6aa922bffa1a/IMG_7948-21_28_55.jpeg
uuid:89ad70b8-a3d1-48f7-a04e-0754747f3104 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_89ad70b8-a3d1-48f7-a04e-0754747f3104/IMG_7895-12_56_53.jpeg | 2025-11-03 | 43.018 | 9.0045 | Boreholes | In Progress | Date: 03/11/2025 Project: Kebribeyah Water Supply Construction Project Location: Borehole Area – BH01 & BH02 ⚠️ Urgent Security Alert A serious and violent security incident has occurred at the borehole site (BH01 & BH02), where workers were attacked and injured by local individuals. This situation poses a direct and immediate threat to the safety of project personnel and the security of project assets. 🚨 Immediate intervention is urgently required from all concerned stakeholders, including the SRSWB Water Bureau, the Local Administration (Mayor’s Office and Woreda Administration), and especially the Utility Office, to coordinate with the relevant security authorities and take swift action to ensure the protection of all staff and the continuation of the ongoing works. Furthermore, it is strongly recommended that the root causes of this conflict be jointly assessed and resolved by the concerned authorities and community representatives to prevent recurrence and restore a safe working environment for the project’s smooth implementation. Best regards, | 3 | robelw@msconsultancyet.com | N/A | 2025-11-03 09:58:06 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_89ad70b8-a3d1-48f7-a04e-0754747f3104/IMG_7894-12_56_59.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_89ad70b8-a3d1-48f7-a04e-0754747f3104/IMG_7893-12_57_6.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_89ad70b8-a3d1-48f7-a04e-0754747f3104/IMG_7891-12_57_12.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_89ad70b8-a3d1-48f7-a04e-0754747f3104/IMG_7892-12_57_19.jpeg
uuid:5b284817-c775-4981-8795-db562fce0e8c | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_5b284817-c775-4981-8795-db562fce0e8c/IMG_7874-11_6_41.png | 2025-11-03 | 43.0448 | 8.9766 | Boreholes | Stalled | Notice to Employer and Project Stakeholders Dear All, The Delegated Project Manager of the contractor, Mr. Xu, has reported the following: During the well construction activities at BH01–BH02, local residents obstructed the work by throwing stones, resulting in injuries to several on-site personnel. In addition, construction tools were stolen. As a result, the contractor has temporarily withdrawn personnel from the site. They have requested that the incident be officially recorded and have indicated their intention to file a claim for project duration and associated costs until the land acquisition issue is resolved and a construction instruction is issued by the Employer. The consultant has acknowledged this report and recommends that the Employer take immediate action to address the security issues so that construction can safely resume. Please treat this information as official notice for documentation and further necessary action. Thank you for your attention. | 3 | robelw@msconsultancyet.com | N/A | 2025-11-03 08:08:15 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_5b284817-c775-4981-8795-db562fce0e8c/IMG_7875-11_7_7.png
uuid:426ba0c0-cad9-45d8-9b54-0a0fc6e26a09 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_426ba0c0-cad9-45d8-9b54-0a0fc6e26a09/IMG_7856-19_19_26.png | 2025-11-02 | 43.1664 | 9.1104 | Existing reservoir site, utility building, bh | In Progress | Daily Site Report (02/11/2025) Dear All, The Kebribeyah R-WaSH Project is progressing in coordination with the City Administration and all stakeholders. While discussions are ongoing regarding the revision of the ground reservoir capacity, the Engineer (LRE) has confirmed that construction of the two elevated reservoirs shall proceed as planned to provide the required elevation head for the distribution network and so many technical reasons. The Contractor is hereby instructed to expedite the necessary arrangements for foundation excavation, take precautions to protect existing pipe connections, carry out immediate maintenance if any damage occurs, and submit a detailed work methodology for excavation and concrete works. All HES requirements must be fully implemented during execution. We thank all stakeholders for your continued cooperation and support in facilitating the progress of the works. Daily Site Report – 02/11/2025 1. Elevated Reservoir: • Site clearance in progress • Foundation excavation ongoing • Checking of existing pipeline routes • Planning for soil bearing test and preparation for foundation works 2. Utility Office: • Column concrete casting completed 3. Boreholes (BH-01 & BH-02): • Foundation excavation for guard house and generator house in progress • Planed for lean concrete. Best regards, Robel W. RE | 3 | robelw@msconsultancyet.com | N/A | 2025-11-02 16:20:56 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_426ba0c0-cad9-45d8-9b54-0a0fc6e26a09/IMG_7847-19_19_35.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_426ba0c0-cad9-45d8-9b54-0a0fc6e26a09/c11ecf24ba942646312d4d70cb1c7462-19_19_46.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_426ba0c0-cad9-45d8-9b54-0a0fc6e26a09/2e873bc2e5c79ffd7edc09c3d8a281dc-19_20_1.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_426ba0c0-cad9-45d8-9b54-0a0fc6e26a09/IMG_7848-19_20_13.jpeg
uuid:be1e46c7-b916-490c-9696-9a7f002e960a | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_be1e46c7-b916-490c-9696-9a7f002e960a/IMG_7817-17_24_43.jpeg | 2025-11-01 | 43.1675 | 9.1093 | Service reservoir compound Utility office & elevated reservoir setting out, boreholes | In Progress | 🛠 Daily Activity Report 🪏 Date: 1 Nov, 2025 Project: R-WASH-Kebribeyah Town– Construction of Civil Works, Supply & Installation of Pipes, and Electro-Mechanical Works 1. Utility Office Building – Existing Reservoir Site • Grade beam works fully completed. ✅ • Column reinforcement installation and formwork in progress. 🧱 • Site maintained clean and well-organized for the next phase of vertical construction. 🧹 2. Borehole Sites (BH-01 & 02) • Site clearance completed. ✅ • Construction materials mobilized to site. 🚚 • Setting-out completed as per approved drawings. 📐 • Foundation excavation for the guard house and generator house commenced. ⛏ Note: The next planned activity in the coming days is the commencement of foundation excavation works for the two elevated reservoirs. 🏗 | 3 | robelw@msconsultancyet.com | N/A | 2025-11-01 14:26:24 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_be1e46c7-b916-490c-9696-9a7f002e960a/IMG_7815-17_24_49.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_be1e46c7-b916-490c-9696-9a7f002e960a/IMG_7816-17_24_54.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_be1e46c7-b916-490c-9696-9a7f002e960a/IMG_7814-17_25_1.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_be1e46c7-b916-490c-9696-9a7f002e960a/IMG_7813-17_25_7.jpeg
uuid:54f64b39-1f25-40fe-ab57-0a0de651a729 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_54f64b39-1f25-40fe-ab57-0a0de651a729/IMG_7725-16_21_46.jpeg | 2025-10-31 | 43.1674 | 9.1095 | Kebribeyah utility office and borehole no-01 | In Progress | 🛠 Daily Activity Report 🪏 Date: 31 October 2025 Location: Kebribeyah Town, Somali Region Project: R-WASH – Construction of Civil Works, Supply & Installation of Pipes, and Electro-Mechanical Works 1. Utility Office Building – Existing Reservoir Site • Grade beam works fully completed. ✅ • Reinforcement installation and formwork for columns are in progress. 🧱 • Site kept organized and prepared for the next phase of construction. 🧹 2. Borehole Sites (BH-01) • Site clearance completed. ✅ • Construction materials mobilized to site. 🚚 • Setting-out works completed as per approved drawings. 📐 • Foundation excavation for the guard house and generator house commenced. ⛏ | 3 | robelw@msconsultancyet.com | N/A | 2025-10-31 13:23:40 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_54f64b39-1f25-40fe-ab57-0a0de651a729/IMG_7741-16_22_7.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_54f64b39-1f25-40fe-ab57-0a0de651a729/0e5c409169f43be1df3a20c148570327-16_22_14.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_54f64b39-1f25-40fe-ab57-0a0de651a729/IMG_7743-16_22_24.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_54f64b39-1f25-40fe-ab57-0a0de651a729/IMG_7671-16_22_52.jpeg
uuid:a04d9c7f-c631-4107-aea8-01b896f0c66c | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a04d9c7f-c631-4107-aea8-01b896f0c66c/IMG_7639-7_19_30.jpeg | 2025-10-29 | 43.1672 | 9.1088 | Kebribeyah utility office, booster pump stations | In Progress | Daily Report Summary Date: 29 October 2025 Location: Kebribeyah Town, Fafen Zone, Somali Region Project: R-WASH–ETH Kebribeyah Water Supply Construction Project Subject: UNICEF/KfW Site Visit A joint site visit was conducted by UNICEF, KfW, and UNHCR representatives to the R-WASH–ETH Kebribeyah Water Supply Construction Project, as part of their itinerary covering Kebribeyah, Awbare, and Sheder sites in the Fafen Zone. The team reviewed progress on key components including the reservoir site, utility office building works, and booster pump station sites. | 3 | robelw@msconsultancyet.com | N/A | 2025-10-30 04:21:40 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a04d9c7f-c631-4107-aea8-01b896f0c66c/IMG_7623-7_19_43.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a04d9c7f-c631-4107-aea8-01b896f0c66c/IMG_7622-7_20_0.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a04d9c7f-c631-4107-aea8-01b896f0c66c/IMG_7611-7_20_12.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_a04d9c7f-c631-4107-aea8-01b896f0c66c/IMG_7555-7_20_32.jpeg
uuid:bc265b24-9c30-4f03-9501-1ffcbe781b8b | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bc265b24-9c30-4f03-9501-1ffcbe781b8b/31a68f6941ce6929f192c24ee2924631-13_9_30.jpeg | 2025-10-28 | 43.1677 | 9.1096 | Utility office and boreholes | In Progress | Daily Activity Report 🪏 Date: 28 October 2025 Location: Kebribeyah Town, Somali Region Project: R-WASH – Civil, Pipeline, and Electro-Mechanical Works Summary: • Utility Office Building: Foundation masonry, grade beam concrete, and septic tank works completed. Backfilling, floor slab rebar, and preparation ongoing. • Borehole Compound & Access Road: Site clearance and stone dumping for foundation masonry carried out. | 2 | robelw@msconsultancyet.com | N/A | 2025-10-28 10:14:03 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bc265b24-9c30-4f03-9501-1ffcbe781b8b/IMG_7487-13_9_57.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bc265b24-9c30-4f03-9501-1ffcbe781b8b/IMG_7488-13_12_33.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bc265b24-9c30-4f03-9501-1ffcbe781b8b/IMG_7486-13_12_43.jpeg
uuid:dc86e899-f22f-4168-a241-672127581c5f | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dc86e899-f22f-4168-a241-672127581c5f/IMG_7407-11_54_38.jpeg | 2025-10-27 | 43.0177 | 9.0048 | Boreholes | In Progress | Daily HSE Activity Report Date: 27 October 2025 Location: Kebribeyah Town, Somali Region Project: R-WASH – Construction of Civil Works, Supply & Installation of Pipes, and Electro-Mechanical Works ⸻ Summary: The Senior Environmental Safeguard Officer of CES-MSC, Mr. Getachew Feten, conducted a comprehensive assessment to evaluate the contractor’s readiness and preparedness for implementing Health, Environmental, and Safety (HES) measures across the project. The assessment was undertaken in close coordination with all key stakeholders — the Employer, Contractor, Consultant, and local community representatives. The discussions focused on reviewing the contractor’s HES management system, assessing site-level preparedness and workforce awareness, addressing Right-of-Way (ROW) concerns, and ensuring alignment with environmental and safety requirements prior to the commencement of major construction works. The session concluded with a shared commitment among all parties to enhance cooperation, improve on-site HES implementation, and maintain continuous monitoring and compliance with contractual and safeguard obligations. | 2 | robelw@msconsultancyet.com | N/A | 2025-10-27 08:57:59 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dc86e899-f22f-4168-a241-672127581c5f/IMG_7406-11_54_48.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dc86e899-f22f-4168-a241-672127581c5f/IMG_7413-11_55_0.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dc86e899-f22f-4168-a241-672127581c5f/IMG_7373-11_55_21.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_dc86e899-f22f-4168-a241-672127581c5f/IMG_7414-11_56_5.jpeg
uuid:ae438c0f-a349-449b-b540-4c19d3b669ae | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ae438c0f-a349-449b-b540-4c19d3b669ae/IMG_7400-10_23_43.jpeg | 2025-10-26 | 43.1675 | 9.1093 | Utility office | In Progress | NOTE: HES MEETING HELD | 2 | robelw@msconsultancyet.com | N/A | 2025-10-27 07:25:32 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ae438c0f-a349-449b-b540-4c19d3b669ae/IMG_7399-10_23_48.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ae438c0f-a349-449b-b540-4c19d3b669ae/IMG_7373-10_24_1.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ae438c0f-a349-449b-b540-4c19d3b669ae/IMG_7298-10_24_21.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ae438c0f-a349-449b-b540-4c19d3b669ae/IMG_7308-10_24_35.jpeg
uuid:f15aa94e-daed-411d-b8c2-e75e3c61990f | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f15aa94e-daed-411d-b8c2-e75e3c61990f/IMG_7405-10_17_28.jpeg | 2025-10-27 | 43.1673 | 9.1096 | Utility office building at the existing reservoir site in the town | In Progress | ⚠️ Note: The Engineer is working tirelessly to ensure the contractor maintains steady progress and strictly implements all Health, Safety, and Environmental (HSE) measures as per the contractual obligations. Continuous supervision, reminders, and follow-ups are being carried out to reinforce compliance and promote safe working practices on site. 🚧👷‍♂️💪 | 2 | robelw@msconsultancyet.com | N/A | 2025-10-27 07:22:59 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f15aa94e-daed-411d-b8c2-e75e3c61990f/IMG_7401-10_17_35.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f15aa94e-daed-411d-b8c2-e75e3c61990f/IMG_7403-10_17_41.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f15aa94e-daed-411d-b8c2-e75e3c61990f/IMG_7402-10_17_52.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_f15aa94e-daed-411d-b8c2-e75e3c61990f/IMG_7370-10_22_50.jpeg
uuid:3b6f75a7-6ca5-4964-b9bd-41fd19e42958 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A3b6f75a7-6ca5-4964-b9bd-41fd19e42958/attachment/IMG_7212-20_16_38.png?project_id=26&form_id=RWASH_Activity_20250831 | 2025-10-23 | 43.1674 | 9.1101 | Utility office, boreholes | In Progress | 🛠 Daily Activity Report – Summary Date: 23 October 2025 Location: Kebribeyah Town, Somali Region Project: R-WASH – Civil Works, Pipe Supply & Installation, and Electro-Mechanical Works 1. Borehole Sites (BHs): • Setting-out works completed as per approved survey data. • ROW and site access restored after delays since 04 October 2025 through joint efforts of SRSWB and the local administration. • Contractor’s survey team mobilized and resumed activities. 2. Utility Office Building – Existing Reservoir Site: • Setting-out, site clearance, excavation, compaction, and lean concrete works completed. • Foundation masonry completed; septic tank and grade beam works in progress. 3. Project Signboard: • Fabricated and installed on site. 🪧 4. Construction Material Testing: • Material samples collected for quality testing. 🧪 5. Surveying Works: • Ongoing data compilation and verification for joint submission. 📏 Note: Site Access Update: Due to Right-of-Way (ROW) and site access challenges around the borehole areas, works had been interrupted since 04 October 2025. Through the joint efforts of the local administration and SRSWB, access to the borehole sites has now been granted. As of today, 23 October 2025, the contractor’s survey team successfully entered the sites and commenced surveying and setting-out activities.🚧👷‍♂️ | 2 | robelw@msconsultancyet.com | N/A | 2025-10-23 17:22:33 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A3b6f75a7-6ca5-4964-b9bd-41fd19e42958/attachment/IMG_7177-20_17_11.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A3b6f75a7-6ca5-4964-b9bd-41fd19e42958/attachment/IMG_7187-20_17_24.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A3b6f75a7-6ca5-4964-b9bd-41fd19e42958/attachment/IMG_7210-20_17_32.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A3b6f75a7-6ca5-4964-b9bd-41fd19e42958/attachment/IMG_7009-20_21_47.jpeg?project_id=26&form_id=RWASH_Activity_20250831
uuid:c982c73a-ffde-4049-9008-4bfe2cc459cb | Ethiopia | Aw Barre | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3Ac982c73a-ffde-4049-9008-4bfe2cc459cb/attachment/1761204208762.jpg?project_id=26&form_id=RWASH_Activity_20250831 | 2025-10-23 | 43.2145 | 9.7796 | Utility office | In Progress | The utility office already commenced and in good progress | 15 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-10-23 09:24:48 | N/A
uuid:8feeaacc-4cf8-42ce-a679-361babc68ded | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A8feeaacc-4cf8-42ce-a679-361babc68ded/attachment/IMG_6958-8_19_1.jpeg?project_id=26&form_id=RWASH_Activity_20250831 | 2025-10-20 | 43.1675 | 9.1087 | Service reservoir / utility office building | In Progress | 🛠 Daily Activity Report 🪏 Date: 20 October 2025 Location: Kebribeyah Town, Somali Region Project: R-WASH – Construction of Civil Works, Supply & Installation of Pipes, and Electro-Mechanical Works ⸻ 1. Utility Office Building – Existing Reservoir Site • Setting-out successfully completed. ✅ • Site clearance completed, ensuring a clean and well-defined work area. ✅ • Bulk foundation excavation completed as per approved dimensions. ✅ • Foundation bed compaction achieved prior to lean concrete. ✅ • Lean concrete placement completed and inspected. ✅ • Masonry work for the foundation completed. 🧱 • Backfilling and compaction around the foundation currently in progress. 🚜 • Septic tank works — including setting-out, site clearance, bulk excavation, lean concrete, and wall masonry — are actively progressing on site. 💪 Overall Progress: Works are advancing steadily with good momentum observed on site. ⚠️ Safety: Ensure strict implementation of HSE measures, including installation of caution boards (“Men at Work”), safety caution tape, and full enforcement of PPE usage within the active work zone. 🚧👷‍♂️🏗 ⸻ ‼️ Note to Employer / Stakeholders: Dear all, Right-of-Way (ROW) and site access to the borehole areas remain restricted despite continuous follow-up and coordination efforts by SRSWB and the local administration. The contractor has raised claim / concern over the ongoing obstruction. ➡️ Immediate intervention by the concerned stakeholders is required to resolve this issue and avoid further project delays. Please maintain close communication and joint coordination to reach a timely solution. | 2 | robelw@msconsultancyet.com | N/A | 2025-10-20 05:37:48 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A8feeaacc-4cf8-42ce-a679-361babc68ded/attachment/IMG_6964-8_19_20.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A8feeaacc-4cf8-42ce-a679-361babc68ded/attachment/IMG_6978-8_22_44.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A8feeaacc-4cf8-42ce-a679-361babc68ded/attachment/IMG_6952-8_22_56.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A8feeaacc-4cf8-42ce-a679-361babc68ded/attachment/IMG_6768-8_23_22.jpeg?project_id=26&form_id=RWASH_Activity_20250831
uuid:ca01e0c8-dd58-4663-b94c-d624f0e0a5d2 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ca01e0c8-dd58-4663-b94c-d624f0e0a5d2/IMG_6722-18_50_15.jpeg | 2025-10-14 | 43.1675 | 9.1092 | Service reservoir; utility office building | In Progress | R-WASH Daily Activity Report Date: 14 October 2025 Project Location: Kebribeyah Town, Somali Region Project: R-WASH – Construction of Civil Works, Supply & Installation of Pipes, and Electro-Mechanical Works 1. Utility Office Building – Existing Reservoir Site • Setting-out completed. • Site clearance completed. • Bulk foundation excavation completed. • Foundation bed compaction completed prior to lean concrete. • Lean concrete placement completed. • Masonry work for foundation in progress. • Note: Benchmark verification and topographic data collection completed to ensure layout accuracy and elevation control. Excavation levels and foundation alignment verified against approved design drawings prior to lean concrete casting. 2. Material Sampling • Selected construction material samples taken for testing to support backfilling granular material. • Previously tested aggregate, sand, and cement used in trial mixes for concrete mix design. • All sampling and testing conducted to ensure quality compliance and mix design verification. | 2 | robelw@msconsultancyet.com | N/A | 2025-10-14 15:52:44 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ca01e0c8-dd58-4663-b94c-d624f0e0a5d2/IMG_6718-18_50_31.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ca01e0c8-dd58-4663-b94c-d624f0e0a5d2/IMG_6725-18_50_53.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ca01e0c8-dd58-4663-b94c-d624f0e0a5d2/IMG_6724-18_51_3.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_ca01e0c8-dd58-4663-b94c-d624f0e0a5d2/IMG_6720-18_51_15.jpeg
uuid:8fa11d4a-f7d7-4ea6-a485-ac29aa1ba369 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8fa11d4a-f7d7-4ea6-a485-ac29aa1ba369/IMG_6531-18_30_6.jpeg | 2025-10-13 | 43.1675 | 9.1091 | Kebribeyah town | In Progress | R-WASH Daily Activity Report Date: 13 October 2025 Project Location: Kebribeyah Town, Somali Region Project: R-WASH – Construction of Civil Works, Supply & Installation of Pipes, and Electro-Mechanical Works ⸻ 1. Utility Office Building – Existing Reservoir Site • Setting-out completed. • Site clearance executed. • Bulk foundation excavation in progress. • Foundation bed compaction completed prior to lean concrete. • Lean concrete placement ongoing. • Note: Topographic data collected and verified for layout accuracy. ⸻ 2. Construction Material Sampling & Laboratory Work • Concrete mix design and trial mix preparation in progress. • Aggregate and sand samples tested for mix-design validation. • Laboratory testing underway to ensure quality compliance. ⸻ 3. Benchmark & Survey Work • Benchmark dissemination and re-establishment completed by subcontracted survey team (original benchmarks missing). • Alternative benchmarks verified and adopted. • Setting-out and topographic data collection continued at the existing reservoir site. • Draft shop drawing for the utility office building submitted and reviewed. ⸻ 4. On-Site Laboratory Setup • On-site laboratory setup and calibration completed. • Equipment testing and verification ongoing to prepare for material testing activities. ⸻ 5. Proposed Rock Stone Quarry (for Masonry Work) • Rock quarry inspected and proposed for masonry use. • Material condition found suitable pending laboratory confirmation. • Recommended Test: Water Absorption Test to confirm durability and quality. ⸻ 6. Site Clearance, Rehabilitation & Coordination • Site clearance and rehabilitation works ongoing at KBPS-01 and KBPS-02. • Work preparation progressing, including shop-drawing updates and methodology development. • Activities under continuous inspection and supervision. • Joint 3C (Client – Consultant – Contractor) coordination meeting conducted for work review. ⸻ 7. Community ROW (Right-of-Way) Issue • Site-access issue encountered near borehole benchmark area due to community ROW obstruction. • Employer’s team, City Mayor’s Office, and Woreda Administration coordinating to resolve the issue. • Immediate intervention required to proceed with borehole-related works. ⸻ 8. Project Sign Board & Fence Post • Shop drawings for sign board, sign post, and fence post under review and revision. • Sample unit production ongoing at contractor’s camp for final approval. • Revised drawings to be re-submitted for Engineer’s approval. ⸻ 9. Shop Drawing Revision & Approval • Revised shop drawings for the utility office building and related structures under Engineer’s review. • Contractor incorporating comments for resubmission. • Approved drawings will guide upcoming structural and finishing works. | 2 | robelw@msconsultancyet.com | N/A | 2025-10-13 15:35:40 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8fa11d4a-f7d7-4ea6-a485-ac29aa1ba369/d89f543784172f0a3482a612207ff269-18_30_32.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_8fa11d4a-f7d7-4ea6-a485-ac29aa1ba369/IMG_6509-18_30_57.jpeg
https://odk-middleman.onrender.com/api/submission/uuid%3A8fa11d4a-f7d7-4ea6-a485-ac29aa1ba369/attachment/IMG_6444-18_31_24.png?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A8fa11d4a-f7d7-4ea6-a485-ac29aa1ba369/attachment/IMG_6532-18_32_7.jpeg?project_id=26&form_id=RWASH_Activity_20250831
uuid:56c0a38e-9c70-44b1-9a84-3773f0bf4d59 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A56c0a38e-9c70-44b1-9a84-3773f0bf4d59/attachment/IMG_6662-18_25_31.jpeg?project_id=26&form_id=RWASH_Activity_20250831 | 2025-10-13 | 43.1674 | 9.1093 | Kebribeyah service reservoir location utility office building | In Progress | R-WASH Daily Activity Report Date: 13 October 2025 Project Location: Kebribeyah Town, Somali Region Project: R-WASH – Construction of Civil Works, Supply & Installation of Pipes, and Electro-Mechanical Works ⸻ 1. Utility Office Building – Existing Reservoir Site • Setting out works completed. • Site clearance carried out. • Bulk foundation excavation in progress. • Foundation bed compaction completed prior to lean concrete. • Lean concrete placement ongoing. • Note: Topographic data collected and verified for layout accuracy. | 2 | robelw@msconsultancyet.com | N/A | 2025-10-13 15:27:53 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A56c0a38e-9c70-44b1-9a84-3773f0bf4d59/attachment/0d8f6e16a74eae30a9a21f7960ea6c55-18_25_48.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A56c0a38e-9c70-44b1-9a84-3773f0bf4d59/attachment/IMG_6675-18_26_1.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A56c0a38e-9c70-44b1-9a84-3773f0bf4d59/attachment/IMG_6676-18_26_11.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A56c0a38e-9c70-44b1-9a84-3773f0bf4d59/attachment/IMG_6511-18_26_39.png?project_id=26&form_id=RWASH_Activity_20250831
uuid:49457ff5-a7e2-4345-9fbf-c0279121c965 | Ethiopia | Shedder | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A49457ff5-a7e2-4345-9fbf-c0279121c965/attachment/1760082877272.jpg?project_id=26&form_id=RWASH_Activity_20250831 | 2025-10-10 | 43.1299 | 9.6926 | Transmission and Distribution pipelines | In Progress | Pipe supply progress going well, the the other activities are has been initiating. | 14 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-10-10 08:04:46 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A49457ff5-a7e2-4345-9fbf-c0279121c965/attachment/1760082882928.jpg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A49457ff5-a7e2-4345-9fbf-c0279121c965/attachment/1760083081023.jpg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A49457ff5-a7e2-4345-9fbf-c0279121c965/attachment/1760083223343.jpg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A49457ff5-a7e2-4345-9fbf-c0279121c965/attachment/1760083279325.jpg?project_id=26&form_id=RWASH_Activity_20250831
uuid:b8a8dfa8-ee73-458b-aefd-f028e2b89c6b | Ethiopia | Aw Barre | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3Ab8a8dfa8-ee73-458b-aefd-f028e2b89c6b/attachment/1760078287396.jpg?project_id=26&form_id=RWASH_Activity_20250831 | 2025-10-07 | 43.2142 | 9.7799 | Transmission and distribution pipeline | In Progress | Supply of all contract pipe quantity about 85% completed and the remain is finalized in October reporting month. | 16 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-10-10 06:46:28 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3Ab8a8dfa8-ee73-458b-aefd-f028e2b89c6b/attachment/1760078305941.jpg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3Ab8a8dfa8-ee73-458b-aefd-f028e2b89c6b/attachment/1760078468307.jpg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3Ab8a8dfa8-ee73-458b-aefd-f028e2b89c6b/attachment/1760078489629.jpg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3Ab8a8dfa8-ee73-458b-aefd-f028e2b89c6b/attachment/1760078595805.jpg?project_id=26&form_id=RWASH_Activity_20250831
uuid:7576b552-a31d-47e1-a8a9-0831dc1da13a | Ethiopia | Aw Barre | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A7576b552-a31d-47e1-a8a9-0831dc1da13a/attachment/1759932249841.jpg?project_id=26&form_id=RWASH_Activity_20250831 | 2025-10-08 | 43.2142 | 9.7753 | Utility office | In Progress | At commencement stage | 2 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-10-08 14:06:29 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A7576b552-a31d-47e1-a8a9-0831dc1da13a/attachment/1759932284336.jpg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A7576b552-a31d-47e1-a8a9-0831dc1da13a/attachment/1759932318862.jpg?project_id=26&form_id=RWASH_Activity_20250831
uuid:030256a3-eed8-42d9-84f3-6c4f35df7714 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A030256a3-eed8-42d9-84f3-6c4f35df7714/attachment/IMG_6444-19_46_0.png?project_id=26&form_id=RWASH_Activity_20250831 | 2025-10-06 | 43.0107 | 9.0036 | kebribeyah booster pump station and borholes | In Progress | R-WASH Activity Monitoring Summary Report Location: Kebribeyah Town, Somali Region Reporting Period: 03 – 06 October 2025 Summary: Calibration of construction and testing equipment was completed and reported. On-site and third-party laboratory works for concrete mix design continued. Preparations for rehabilitation of Booster Pump Stations 01 & 02 and related infrastructure are underway, with mobilization and site setup progressing. ROW and access challenges at borehole sites are impacting progress; coordination with local authorities and the Water Utility is ongoing to ensure timely resolution. Observations & Highlights • ROW and access issues remain a key concern; resolution efforts shall be actively engaged by the SRS Water Bureau and Water Utility representatives, in collaboration with the local administration. | 1 | robelw@msconsultancyet.com | N/A | 2025-10-06 16:50:02 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A030256a3-eed8-42d9-84f3-6c4f35df7714/attachment/IMG_6457-19_46_10.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A030256a3-eed8-42d9-84f3-6c4f35df7714/attachment/IMG_6448-19_47_18.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A030256a3-eed8-42d9-84f3-6c4f35df7714/attachment/IMG_6453-19_47_29.jpeg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A030256a3-eed8-42d9-84f3-6c4f35df7714/attachment/3b5d92836693ea6987ff6aa85934b9ae-19_48_48.jpeg?project_id=26&form_id=RWASH_Activity_20250831
uuid:521beb75-c1d5-478f-8c1a-693410a89828 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A521beb75-c1d5-478f-8c1a-693410a89828/attachment/1759495470188.jpg?project_id=26&form_id=RWASH_Activity_20250831 | 2025-10-03 | 43.2115 | 9.7833 | Service Reservoir | In Progress | The contractor has damaged constraction material at different sites and quality, trail and mix-design test will conducted soon jointly with consultant. | 2 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-10-03 12:48:10 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A521beb75-c1d5-478f-8c1a-693410a89828/attachment/1759495494848.jpg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A521beb75-c1d5-478f-8c1a-693410a89828/attachment/1759495511884.jpg?project_id=26&form_id=RWASH_Activity_20250831
https://odk-middleman.onrender.com/api/submission/uuid%3A521beb75-c1d5-478f-8c1a-693410a89828/attachment/1759495544939.jpg?project_id=26&form_id=RWASH_Activity_20250831
uuid:de81fba4-6593-47bf-b655-2d7fe6a7a0c2 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_de81fba4-6593-47bf-b655-2d7fe6a7a0c2/1759495030177.jpg | 2025-10-03 | 43.2219 | 9.7828 | Distribution pipeline | In Progress | Distribution popeline survey work completed. | 2 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-10-03 12:39:00 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_de81fba4-6593-47bf-b655-2d7fe6a7a0c2/1759495036556.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_de81fba4-6593-47bf-b655-2d7fe6a7a0c2/1759495045713.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_de81fba4-6593-47bf-b655-2d7fe6a7a0c2/1759495051585.jpg
uuid:bcafc3f1-f5c8-467d-928e-75ca5bfb8ddb | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bcafc3f1-f5c8-467d-928e-75ca5bfb8ddb/1759494456119.jpg | 2025-10-03 | 43.2152 | 9.806 | Transmissions and collector pipeline | In Progress | Transmission pipeline seet out already completed. | 2 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-10-03 12:32:28 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bcafc3f1-f5c8-467d-928e-75ca5bfb8ddb/1759494511345.jpg
uuid:0d5d5b44-c013-4695-a2d1-c9efafe3712f | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0d5d5b44-c013-4695-a2d1-c9efafe3712f/IMG_6272-18_41_11.jpeg | 2025-10-02 | 43.167 | 9.1094 | Kebribeyah town, Somali region | In Progress | R-WASH Activity Monitoring Summary Report Region: Eastern and Southern Africa Region (ESAR) Country: Ethiopia Project Locations: Kebribeyah Town, Somali Region Reporting Period / Date: 30 September – 02 October 2025 1. Project Overview • Construction of Civil Works, Supply & Installation of Pipes, Electro-Mechanical works, and Material Testing. 2. Key Activities Conducted • Material Sampling & Laboratory Work: o Aggregate sampling (Type 02 & 01) completed at Jigjiga crusher for concrete mix design. o Sand sampling conducted/planned at Kebribeyah Quarry (Option Quarry-1) on 01 October 2025. o Onsite and contractor laboratories setup ongoing for quality control and mix design preparation. o Third-party document review and material testing coordinated with consultants. • Benchmarking & Site Verification: o Benchmark leveling, dissimulation checks, and verification completed per contract requirements. o Topographic and setting-out data collected to support upcoming works. • Contractor Camp & Facility Works: o Establishing offices, dormitories, kitchen, storage, guard house, toilets, and on-site labs. o Garage/workshop, car parking, main gate, and fencing works in progress. o Material mobilization and other camp construction activities ongoing. • Engineer Document Review & Onsite Follow-Up: o Reviewed and responded to contractor-submitted documents. o Conducted office tasks, report preparation, and internal coordination. o Followed up onsite to ensure compliance with project specifications. • Contractor Work Facilitation: o Issued instructions and facilitated contractor activities to maintain schedule and quality. • Stakeholder Engagement: o Joint meetings held with client, contractor, and consultant on: - Rehabilitation of Booster Pump Stations 1 & 2, Existing reservoirs o Planned site inspections for 03 October 2025 coordinated. 3. Observations & Highlights • Contractor camp and site preparation progressing well. • Material sampling activities on schedule to support upcoming concrete works. • Benchmarking and verification provide a solid foundation for accurate site layout. • Coordination with stakeholders ensures smooth commencement of rehabilitation works. • Consideration ongoing for pipeline integration with master plan, community participation, and ROW issues. 4. Next Steps / Planned Activities • Continue guiding and monitoring overall project implementation. • Follow up on material sampling and testing results to ensure quality compliance. • Support the contractor and consultant in rehabilitation works, ensuring integration with uninterrupted operation of the existing water supply system, and preparing, implementing, and agreeing on the work methodology. • Conduct planned site inspections for Booster Pump Stations and existing reservoirs. • Facilitate and commence civil works as per approved plans. • Review, verify, and approve shop drawings to ensure conformity with project specifications. | 1 | N/A | N/A | 2025-10-02 15:43:18 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0d5d5b44-c013-4695-a2d1-c9efafe3712f/IMG_6282-18_41_23.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0d5d5b44-c013-4695-a2d1-c9efafe3712f/IMG_6242-18_41_58.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0d5d5b44-c013-4695-a2d1-c9efafe3712f/IMG_6279-18_42_25.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_0d5d5b44-c013-4695-a2d1-c9efafe3712f/IMG_6283-18_42_43.jpeg
uuid:4ecb66b5-4194-4afc-b21f-428939a4c54d | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_4ecb66b5-4194-4afc-b21f-428939a4c54d/1759298405176.jpg | 2025-10-01 | 43.1225 | 9.6916 | Town Distribution Pipeline | In Progress | Distribution pipeline setting out has completed and the others activities going well. | 1 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-10-01 06:03:19 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_4ecb66b5-4194-4afc-b21f-428939a4c54d/1759298412953.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_4ecb66b5-4194-4afc-b21f-428939a4c54d/1759298424924.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_4ecb66b5-4194-4afc-b21f-428939a4c54d/1759298468766.jpg
uuid:04302c76-c88e-46a7-a04f-d5dd79bcfd21 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_04302c76-c88e-46a7-a04f-d5dd79bcfd21/1759297710085.jpg | 2025-10-01 | 43.1315 | 9.6853 | Service Reservoir | In Progress | Mobilization and construction material delivery on site has going well | 1 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-10-01 05:52:22 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_04302c76-c88e-46a7-a04f-d5dd79bcfd21/1759297790174.jpg
uuid:e63dab79-311c-45bb-80da-da77ecab22d4 | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e63dab79-311c-45bb-80da-da77ecab22d4/IMG_6214-19_23_37.jpeg | 2025-09-29 | 43.1626 | 9.11 | Kebribeyah | In Progress | Contractor’s Camp Construction • Site offices, dormitory, kitchen, storage containers, guard house, toilets, and onsite laboratory are being established. • Garage/workshop, car parking, main gate, and fence installation are ongoing. • Labour housing with cooking and eating areas has been prepared. ⸻ Material Sampling Activities • 29 Sept 2025 (Today): Aggregate samples (Type 02 & Type 01) collected from Jigjiga crusher for concrete mix design preparation. • 30 Sept 2025 (Planned): Sand sample collection scheduled at Kebribeyah quarry for use in concrete mix design and compliance testing. | 1 | N/A | N/A | 2025-09-29 16:26:33 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e63dab79-311c-45bb-80da-da77ecab22d4/IMG_6205-19_23_47.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e63dab79-311c-45bb-80da-da77ecab22d4/IMG_6201-19_23_55.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e63dab79-311c-45bb-80da-da77ecab22d4/IMG_6203-19_24_5.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_e63dab79-311c-45bb-80da-da77ecab22d4/IMG_6176-19_24_23.jpeg
uuid:5e16a0d3-dfb8-401f-bc88-498d03d03bf6 | Ethiopia | Aw Barre | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_5e16a0d3-dfb8-401f-bc88-498d03d03bf6/1758888363893.jpg | 2025-09-26 | 43.2142 | 9.7818 | Mobilization and camp construction at service Reservoir | In Progress | The contractor has been mobilizing machinery, key personnel and camp construction the remaining 50% will be finalized until end of the reporting month. | 50 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-09-26 12:12:31 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_5e16a0d3-dfb8-401f-bc88-498d03d03bf6/1758888388649.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_5e16a0d3-dfb8-401f-bc88-498d03d03bf6/1758888436797.jpg
uuid:bba4226f-4b25-4f6d-951f-f83369ee374c | Ethiopia | Kebribeyah | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_bba4226f-4b25-4f6d-951f-f83369ee374c/Screenshot%202025-07-16%20160458-15_37_37.png | 2025-09-23 | 38.7678 | 9.0079 | booster pump station | In Progress | under progress | 15 | robelw@msconsultancyet.com | N/A | 2025-09-23 12:38:48 | N/A
uuid:2db735f8-b89c-4906-9ad4-7e34557620db | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_2db735f8-b89c-4906-9ad4-7e34557620db/1758629805367.jpg | 2025-09-23 | 36.8845 | -1.2357 | Shedder Booster Station | In Progress | Good progress | 26 | N/A | collect:hNjsSOlP0WGhSZEX | 2025-09-23 12:19:02 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_2db735f8-b89c-4906-9ad4-7e34557620db/1758629837462.jpg
uuid:c4cd4637-6f3d-4e6e-9354-e8ccb0a7e0d4 | Ethiopia | Shedder | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c4cd4637-6f3d-4e6e-9354-e8ccb0a7e0d4/1758629805957.jpg | 2025-09-23 | 42.8084 | 9.3552 | Shedder booster station | In Progress | Good progress | 26 | N/A | collect:G2pcZJtXH1x4Swyk | 2025-09-23 12:18:59 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/26/RWASH_Activity_20250831/uuid_c4cd4637-6f3d-4e6e-9354-e8ccb0a7e0d4/1758629844696.jpg