## RWASH_Activity_20250730
Instance ID | Country Name | Site Name | Image Description | Image Path | Image Date | Longitude | Latitude | Activity Status | Comments | Project Description | Completion Percentage | Username | Device ID | Created At | Status
uuid:fb305ba6-8db4-4873-a81e-11dc2f439243 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_fb305ba6-8db4-4873-a81e-11dc2f439243/1770391526848.jpg | 2026-02-06 | 48.4824 | 8.4031 | GLA-BH-01-2025 | Completed | The team completed the remaining works like grouting of the surface casing and well head construction and demobilized the rig and all other drilling materials from the site. | N/A | N/A | collect:oJw9QIFTUBAakeRh | 2026-02-06 15:28:25 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_fb305ba6-8db4-4873-a81e-11dc2f439243/1770391536800.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_fb305ba6-8db4-4873-a81e-11dc2f439243/1770391549196.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_fb305ba6-8db4-4873-a81e-11dc2f439243/1770391556908.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_fb305ba6-8db4-4873-a81e-11dc2f439243/1770391570618.jpg
uuid:b399c0a8-c380-41e3-888c-e22c1625aea4 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_b399c0a8-c380-41e3-888c-e22c1625aea4/1770098934936.jpg | 2026-02-03 | 48.41 | 8.3915 | GLA-BH-01-2025 | In Progress | The team completed the constant pumping test and the total pumping duration is 72 hours. The remaining work is flushing the water with compressor to confirm the water quality, grouting and site cleearing. | 80 | N/A | collect:oJw9QIFTUBAakeRh | 2026-02-03 06:13:11 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_b399c0a8-c380-41e3-888c-e22c1625aea4/1770098954044.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_b399c0a8-c380-41e3-888c-e22c1625aea4/1770098971084.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_b399c0a8-c380-41e3-888c-e22c1625aea4/1770098991109.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_b399c0a8-c380-41e3-888c-e22c1625aea4/1770099010448.jpg
uuid:f522c540-5780-41ae-9893-01029be98c6e | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_f522c540-5780-41ae-9893-01029be98c6e/1769853054365.jpg | 2026-01-31 | 48.41 | 8.3914 | GLA-BH-01-2025 | In Progress | The team started the pumping test at a pump position of 453m with discharge 3.5 l/sec. | 80 | N/A | collect:oJw9QIFTUBAakeRh | 2026-01-31 09:53:26 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_f522c540-5780-41ae-9893-01029be98c6e/1769853066571.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_f522c540-5780-41ae-9893-01029be98c6e/1769853078324.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_f522c540-5780-41ae-9893-01029be98c6e/1769853092289.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_f522c540-5780-41ae-9893-01029be98c6e/1769853105894.jpg
uuid:3331f977-f1bd-4358-b068-f9553d77bb0a | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_3331f977-f1bd-4358-b068-f9553d77bb0a/1769074043742.jpg | 2026-01-22 | 48.41 | 8.3914 | GLA-01-BH | In Progress | The team started sealing the borehole by making ball with mixture of clay and bentonite with a size of 30-40mm. | 78 | N/A | collect:oJw9QIFTUBAakeRh | 2026-01-22 09:30:34 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_3331f977-f1bd-4358-b068-f9553d77bb0a/1769074053324.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_3331f977-f1bd-4358-b068-f9553d77bb0a/1769074064154.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_3331f977-f1bd-4358-b068-f9553d77bb0a/1769074080253.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_3331f977-f1bd-4358-b068-f9553d77bb0a/1769074090680.jpg
uuid:2245ffc6-3ecd-4953-8e8e-62e17872ffc3 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_2245ffc6-3ecd-4953-8e8e-62e17872ffc3/1768887901002.jpg | 2026-01-20 | 48.4101 | 8.3913 | GLA-01-BH | In Progress | The team started sealing of the upper part of the borehole with a mixture of clay and bentonite. | 76 | N/A | collect:oJw9QIFTUBAakeRh | 2026-01-20 05:48:25 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_2245ffc6-3ecd-4953-8e8e-62e17872ffc3/1768887912784.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_2245ffc6-3ecd-4953-8e8e-62e17872ffc3/1768887930695.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_2245ffc6-3ecd-4953-8e8e-62e17872ffc3/1768887950012.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_2245ffc6-3ecd-4953-8e8e-62e17872ffc3/1768887992571.jpg
uuid:0aed3f02-0ff6-4883-a1c8-3676f230f6fb | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_0aed3f02-0ff6-4883-a1c8-3676f230f6fb/1768486283306.jpg | 2026-01-15 | 48.41 | 8.3915 | GLA-BH-01 | In Progress | The team started camera recording today at 5:00PM to inspect the gravel and the casing untill the last depth. | 76 | N/A | collect:oJw9QIFTUBAakeRh | 2026-01-15 14:14:10 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_0aed3f02-0ff6-4883-a1c8-3676f230f6fb/1768486292786.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_0aed3f02-0ff6-4883-a1c8-3676f230f6fb/1768486311589.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_0aed3f02-0ff6-4883-a1c8-3676f230f6fb/1768486327559.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_0aed3f02-0ff6-4883-a1c8-3676f230f6fb/1768486343766.jpg
uuid:b1457b4d-15e4-4af9-ba17-e1147570c593 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_b1457b4d-15e4-4af9-ba17-e1147570c593/1768310119593.jpg | 2026-01-13 | 48.4823 | 8.4031 | GLA-BH-01 | In Progress | The team completed well development and waiting for borehole camera to inspect the borehole and gravel packing. | 75 | N/A | collect:oJw9QIFTUBAakeRh | 2026-01-13 13:17:48 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_b1457b4d-15e4-4af9-ba17-e1147570c593/1768310128919.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_b1457b4d-15e4-4af9-ba17-e1147570c593/1768310136172.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_b1457b4d-15e4-4af9-ba17-e1147570c593/1768310147631.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_b1457b4d-15e4-4af9-ba17-e1147570c593/1768310158806.jpg
uuid:e73e8430-c832-46d1-85ec-c3bb5c8e2e81 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_e73e8430-c832-46d1-85ec-c3bb5c8e2e81/1767773084877.jpg | 2026-01-07 | 48.41 | 8.3914 | GLA-BH-01 | In Progress | The team completed casing installation and gravel packing, now it started well development. | 75 | N/A | collect:oJw9QIFTUBAakeRh | 2026-01-07 08:07:39 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_e73e8430-c832-46d1-85ec-c3bb5c8e2e81/1767773095421.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_e73e8430-c832-46d1-85ec-c3bb5c8e2e81/1767773122933.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_e73e8430-c832-46d1-85ec-c3bb5c8e2e81/1767773137820.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_e73e8430-c832-46d1-85ec-c3bb5c8e2e81/1767773160239.jpg
uuid:3c9f67ba-d8c6-4d8a-8db7-a0f277b82c92 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_3c9f67ba-d8c6-4d8a-8db7-a0f277b82c92/1767504999160.jpg | 2026-01-04 | 48.41 | 8.3914 | GLA-BH-01 | In Progress | The team started installation of 8" production casing, it is going smoothly and reached at a depth of 520m. | 70 | N/A | collect:oJw9QIFTUBAakeRh | 2026-01-04 05:40:14 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_3c9f67ba-d8c6-4d8a-8db7-a0f277b82c92/1767505015775.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_3c9f67ba-d8c6-4d8a-8db7-a0f277b82c92/1767505034090.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_3c9f67ba-d8c6-4d8a-8db7-a0f277b82c92/1767505057155.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_3c9f67ba-d8c6-4d8a-8db7-a0f277b82c92/1767505070174.jpg
uuid:5d36f400-938b-4aed-811a-192fea9a8d94 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_5d36f400-938b-4aed-811a-192fea9a8d94/1767184923292.jpg | 2025-12-31 | 48.4101 | 8.3914 | GLA-BH-01 | In Progress | The team continued preparation to start installation of the production casing. | 49 | N/A | collect:oJw9QIFTUBAakeRh | 2025-12-31 12:44:59 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_5d36f400-938b-4aed-811a-192fea9a8d94/1767184941524.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_5d36f400-938b-4aed-811a-192fea9a8d94/1767184960407.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_5d36f400-938b-4aed-811a-192fea9a8d94/1767184987817.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_5d36f400-938b-4aed-811a-192fea9a8d94/1767185008572.jpg
uuid:1f885ac8-5614-4e9e-87a3-9a5c8c465123 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_1f885ac8-5614-4e9e-87a3-9a5c8c465123/1766926487940.jpg | 2025-12-28 | 48.4101 | 8.3914 | GLA-BH-1-2025 | In Progress | The team completed conducting of the geophysical logging and started preparation for installation of 8" production casing. | 48 | N/A | collect:oJw9QIFTUBAakeRh | 2025-12-28 12:57:48 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_1f885ac8-5614-4e9e-87a3-9a5c8c465123/1766926508870.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_1f885ac8-5614-4e9e-87a3-9a5c8c465123/1766926526258.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_1f885ac8-5614-4e9e-87a3-9a5c8c465123/1766926554174.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_1f885ac8-5614-4e9e-87a3-9a5c8c465123/1766926573947.jpg
uuid:8b40941e-9044-4bd7-9bd6-5c0eba49b419 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_8b40941e-9044-4bd7-9bd6-5c0eba49b419/1766668155552.jpg | 2025-12-25 | 48.41 | 8.3914 | GLA-BH-01 | In Progress | The team tried to conduct the geophysical logging for the second time, b/c the first operation was not successful due to stacked of the logging probe at 510m. | 46 | N/A | collect:oJw9QIFTUBAakeRh | 2025-12-25 13:13:00 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_8b40941e-9044-4bd7-9bd6-5c0eba49b419/1766668168550.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_8b40941e-9044-4bd7-9bd6-5c0eba49b419/1766668186251.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_8b40941e-9044-4bd7-9bd6-5c0eba49b419/1766668203264.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_8b40941e-9044-4bd7-9bd6-5c0eba49b419/1766668215090.jpg
uuid:8c888470-d931-46f6-a436-42031a7ba9db | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_8c888470-d931-46f6-a436-42031a7ba9db/1766498632076.jpg | 2025-12-23 | 48.4101 | 8.3914 | GLA-BH-01 | In Progress | Conducting of geophysical logging and camera inspection is in progress. | 46 | N/A | collect:oJw9QIFTUBAakeRh | 2025-12-23 14:06:03 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_8c888470-d931-46f6-a436-42031a7ba9db/1766498649588.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_8c888470-d931-46f6-a436-42031a7ba9db/1766498663167.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_8c888470-d931-46f6-a436-42031a7ba9db/1766498676203.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_8c888470-d931-46f6-a436-42031a7ba9db/1766498686605.jpg
uuid:ded1b841-8a7a-4758-84d7-25da1595d51f | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_ded1b841-8a7a-4758-84d7-25da1595d51f/1766299805285.jpg | 2025-12-21 | 48.41 | 8.3915 | GLA-01-BH | In Progress | The drilling operation halted at a depth of 644m and now the team prepared to start geophysical logging and camera inspection. | 46 | N/A | collect:oJw9QIFTUBAakeRh | 2025-12-21 06:53:17 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_ded1b841-8a7a-4758-84d7-25da1595d51f/1766299820271.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_ded1b841-8a7a-4758-84d7-25da1595d51f/1766299845858.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_ded1b841-8a7a-4758-84d7-25da1595d51f/1766299856851.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_ded1b841-8a7a-4758-84d7-25da1595d51f/1766299872387.jpg
uuid:674280ed-490e-475b-97f6-108483e731af | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_674280ed-490e-475b-97f6-108483e731af/1765803169095.jpg | 2025-12-15 | 48.41 | 8.3915 | GLA-BH-01 | Stalled | The drilling operation halted at a depth of 644m due to circulation loss, back fill accumulation, inflow of water from the lower part of the surface casing. It is planned to finalize the drilling at this depth and start well construction after conducted geophysical logging. | 46 | N/A | collect:oJw9QIFTUBAakeRh | 2025-12-15 12:58:07 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_674280ed-490e-475b-97f6-108483e731af/1765803192209.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_674280ed-490e-475b-97f6-108483e731af/1765803207720.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_674280ed-490e-475b-97f6-108483e731af/1765803222682.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_674280ed-490e-475b-97f6-108483e731af/1765803242329.jpg
uuid:4da049e0-ab89-4d34-a9a8-ccf02a62b5d9 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_4da049e0-ab89-4d34-a9a8-ccf02a62b5d9/1765457995082.jpg | 2025-12-11 | 48.41 | 8.3914 | GLA-BH-01 | In Progress | The circulation loss encountered at a depth of 616m, however the drilling resumed without circulation and reached at depth of 638m. | 46 | N/A | collect:oJw9QIFTUBAakeRh | 2025-12-11 13:03:21 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_4da049e0-ab89-4d34-a9a8-ccf02a62b5d9/1765458010662.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_4da049e0-ab89-4d34-a9a8-ccf02a62b5d9/1765458023380.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_4da049e0-ab89-4d34-a9a8-ccf02a62b5d9/1765458040628.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_4da049e0-ab89-4d34-a9a8-ccf02a62b5d9/1765458059917.jpg
uuid:09a13681-5c88-4a2b-bed0-3ab50a560b0e | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_09a13681-5c88-4a2b-bed0-3ab50a560b0e/1765177019335.jpg | 2025-12-08 | 48.41 | 8.3914 | GLA-BH-01 | In Progress | The drilling depth of garowe borehole reached at a depth of 616m, however at this depth a sudden circulation loss encountered and the teams are trying to resolve this issue. | 45 | N/A | collect:oJw9QIFTUBAakeRh | 2025-12-08 07:01:07 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_09a13681-5c88-4a2b-bed0-3ab50a560b0e/1765177029363.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_09a13681-5c88-4a2b-bed0-3ab50a560b0e/1765177045305.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_09a13681-5c88-4a2b-bed0-3ab50a560b0e/1765177064455.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_09a13681-5c88-4a2b-bed0-3ab50a560b0e/1765177105913.jpg
uuid:27dab86f-e4e8-442c-887d-accd5138b3ea | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_27dab86f-e4e8-442c-887d-accd5138b3ea/1764939412821.jpg | 2025-12-05 | 48.41 | 8.3914 | GLA-BH-01 | In Progress | The team resolved the mechanical problem of the rig and resume reinstallation of the drilling pipes and cleaning of the borehole upto the last drilled depth. | 43 | N/A | collect:oJw9QIFTUBAakeRh | 2025-12-05 13:00:25 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_27dab86f-e4e8-442c-887d-accd5138b3ea/1764939427099.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_27dab86f-e4e8-442c-887d-accd5138b3ea/1764939441105.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_27dab86f-e4e8-442c-887d-accd5138b3ea/1764939453247.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_27dab86f-e4e8-442c-887d-accd5138b3ea/1764939475837.jpg
uuid:5f3369b3-6c95-48b5-a4fa-ed365173934e | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_5f3369b3-6c95-48b5-a4fa-ed365173934e/1764572318288.jpg | 2025-12-01 | 48.41 | 8.3914 | GLA-BH-01 | Stalled | Still now the drilling operation not started due to the mechanical problem of the rig (Table rotary) and the team took the damaged part to the workshop, it is planned to resume the drilling within 3 days after the maintenance completed. | 43 | N/A | collect:oJw9QIFTUBAakeRh | 2025-12-01 07:03:05 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_5f3369b3-6c95-48b5-a4fa-ed365173934e/1764572342703.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_5f3369b3-6c95-48b5-a4fa-ed365173934e/1764572352843.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_5f3369b3-6c95-48b5-a4fa-ed365173934e/1764572382774.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_5f3369b3-6c95-48b5-a4fa-ed365173934e/1764572407657.jpg
uuid:547a8c7a-009f-414b-8554-a9b7bb30286b | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_547a8c7a-009f-414b-8554-a9b7bb30286b/1764247695356.jpg | 2025-11-27 | 48.41 | 8.3914 | GLA-BH-01 | Stalled | The team resumed the drilling operation on Nov 26, 2025 after delivered the required drilling rods, however the operation halted again today Nov 27, 2025 at 10:30AM due to mechanical problem of the rig (Table rotary). | 43 | N/A | collect:oJw9QIFTUBAakeRh | 2025-11-27 12:53:51 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_547a8c7a-009f-414b-8554-a9b7bb30286b/1764247733941.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_547a8c7a-009f-414b-8554-a9b7bb30286b/1764247755111.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_547a8c7a-009f-414b-8554-a9b7bb30286b/1764247790747.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_547a8c7a-009f-414b-8554-a9b7bb30286b/1764247840925.jpg
uuid:c42765f2-13a2-4de9-ae72-f05d9c524790 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_c42765f2-13a2-4de9-ae72-f05d9c524790/1763965703784.jpg | 2025-11-24 | 48.41 | 8.3914 | GLA-BH-1 | Stalled | The drilling operation halted starting from Nov 11,2025 due to technical defect of the remaining drilling pipes on the site and the contractor trying to bring it from ethiopia, it will expected to reach the site within 2 days. | 42 | N/A | collect:oJw9QIFTUBAakeRh | 2025-11-24 06:33:13 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_c42765f2-13a2-4de9-ae72-f05d9c524790/1763965726496.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_c42765f2-13a2-4de9-ae72-f05d9c524790/1763965761847.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_c42765f2-13a2-4de9-ae72-f05d9c524790/1763965790087.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_c42765f2-13a2-4de9-ae72-f05d9c524790/1763965821106.jpg
uuid:ccdb4028-1203-4605-9dae-42441dc99863 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_ccdb4028-1203-4605-9dae-42441dc99863/1763383369368.jpg | 2025-11-17 | 48.41 | 8.3914 | GLA-BH-1 | Stalled | The drilling operation halted on Nov 10, 2025 at 10:00PM due to shortage of drilling rods.the contractor trying to get it from ethiopia. | 42 | N/A | collect:oJw9QIFTUBAakeRh | 2025-11-17 12:47:45 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_ccdb4028-1203-4605-9dae-42441dc99863/1763383388985.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_ccdb4028-1203-4605-9dae-42441dc99863/1763383407097.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_ccdb4028-1203-4605-9dae-42441dc99863/1763383429131.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_ccdb4028-1203-4605-9dae-42441dc99863/1763383480870.jpg
uuid:562432f2-3f8c-424a-a4af-f9344026b666 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_562432f2-3f8c-424a-a4af-f9344026b666/1762758291175.jpg | 2025-11-10 | 48.4099 | 8.3915 | GLA-BH-01 | In Progress | Good Progress, However Slow drilling rate due to very hard nature of the geological formation. | 42 | N/A | collect:oJw9QIFTUBAakeRh | 2025-11-10 07:08:52 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_562432f2-3f8c-424a-a4af-f9344026b666/1762758317233.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_562432f2-3f8c-424a-a4af-f9344026b666/1762758347792.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_562432f2-3f8c-424a-a4af-f9344026b666/1762758412542.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_562432f2-3f8c-424a-a4af-f9344026b666/1762758432678.jpg
uuid:c795c3c6-e184-40c4-bdcf-9867e424e79d | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_c795c3c6-e184-40c4-bdcf-9867e424e79d/1762174063023.jpg | 2025-11-03 | 48.41 | 8.3914 | GLA-BH-1 | In Progress | Slow drilling rate due to the nature of very hard formation and rig mechanical problem. | 40 | N/A | collect:oJw9QIFTUBAakeRh | 2025-11-03 12:51:05 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_c795c3c6-e184-40c4-bdcf-9867e424e79d/1762174087483.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_c795c3c6-e184-40c4-bdcf-9867e424e79d/1762174122191.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_c795c3c6-e184-40c4-bdcf-9867e424e79d/1762174152392.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_c795c3c6-e184-40c4-bdcf-9867e424e79d/1762174193480.jpg
uuid:b467a767-1470-4f55-a596-19f4c2798d0c | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_b467a767-1470-4f55-a596-19f4c2798d0c/1761568803340.jpg | 2025-10-27 | 48.41 | 8.3915 | GLA-BH-1 | Stalled | The drilling operation halted at a depth of 497m due to mechanical problem of the drilling rig (Damaged of ball bearing of the rotary transmission) | 40 | N/A | collect:oJw9QIFTUBAakeRh | 2025-10-27 12:45:39 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_b467a767-1470-4f55-a596-19f4c2798d0c/1761568819217.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_b467a767-1470-4f55-a596-19f4c2798d0c/1761568918851.jpg
uuid:079029c2-a1bc-4c15-8d5a-32250ce9e426 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_079029c2-a1bc-4c15-8d5a-32250ce9e426/1760941229524.jpg | 2025-10-20 | 48.41 | 8.3914 | GLA-BH-1 | In Progress | Good Progress (Slow drilling rate) due to hard formation. | 38 | N/A | collect:oJw9QIFTUBAakeRh | 2025-10-20 06:24:30 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_079029c2-a1bc-4c15-8d5a-32250ce9e426/1760941255887.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_079029c2-a1bc-4c15-8d5a-32250ce9e426/1760941351520.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_079029c2-a1bc-4c15-8d5a-32250ce9e426/1760941372248.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_079029c2-a1bc-4c15-8d5a-32250ce9e426/1760941403714.jpg
uuid:2aac2395-de66-41bc-856e-3c5bca14a57e | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_2aac2395-de66-41bc-856e-3c5bca14a57e/1760337174848.jpg | 2025-10-13 | 48.4101 | 8.3915 | GLA-BH-01 | In Progress | Good Progress | 33 | N/A | collect:oJw9QIFTUBAakeRh | 2025-10-13 06:36:25 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_2aac2395-de66-41bc-856e-3c5bca14a57e/1760337211813.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_2aac2395-de66-41bc-856e-3c5bca14a57e/1760337241699.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_2aac2395-de66-41bc-856e-3c5bca14a57e/1760337291316.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_2aac2395-de66-41bc-856e-3c5bca14a57e/1760337348006.jpg
uuid:4ecaab8e-19f4-43fb-8c67-3f3213909fd0 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_4ecaab8e-19f4-43fb-8c67-3f3213909fd0/1759754996753.jpg | 2025-10-06 | 48.41 | 8.3914 | GLA-01-25 | In Progress | Good Progress | 25 | N/A | collect:oJw9QIFTUBAakeRh | 2025-10-06 12:52:42 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_4ecaab8e-19f4-43fb-8c67-3f3213909fd0/1759755026484.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_4ecaab8e-19f4-43fb-8c67-3f3213909fd0/1759755076217.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_4ecaab8e-19f4-43fb-8c67-3f3213909fd0/1759755092852.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_4ecaab8e-19f4-43fb-8c67-3f3213909fd0/1759755116103.jpg
uuid:88c58c7b-ff7b-4d7a-ac18-2e7e484090f1 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_88c58c7b-ff7b-4d7a-ac18-2e7e484090f1/GLA-BH-1%20Image%201-14_19_0.jpeg | 2025-08-28 | 48.41 | 8.3914 | GLA-BH-1 | In Progress | Overally good drilling progress for the deep well. | 5 | tonyouh@gmail.com | N/A | 2025-10-01 11:20:24 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_88c58c7b-ff7b-4d7a-ac18-2e7e484090f1/GLA-BH-1%20Image%202-14_19_7.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_88c58c7b-ff7b-4d7a-ac18-2e7e484090f1/GLA-BH-1%20Image%203-14_19_14.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_88c58c7b-ff7b-4d7a-ac18-2e7e484090f1/GLA-BH-1%20Image%204-14_19_21.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_88c58c7b-ff7b-4d7a-ac18-2e7e484090f1/GLA-BH-1%20Image%205-14_19_27.jpg
uuid:fb6c96c1-0d99-4285-862e-2306c2aeb491 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_fb6c96c1-0d99-4285-862e-2306c2aeb491/GBH-01%20Image%201-11_13_16.jpeg | 2025-08-08 | 48.4103 | 8.3917 | GBH-01 | N/A | The GBH-01 collapse has exposed serious gaps in equipment readiness, casing depth, and Contractor compliance. The protracted disputes from February to July 2025 caused major delays and strained relations between the Contractor, Consultant, and Client. The 15 July Action Points represent a turning point, setting enforceable obligations that address the root causes of failure: inadequate casing, weak site supervision, and lack of continuous drilling. | N/A | tonyouh@gmail.com | N/A | 2025-10-01 08:16:04 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_fb6c96c1-0d99-4285-862e-2306c2aeb491/GBH-01%20Image%202-11_13_24.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_fb6c96c1-0d99-4285-862e-2306c2aeb491/GBH-01%20Image%203-11_13_31.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_fb6c96c1-0d99-4285-862e-2306c2aeb491/GBH-01%20Image%204-11_13_39.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_fb6c96c1-0d99-4285-862e-2306c2aeb491/GBH-01%20Image%205-11_13_46.jpeg
uuid:d7f531b3-19f9-465f-9a74-13667ee110f7 | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_d7f531b3-19f9-465f-9a74-13667ee110f7/1759151427725.jpg | 2025-09-29 | 48.41 | 8.3914 | GLA-BH-1 | In Progress | Good Progress | 21 | N/A | collect:oJw9QIFTUBAakeRh | 2025-09-29 13:34:01 | N/A
uuid:6b536d3b-e007-4c4a-be52-bbe5e6daac7e | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_6b536d3b-e007-4c4a-be52-bbe5e6daac7e/1759135352450.jpg | 2025-09-29 | 48.4799 | 8.4061 | Bhgfg=4 | In Progress | Good progress | 25 | N/A | collect:y0t2mU4wj7zHSQgt | 2025-09-29 08:47:55 | N/A
uuid:5f88453f-bf08-4463-b32d-10ae6ea1cc0d | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_5f88453f-bf08-4463-b32d-10ae6ea1cc0d/1759135356356.jpg | 2025-09-29 | 48.4798 | 8.4061 | KBH-001 | In Progress | Good Progress | 25 | N/A | collect:oJw9QIFTUBAakeRh | 2025-09-29 08:47:55 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_5f88453f-bf08-4463-b32d-10ae6ea1cc0d/1759135488962.jpg
uuid:24370087-5909-43f4-9e01-c29b3b0d3d7f | Somalia | Garowe | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_24370087-5909-43f4-9e01-c29b3b0d3d7f/1759135354218.jpg | 2025-09-29 | 37.0161 | -1.1073 | KBH001 | In Progress | Good progress | 23 | N/A | collect:aqr83sJveMKW2rNe | 2025-09-29 08:47:52 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_24370087-5909-43f4-9e01-c29b3b0d3d7f/1759135539296.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_24370087-5909-43f4-9e01-c29b3b0d3d7f/1759135546172.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_24370087-5909-43f4-9e01-c29b3b0d3d7f/1759135550609.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/21/RWASH_Activity_20250730/uuid_24370087-5909-43f4-9e01-c29b3b0d3d7f/1759135490238.jpg