## RWASH_Activity_20240924
Instance ID | Country Name | Site Name | Image Description | Image Path | Image Date | Longitude | Latitude | Activity Status | Comments | Project Description | Completion Percentage | Username | Device ID | Created At | Status
uuid:5b176c73-be94-4b93-909b-29a5ec2d9a33 | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A5b176c73-be94-4b93-909b-29a5ec2d9a33/attachment/1745141946790.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-04-20 | 42.0544 | 4.1456 | PSW 1 | In Progress | Drilling works has been completed, constant pump testing ongoing | 80 | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-05-19 09:34:39 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A5b176c73-be94-4b93-909b-29a5ec2d9a33/attachment/1745141966198.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:c85802fe-fb08-48e5-889a-66fdf5070b9b | Somalia | Dollow | Environmental Social Safeguards (ESS) | https://odk-middleman.onrender.com/api/submission/uuid%3Ac85802fe-fb08-48e5-889a-66fdf5070b9b/attachment/1744961050905.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-04-18 | N/A | N/A | N/A | Completed | PSW 5 site restoration as part of ESMP | N/A | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-05-19 09:31:12 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3Ac85802fe-fb08-48e5-889a-66fdf5070b9b/attachment/1744961064876.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:4ed6df8a-7733-41f1-9865-be3f3b6219f3 | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A4ed6df8a-7733-41f1-9865-be3f3b6219f3/attachment/1747639600447.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-05-19 | 42.0934 | 4.1674 | Psw6 | In Progress | Drilling in progress | 40 | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-05-19 09:25:54 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A4ed6df8a-7733-41f1-9865-be3f3b6219f3/attachment/1747639612246.jpg?project_id=8&form_id=RWASH_Activity_20240924
https://odk-middleman.onrender.com/api/submission/uuid%3A4ed6df8a-7733-41f1-9865-be3f3b6219f3/attachment/1747639629581.jpg?project_id=8&form_id=RWASH_Activity_20240924
https://odk-middleman.onrender.com/api/submission/uuid%3A4ed6df8a-7733-41f1-9865-be3f3b6219f3/attachment/1747639743028.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:769b0a2a-7aee-4acd-8bb0-3fe5037112fd | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A769b0a2a-7aee-4acd-8bb0-3fe5037112fd/attachment/1746952451754.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-05-11 | 42.0541 | 4.1446 | Psw 2 | Completed | Water source Development completed | N/A | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-05-19 09:23:53 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A769b0a2a-7aee-4acd-8bb0-3fe5037112fd/attachment/1746952469365.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:91959931-7fb6-4fad-a212-7bd8f994fb9d | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A91959931-7fb6-4fad-a212-7bd8f994fb9d/attachment/1746952282706.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-05-11 | 42.0548 | 4.1455 | Psw 1 | Completed | Source development work completed | N/A | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-05-19 09:22:04 | N/A
uuid:b7c1d35b-8f80-4a67-a856-daa991432866 | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3Ab7c1d35b-8f80-4a67-a856-daa991432866/attachment/1746951481930.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-05-11 | 42.0557 | 4.1461 | PSW 4 | In Progress | Drilling completed, casing installation completed, pumping testing and site restoration pending | 70 | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-05-19 09:20:59 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3Ab7c1d35b-8f80-4a67-a856-daa991432866/attachment/1746951498316.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:3730ddc0-7079-420e-befd-1c4cbfc9385a | Somalia | Dollow | Capacity Building | https://odk-middleman.onrender.com/api/submission/uuid%3A3730ddc0-7079-420e-befd-1c4cbfc9385a/attachment/1745397081615.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-04-23 | N/A | N/A | N/A | In Progress | N/A | N/A | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-05-19 09:18:26 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A3730ddc0-7079-420e-befd-1c4cbfc9385a/attachment/1745397116704.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:b2e00f4d-ed7e-485e-915b-731b8cbb774f | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3Ab2e00f4d-ed7e-485e-915b-731b8cbb774f/attachment/1745307314999.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-04-22 | 42.0541 | 4.1445 | Psw2 | In Progress | The contractor is working in a good commitment. | 50 | N/A | collect:DFY3FpBdcASaKbVr | 2025-04-22 07:36:48 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3Ab2e00f4d-ed7e-485e-915b-731b8cbb774f/attachment/1745307322795.jpg?project_id=8&form_id=RWASH_Activity_20240924
https://odk-middleman.onrender.com/api/submission/uuid%3Ab2e00f4d-ed7e-485e-915b-731b8cbb774f/attachment/1745307331084.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:1864bc8b-726f-4415-a1c9-76a55d7c3d8b | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A1864bc8b-726f-4415-a1c9-76a55d7c3d8b/attachment/1745306095076.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-04-22 | 42.0544 | 4.1455 | Psw1 | In Progress | Q=30l/s | 90 | N/A | collect:DFY3FpBdcASaKbVr | 2025-04-22 07:15:50 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A1864bc8b-726f-4415-a1c9-76a55d7c3d8b/attachment/1745306106664.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:61a778f9-dace-4eb4-b247-29125d524384 | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A61a778f9-dace-4eb4-b247-29125d524384/attachment/1744960936146.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-04-18 | 42.0589 | 4.1459 | PSW 5 | Completed | 100 | N/A | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-04-18 07:25:59 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A61a778f9-dace-4eb4-b247-29125d524384/attachment/1744960956591.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:5479384d-6d58-42e0-b80e-168a1549dfcf | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A5479384d-6d58-42e0-b80e-168a1549dfcf/attachment/1742630400724.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-03-22 | 42.0744 | 4.1683 | PSW 8 | Completed | The development work completed | N/A | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-04-18 00:11:29 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A5479384d-6d58-42e0-b80e-168a1549dfcf/attachment/1742630422095.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:18941237-f61d-4409-84e1-c2db91fc75fa | Somalia | Dollow | Capacity Building | N/A | 2025-04-17 | N/A | N/A | N/A | Completed | N/A | N/A | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-04-17 15:11:36 | N/A
uuid:cfafb5fb-347c-4718-bf4f-5ee886a17cad | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3Acfafb5fb-347c-4718-bf4f-5ee886a17cad/attachment/1742196059147.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-03-17 | 42.0774 | 4.1647 | PSW8 | In Progress | Constant pump testing with 27l/s for the second day | 85 | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-03-17 07:22:26 | N/A
uuid:3cd3f599-0086-491d-a601-d23686d8cc32 | Somalia | Dollow | Environmental Social Safeguards (ESS) | https://odk-middleman.onrender.com/api/submission/uuid%3A3cd3f599-0086-491d-a601-d23686d8cc32/attachment/1741247648665.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-03-06 | N/A | N/A | Psw 8 | In Progress | The staff working on drilling have PEPs as required | N/A | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-03-16 14:48:05 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A3cd3f599-0086-491d-a601-d23686d8cc32/attachment/1741247658874.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:494cddd3-f0a7-42a3-b38f-6c7e0a01680b | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A494cddd3-f0a7-42a3-b38f-6c7e0a01680b/attachment/1740754548532.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-02-28 | 42.0762 | 4.1643 | PSW 8 | In Progress | Mobilization of the rig completed, construction of mud pit completed | 10 | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-03-16 14:47:52 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A494cddd3-f0a7-42a3-b38f-6c7e0a01680b/attachment/1740754564244.jpg?project_id=8&form_id=RWASH_Activity_20240924
https://odk-middleman.onrender.com/api/submission/uuid%3A494cddd3-f0a7-42a3-b38f-6c7e0a01680b/attachment/1740754579526.jpg?project_id=8&form_id=RWASH_Activity_20240924
https://odk-middleman.onrender.com/api/submission/uuid%3A494cddd3-f0a7-42a3-b38f-6c7e0a01680b/attachment/1740754595951.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:cbe3f1b5-dc3b-49e4-b819-1cd952c47515 | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3Acbe3f1b5-dc3b-49e4-b819-1cd952c47515/attachment/1741420701737.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-03-08 | 42.0743 | 4.1681 | psw 8 | In Progress | Well development is going good | 70 | N/A | collect:DFY3FpBdcASaKbVr | 2025-03-08 08:01:25 | N/A
uuid:4093bcd7-3867-420d-b4a4-f579601963fb | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A4093bcd7-3867-420d-b4a4-f579601963fb/attachment/1740988792088.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-03-03 | 42.0743 | 4.1683 | Psw 8 | In Progress | Drilling work completed and the remaining work will continue | 60 | N/A | collect:DFY3FpBdcASaKbVr | 2025-03-03 08:01:37 | N/A
uuid:db61802e-0b09-4740-a284-ad15cadfac9f | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3Adb61802e-0b09-4740-a284-ad15cadfac9f/attachment/1740754345500.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-02-26 | 42.0762 | 4.1643 | RMAR launching workshop | Completed | RMAR project launching in Dollow | N/A | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-02-28 14:58:30 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3Adb61802e-0b09-4740-a284-ad15cadfac9f/attachment/1740754358142.jpg?project_id=8&form_id=RWASH_Activity_20240924
https://odk-middleman.onrender.com/api/submission/uuid%3Adb61802e-0b09-4740-a284-ad15cadfac9f/attachment/1740754379223.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:34851a2e-86e7-4448-bc8d-2b6a78418348 | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A34851a2e-86e7-4448-bc8d-2b6a78418348/attachment/1740121547401.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-02-21 | 42.0763 | 4.1639 | PSW-9* | In Progress | Drilling works of PSW-9* drilling completed, well designed completed, casing installation completed and gravel packing is in progress and the remaining works are well development,pump testing and site restoration | 65 | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-02-23 09:12:00 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A34851a2e-86e7-4448-bc8d-2b6a78418348/attachment/1740121557330.jpg?project_id=8&form_id=RWASH_Activity_20240924
https://odk-middleman.onrender.com/api/submission/uuid%3A34851a2e-86e7-4448-bc8d-2b6a78418348/attachment/1740121572838.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:77f20002-636a-4181-98b7-08ab935d933e | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A77f20002-636a-4181-98b7-08ab935d933e/attachment/1740301790999.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-02-23 | 42.0739 | 4.1667 | PSW 10* | Completed | 100%completed | N/A | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-02-23 09:11:32 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A77f20002-636a-4181-98b7-08ab935d933e/attachment/1740301804641.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:23cdb4c4-676d-46a2-87fc-7194f3302b51 | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A23cdb4c4-676d-46a2-87fc-7194f3302b51/attachment/1740120990750.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-02-21 | 42.074 | 4.1667 | PSW 10* | Completed | PSW 10*Drilling works completed at final stage of site restoration and is 99% completed | N/A | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-02-23 09:10:54 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A23cdb4c4-676d-46a2-87fc-7194f3302b51/attachment/1740121002584.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:f9415705-f8df-49e3-951d-339bba444c44 | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3Af9415705-f8df-49e3-951d-339bba444c44/attachment/1740295306235.heic?project_id=8&form_id=RWASH_Activity_20240924 | 2025-02-23 | 42.0741 | 4.1677 | Psw9 | In Progress | Well development work is ongoing | 75 | N/A | collect:DFY3FpBdcASaKbVr | 2025-02-23 07:23:16 | N/A
uuid:f9497746-3463-4237-948b-21ee035a7ffa | Somalia | Dollow | Environmental Social Safeguards (ESS) | https://odk-middleman.onrender.com/api/submission/uuid%3Af9497746-3463-4237-948b-21ee035a7ffa/attachment/1739200517736.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-02-10 | N/A | N/A | N/A | In Progress | It good mitigation measures has been put in place | N/A | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-02-11 13:04:27 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3Af9497746-3463-4237-948b-21ee035a7ffa/attachment/1739200547928.jpg?project_id=8&form_id=RWASH_Activity_20240924
https://odk-middleman.onrender.com/api/submission/uuid%3Af9497746-3463-4237-948b-21ee035a7ffa/attachment/1739200620662.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:366c2b31-6744-4cc9-9b96-1a11bf293b39 | Somalia | Dollow | Capacity Building | N/A | 2025-02-04 | N/A | N/A | N/A | In Progress | N/A | N/A | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-02-11 13:04:06 | N/A
uuid:1a61ac5e-e9ea-4b2b-bf05-6e13c05c58da | Somalia | Dollow | Environmental Social Safeguards (ESS) | https://odk-middleman.onrender.com/api/submission/uuid%3A1a61ac5e-e9ea-4b2b-bf05-6e13c05c58da/attachment/1737185580920.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-01-18 | N/A | N/A | Use of PEPs by the drilling team | In Progress | All is in order in terms of staff safety mitigation measures and safeguarding the site | N/A | N/A | collect:SXzFwQKzt8z5QZH8 | 2025-01-18 08:57:09 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A1a61ac5e-e9ea-4b2b-bf05-6e13c05c58da/attachment/1737185595038.jpg?project_id=8&form_id=RWASH_Activity_20240924
https://odk-middleman.onrender.com/api/submission/uuid%3A1a61ac5e-e9ea-4b2b-bf05-6e13c05c58da/attachment/1737185625959.jpg?project_id=8&form_id=RWASH_Activity_20240924
https://odk-middleman.onrender.com/api/submission/uuid%3A1a61ac5e-e9ea-4b2b-bf05-6e13c05c58da/attachment/1737185635393.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:f2be2ff0-2411-4929-bfc0-a92e5aa9ec68 | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3Af2be2ff0-2411-4929-bfc0-a92e5aa9ec68/attachment/1737008549657.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2025-01-16 | 42.0739 | 4.1666 | Psw10 | Not Started | Mud pit excavation and rig up done | N/A | N/A | collect:DFY3FpBdcASaKbVr | 2025-01-16 06:23:50 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3Af2be2ff0-2411-4929-bfc0-a92e5aa9ec68/attachment/1737008560437.jpg?project_id=8&form_id=RWASH_Activity_20240924
https://odk-middleman.onrender.com/api/submission/uuid%3Af2be2ff0-2411-4929-bfc0-a92e5aa9ec68/attachment/1737008569981.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:1182197b-cc70-4ece-bfc4-66d486fa19b8 | Somalia | Dollow | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A1182197b-cc70-4ece-bfc4-66d486fa19b8/attachment/1727417210908.jpg?project_id=8&form_id=RWASH_Activity_20240924 | 2024-09-27 | 42.0872 | 4.1654 | Dollow Deep well one(DDW-1) | In Progress | Good progress with some challenges | 26 | N/A | collect:DFY3FpBdcASaKbVr | 2024-09-27 06:11:21 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A1182197b-cc70-4ece-bfc4-66d486fa19b8/attachment/1727417229066.jpg?project_id=8&form_id=RWASH_Activity_20240924
uuid:5998cebc-50c4-4c2f-814c-ea4924d41de1 | Somalia | Dollow | Capacity Building | N/A | 2024-09-24 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-09-24 12:20:20 | N/A