## Act_Mon_SDN_v2
Instance ID | Country Name | Site Name | Image Description | Image Path | Image Date | Longitude | Latitude | Activity Status | Comments | Project Description | Completion Percentage | Username | Device ID | Created At | Status
uuid:f14c4472-45e3-46ee-badf-c78242e1229b | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f14c4472-45e3-46ee-badf-c78242e1229b/1781074276737.jpg | 2026-06-09 | 35.9017 | 14.985 | PT-34 | In Progress | Current activity: pipe welding Status: Excavation, bedding, welding completed | 45 | N/A | collect:c9hqC63bGpKD0X2x | 2026-06-11 07:26:49 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f14c4472-45e3-46ee-badf-c78242e1229b/1781074281478.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f14c4472-45e3-46ee-badf-c78242e1229b/1781162664044.jpg
uuid:25c48031-8fad-4a30-927f-05685758af3d | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_25c48031-8fad-4a30-927f-05685758af3d/1781073495483.jpg | 2026-06-10 | 35.9024 | 14.9817 | PC-41 | In Progress | Current activity: Final backfilling Status: ongoing | 70 | N/A | collect:c9hqC63bGpKD0X2x | 2026-06-11 07:26:39 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_25c48031-8fad-4a30-927f-05685758af3d/1781073502167.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_25c48031-8fad-4a30-927f-05685758af3d/1781073515584.jpg
uuid:25e0265f-8d03-40ef-99bb-746bc7fb87a6 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_25e0265f-8d03-40ef-99bb-746bc7fb87a6/1781074967818.jpg | 2026-06-10 | N/A | N/A | Elevated Tank Refugee Camp | In Progress | Current activity: Compaction of layer 3 Status: completed | 5 | N/A | collect:c9hqC63bGpKD0X2x | 2026-06-11 07:26:27 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_25e0265f-8d03-40ef-99bb-746bc7fb87a6/1781162264755.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_25e0265f-8d03-40ef-99bb-746bc7fb87a6/1781162274336.jpg
uuid:2d8389ae-ad18-449e-9545-eb111f52b71d | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_2d8389ae-ad18-449e-9545-eb111f52b71d/1780985315320.jpg | 2026-06-09 | 35.9046 | 14.9574 | PT-24 | In Progress | Current activity: Initial backfilling Status: initial backfilling layer two is ongoing | 26 | N/A | collect:c9hqC63bGpKD0X2x | 2026-06-09 06:43:24 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_2d8389ae-ad18-449e-9545-eb111f52b71d/1780987313600.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_2d8389ae-ad18-449e-9545-eb111f52b71d/1780987323803.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_2d8389ae-ad18-449e-9545-eb111f52b71d/1780987335179.jpg
uuid:624967dc-ee6d-490b-a474-87f2cc7ff215 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_624967dc-ee6d-490b-a474-87f2cc7ff215/1780474488007.jpg | 2026-06-03 | 35.902 | 14.9804 | PC-41 | In Progress | Current activity: Excavation and pipes welding Status: Excavation completed along the profile | 20 | N/A | collect:c9hqC63bGpKD0X2x | 2026-06-04 08:03:37 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_624967dc-ee6d-490b-a474-87f2cc7ff215/1780560043839.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_624967dc-ee6d-490b-a474-87f2cc7ff215/1780560059226.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_624967dc-ee6d-490b-a474-87f2cc7ff215/1780560080060.jpg
uuid:00efddbb-7d08-4ec8-8035-2c53926c2e89 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_00efddbb-7d08-4ec8-8035-2c53926c2e89/1780313630911.jpg | 2026-05-31 | 35.9048 | 14.9579 | PT-24 | In Progress | Current activity: Excavation Status: Bedding phase to the excavated section | 6 | N/A | collect:c9hqC63bGpKD0X2x | 2026-06-04 07:59:00 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_00efddbb-7d08-4ec8-8035-2c53926c2e89/1780559655191.jpg
uuid:87b07c10-0232-4c7c-9998-40ba80b39f4a | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_87b07c10-0232-4c7c-9998-40ba80b39f4a/1780314528574.jpg | 2026-05-31 | 35.9028 | 14.9484 | PT-23 | Completed | Current activity: Final backfilling Status: completed | N/A | N/A | collect:c9hqC63bGpKD0X2x | 2026-06-04 07:58:47 | N/A
uuid:6664e434-62da-4e04-b4bb-5f7084b0242a | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_6664e434-62da-4e04-b4bb-5f7084b0242a/1780313536977.jpg | 2026-06-01 | 35.9051 | 14.9587 | PT-25 | In Progress | Current activity: Excavation Status: Excavation is ongoing | 4 | N/A | collect:c9hqC63bGpKD0X2x | 2026-06-04 07:51:17 | N/A
uuid:17da4e17-0306-45db-aec2-19f282f05ffc | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_17da4e17-0306-45db-aec2-19f282f05ffc/1780383997301.jpg | 2026-06-02 | 35.9018 | 14.9796 | PC-41 | In Progress | Current activity: Excavation Status: Excavation is ongoing along the profile | 7 | N/A | collect:c9hqC63bGpKD0X2x | 2026-06-03 05:54:14 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_17da4e17-0306-45db-aec2-19f282f05ffc/1780465709824.jpg
uuid:0f276111-569d-4420-997f-f8c31c234217 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_0f276111-569d-4420-997f-f8c31c234217/1779347969055.jpg | 2026-05-24 | N/A | N/A | Refugee Camp Water Tank | In Progress | Current activity: Excavation completed. Subgrade preparation, leveling, and compaction works ongoing at elevated tank foundation area. | 25 | N/A | collect:c9hqC63bGpKD0X2x | 2026-05-28 20:43:22 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_0f276111-569d-4420-997f-f8c31c234217/1779656549351.jpg
https://odk-middleman.onrender.com/api/submission/uuid%3A0f276111-569d-4420-997f-f8c31c234217/attachment/1779656558337.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:e1e70f17-ba4c-425c-874a-6657c5ddf9e4 | Sudan | Girba | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3Ae1e70f17-ba4c-425c-874a-6657c5ddf9e4/attachment/1779346832260.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2026-05-21 | 35.9082 | 14.9791 | PC-24 | In Progress | Current activity: Initial backfilling Status: Pipes are ready for final backfilling | 85 | N/A | collect:c9hqC63bGpKD0X2x | 2026-05-28 20:43:19 | N/A
uuid:94b334db-0509-4a80-b8fd-ab5bc1b15fc9 | Sudan | Wad Sharifey | Other – please specify | N/A | 2026-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:6OVgPYU7dZbRgkTn | 2026-05-26 06:44:03 | N/A
uuid:1e643a9d-71b0-407c-9ded-dbddb4f13bf3 | Sudan | Girba | Other – please specify | N/A | 2026-05-26 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:d92qY1lGZ09n3ZhL | 2026-05-26 06:40:23 | N/A
uuid:9115f6fb-83c6-467d-b42f-722d42c9c7c6 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_9115f6fb-83c6-467d-b42f-722d42c9c7c6/1779271305190.jpg | 2026-05-20 | N/A | N/A | Elevated warer tank excavation works | In Progress | Exacavation stage of elevated water tank in Refugee camp | 2 | N/A | collect:FCb5eWMM6uQSJ04H | 2026-05-20 10:03:36 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_9115f6fb-83c6-467d-b42f-722d42c9c7c6/1779271323287.jpg
uuid:6d9f55f0-8449-46cd-9341-cad053909abb | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_6d9f55f0-8449-46cd-9341-cad053909abb/1778416888966.jpg | 2026-05-10 | 35.8957 | 14.9557 | PT-18 | In Progress | Current activity: Excavation Status: Excavation nearly completed | 14 | N/A | collect:c9hqC63bGpKD0X2x | 2026-05-11 09:00:16 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_6d9f55f0-8449-46cd-9341-cad053909abb/1778416898839.jpg
uuid:b685211a-1f0c-4f4f-8d79-c3c24d3c3f6e | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b685211a-1f0c-4f4f-8d79-c3c24d3c3f6e/1778480001024.jpg | 2026-05-11 | 35.8908 | 14.9505 | PT-16 | In Progress | Current activity: Initial backfilling Status: Initial backfilling is ongoing | 79 | N/A | collect:c9hqC63bGpKD0X2x | 2026-05-11 08:56:35 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b685211a-1f0c-4f4f-8d79-c3c24d3c3f6e/1778489351320.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b685211a-1f0c-4f4f-8d79-c3c24d3c3f6e/1778489418363.jpg
uuid:92b54af5-7a76-4932-968c-90735aebdd40 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_92b54af5-7a76-4932-968c-90735aebdd40/1778483681138.jpg | 2026-05-11 | 35.9033 | 14.9527 | PT-23 | In Progress | Current activity: Compaction(Moisture conditioning) Status: Compaction of the bedding layer is ongoing | 55 | N/A | collect:c9hqC63bGpKD0X2x | 2026-05-11 08:56:26 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_92b54af5-7a76-4932-968c-90735aebdd40/1778483743908.jpg
uuid:86c3a3e9-a474-4cee-a99c-ef051a6d7d80 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_86c3a3e9-a474-4cee-a99c-ef051a6d7d80/1778242491943.jpg | 2026-05-07 | 35.8921 | 14.9556 | PT-17 | In Progress | Current activity: Excavation Status: Completed, welding commenced in parallel reached 200m | 25 | N/A | collect:c9hqC63bGpKD0X2x | 2026-05-11 06:48:48 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A86c3a3e9-a474-4cee-a99c-ef051a6d7d80/attachment/1778242503718.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:07a002c5-6598-4018-81b3-158daaf44ca0 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_07a002c5-6598-4018-81b3-158daaf44ca0/1778137391911.jpg | 2026-04-28 | 35.8915 | 14.9501 | PT-16 | In Progress | Current activity: Bedding Status: Bedding layer have been completed Remarks: Next stage -pipe laying- will commence shortly | 60 | N/A | collect:c9hqC63bGpKD0X2x | 2026-05-07 07:08:52 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_07a002c5-6598-4018-81b3-158daaf44ca0/1778137458017.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_07a002c5-6598-4018-81b3-158daaf44ca0/1778137507327.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_07a002c5-6598-4018-81b3-158daaf44ca0/1777373525824.jpg
uuid:743de1e5-7f53-4e1c-95b8-4587d60d3d07 | Sudan | Girba | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A743de1e5-7f53-4e1c-95b8-4587d60d3d07/attachment/1777788525493.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2026-05-03 | 35.8915 | 14.9501 | PT-15 | In Progress | Current activity: initial backfill Status: completed Remarks: Final backfilling will commence shortly | 85 | N/A | collect:c9hqC63bGpKD0X2x | 2026-05-07 07:02:25 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A743de1e5-7f53-4e1c-95b8-4587d60d3d07/attachment/1778137112562.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3A743de1e5-7f53-4e1c-95b8-4587d60d3d07/attachment/1778137149864.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3A743de1e5-7f53-4e1c-95b8-4587d60d3d07/attachment/1778137181997.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:98bbed30-06a8-4644-914e-14eeb7355743 | Sudan | Girba | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A98bbed30-06a8-4644-914e-14eeb7355743/attachment/1778136264635.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2026-05-04 | 35.9022 | 14.9443 | PT-22 | In Progress | Current activity: Initial Backfilling Status: Backfilling works have been completed Remark: Almost the final stage (final backfilling) | 85 | N/A | collect:c9hqC63bGpKD0X2x | 2026-05-07 06:55:23 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A98bbed30-06a8-4644-914e-14eeb7355743/attachment/1778136386353.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3A98bbed30-06a8-4644-914e-14eeb7355743/attachment/1778136498134.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_98bbed30-06a8-4644-914e-14eeb7355743/1778136880132.jpg
uuid:2ae75293-66ee-48ff-a46e-17262af1e03e | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_2ae75293-66ee-48ff-a46e-17262af1e03e/1777360035116.jpg | 2026-04-28 | 35.902 | 14.9433 | PT-22 | In Progress | • Current Activity: pipe installation • Status: Pipe installation has been completed along the trench • Remarks: initial backfilling will take place shortly | 75 | N/A | collect:c9hqC63bGpKD0X2x | 2026-04-28 10:59:28 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_2ae75293-66ee-48ff-a46e-17262af1e03e/1777373653246.jpg
https://odk-middleman.onrender.com/api/submission/uuid%3A2ae75293-66ee-48ff-a46e-17262af1e03e/attachment/1777373696924.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3A2ae75293-66ee-48ff-a46e-17262af1e03e/attachment/1777373705495.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:13faf361-9160-44fd-a942-8deab87a2437 | Sudan | Girba | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A13faf361-9160-44fd-a942-8deab87a2437/attachment/1777187398712.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2026-04-26 | 35.9019 | 14.9431 | PT-22 | In Progress | • Current activity: Welding • Status: Welding Works have been completed along the profile (737m) | 45 | N/A | collect:c9hqC63bGpKD0X2x | 2026-04-28 10:50:59 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A13faf361-9160-44fd-a942-8deab87a2437/attachment/1777187407254.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3A13faf361-9160-44fd-a942-8deab87a2437/attachment/1777187421022.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3A13faf361-9160-44fd-a942-8deab87a2437/attachment/1777205502270.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:e6168cda-f7a5-4207-86ff-7a4619191ab6 | Sudan | Girba | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3Ae6168cda-f7a5-4207-86ff-7a4619191ab6/attachment/1777204376011.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2026-04-25 | 35.8922 | 14.9493 | PT-15 | In Progress | • Current activity: Excavation • Status: Excavation has been completed along the profile (320m) | 20 | N/A | collect:c9hqC63bGpKD0X2x | 2026-04-26 12:10:44 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3Ae6168cda-f7a5-4207-86ff-7a4619191ab6/attachment/1777204389714.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3Ae6168cda-f7a5-4207-86ff-7a4619191ab6/attachment/1777204399504.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3Ae6168cda-f7a5-4207-86ff-7a4619191ab6/attachment/1777204435503.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:c9dccc1e-ef47-44f7-b597-c14ead43e976 | Sudan | Girba | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3Ac9dccc1e-ef47-44f7-b597-c14ead43e976/attachment/1776937541746.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2026-04-22 | 35.8929 | 14.9464 | PT-27 | In Progress | • Current activity: Bedding, compaction, welding, and pipe laying are all done to Chainage 0+320 • Status: Next stage will be final backfilling | 23 | N/A | collect:c9hqC63bGpKD0X2x | 2026-04-23 09:51:11 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3Ac9dccc1e-ef47-44f7-b597-c14ead43e976/attachment/1776937550588.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3Ac9dccc1e-ef47-44f7-b597-c14ead43e976/attachment/1776937595325.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3Ac9dccc1e-ef47-44f7-b597-c14ead43e976/attachment/1776937659229.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:f5989edf-d4ec-4728-8764-5ecea204ebcd | Sudan | Girba | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3Af5989edf-d4ec-4728-8764-5ecea204ebcd/attachment/1776936527645.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2026-04-23 | 35.902 | 14.944 | PT-22 | In Progress | • Current Activity: Welding • Status: Joining and welding work are ongoing • Remark: Section Chainage 0+200 to 0+240 needs repair for bedding due to soil collapse because of the soil nature. | 49 | N/A | collect:c9hqC63bGpKD0X2x | 2026-04-23 09:37:23 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3Af5989edf-d4ec-4728-8764-5ecea204ebcd/attachment/1776936538948.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3Af5989edf-d4ec-4728-8764-5ecea204ebcd/attachment/1776936589700.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3Af5989edf-d4ec-4728-8764-5ecea204ebcd/attachment/1776936689596.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3Af5989edf-d4ec-4728-8764-5ecea204ebcd/attachment/1776936704101.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:9fec70a1-e740-4a94-a358-c1b771d52cd6 | Sudan | Girba | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A9fec70a1-e740-4a94-a358-c1b771d52cd6/attachment/1776922853609.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2026-04-22 | 35.8922 | 14.9476 | PT-15 | In Progress | • Current activity: Excavation • Status: Excavation is ongoing along the profile, reached Chainage 0+140 • Remarks: subsequent works have not started yet. | 9 | N/A | collect:c9hqC63bGpKD0X2x | 2026-04-23 09:23:38 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A9fec70a1-e740-4a94-a358-c1b771d52cd6/attachment/1776922864308.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3A9fec70a1-e740-4a94-a358-c1b771d52cd6/attachment/1776922872228.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3A9fec70a1-e740-4a94-a358-c1b771d52cd6/attachment/1776935807211.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:a571e459-50f5-4b2d-858c-54a6601c32cd | Sudan | Girba | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3Aa571e459-50f5-4b2d-858c-54a6601c32cd/attachment/1776581380103.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2026-04-18 | 35.9018 | 14.9426 | PT-22 | In Progress | Current activity: Compaction Status: Compaction of the bedding layer is ongoing. Remarks: This progress reflects bedding preparation works prior to pipe installation. | 38 | N/A | collect:c9hqC63bGpKD0X2x | 2026-04-19 09:48:32 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3Aa571e459-50f5-4b2d-858c-54a6601c32cd/attachment/1776591601305.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3Aa571e459-50f5-4b2d-858c-54a6601c32cd/attachment/1776591644665.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:48f6f565-a410-44ce-9e58-94d6b42c9c67 | Sudan | Girba | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A48f6f565-a410-44ce-9e58-94d6b42c9c67/attachment/1776583135815.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2026-04-19 | 35.893 | 14.9464 | PT-27 | In Progress | Current activity: Welding Status: Jointing and welding works ongoing. Remarks: Installed pipe sections are being prepared for further laying works. | 14 | N/A | collect:c9hqC63bGpKD0X2x | 2026-04-19 09:39:06 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A48f6f565-a410-44ce-9e58-94d6b42c9c67/attachment/1776583155513.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3A48f6f565-a410-44ce-9e58-94d6b42c9c67/attachment/1776583165505.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:88259f4f-4d87-4eb3-b88b-eb3b47141f62 | Sudan | Girba | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3A88259f4f-4d87-4eb3-b88b-eb3b47141f62/attachment/1775119883773.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2026-04-01 | 35.9027 | 14.9477 | PT-23 | In Progress | Excavation works commenced at Profile PT-23. Current progress reached approximately Chainage 0+180. No pipe installation or bedding works started yet. |  | N/A | collect:pRiwvOl04AF4nIwN | 2026-04-02 08:56:22 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A88259f4f-4d87-4eb3-b88b-eb3b47141f62/attachment/1775119912536.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3A88259f4f-4d87-4eb3-b88b-eb3b47141f62/attachment/1775119921368.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3A88259f4f-4d87-4eb3-b88b-eb3b47141f62/attachment/1775119930254.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:c2157456-9a74-47c9-8182-4cf310762d01 | Sudan | Girba | Construction of Water Supply Schemes | https://odk-middleman.onrender.com/api/submission/uuid%3Ac2157456-9a74-47c9-8182-4cf310762d01/attachment/1773585547622.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2026-03-15 | 35.9026 | 14.9472 | PT-22 | In Progress | Excavation works at Profile PT-22 have been completed. Final progress reached approximately Chainage 0+737. Pipe installation and bedding works have not started yet. |  | N/A | collect:pRiwvOl04AF4nIwN | 2026-03-15 14:43:13 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_c2157456-9a74-47c9-8182-4cf310762d01/1773585701397.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_c2157456-9a74-47c9-8182-4cf310762d01/1773585719538.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_c2157456-9a74-47c9-8182-4cf310762d01/1773585736726.jpg
uuid:67092afc-dfd4-465a-ae6d-e0d0e987abc7 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_67092afc-dfd4-465a-ae6d-e0d0e987abc7/1770647629326.jpg | 2026-03-11 | 35.9054 | 14.9631 | 6-inch line pvc at Al-Shati neighborhood | Not Started | A 6-inch line was discovered inside the Al-Shati neighborhood. | N/A | N/A | collect:MR4mgpYqgHCWHAO3 | 2026-03-12 13:33:18 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_67092afc-dfd4-465a-ae6d-e0d0e987abc7/1770647639836.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_67092afc-dfd4-465a-ae6d-e0d0e987abc7/1770647654933.jpg
uuid:90efd094-a621-4694-b46c-7fa753729d55 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_90efd094-a621-4694-b46c-7fa753729d55/1770644432113.jpg | 2026-03-11 | 35.9084 | 14.9824 | PC_44 | Not Started | 5-inch line revealed, Xin end line. | N/A | N/A | collect:MR4mgpYqgHCWHAO3 | 2026-03-12 13:32:54 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_90efd094-a621-4694-b46c-7fa753729d55/1770644462104.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_90efd094-a621-4694-b46c-7fa753729d55/1770644478328.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_90efd094-a621-4694-b46c-7fa753729d55/1770644506956.jpg
uuid:f3d30501-efac-4fa3-8fcb-0ca28cf3f2ec | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f3d30501-efac-4fa3-8fcb-0ca28cf3f2ec/1770643283659.jpg | 2026-03-11 | 35.9004 | 14.9702 | PC-44 | Not Started | كشف خط ٤بوصه P. V. C المعسكر | N/A | N/A | collect:MR4mgpYqgHCWHAO3 | 2026-03-12 13:31:53 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f3d30501-efac-4fa3-8fcb-0ca28cf3f2ec/1770643296610.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f3d30501-efac-4fa3-8fcb-0ca28cf3f2ec/1770643314849.jpg
uuid:6c5906e0-89ca-4822-be99-826c9706bb11 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_6c5906e0-89ca-4822-be99-826c9706bb11/1770643771753.jpg | 2026-03-11 | 35.9098 | 14.9804 | PC_24 | Not Started | كشف خطه 5 بوصهp.v.c | N/A | N/A | collect:MR4mgpYqgHCWHAO3 | 2026-03-12 13:31:41 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_6c5906e0-89ca-4822-be99-826c9706bb11/1770643782294.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_6c5906e0-89ca-4822-be99-826c9706bb11/1770643791975.jpg
uuid:86d4fac4-b1e9-495f-b527-81e47788cb67 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_86d4fac4-b1e9-495f-b527-81e47788cb67/1773251539573.jpg | 2026-03-11 | 35.9021 | 14.9443 | PT-22 | In Progress | Excavation works ongoing at Profile PT-22. Current progress reached approximately Chainage 0+420. No pipe installation or bedding works started yet. |  | N/A | collect:pRiwvOl04AF4nIwN | 2026-03-12 09:09:49 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_86d4fac4-b1e9-495f-b527-81e47788cb67/1773251558894.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_86d4fac4-b1e9-495f-b527-81e47788cb67/1773306530090.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_86d4fac4-b1e9-495f-b527-81e47788cb67/1773306542409.jpg
uuid:dd40c66d-3b2c-4c33-98e5-fec88b14bd69 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_dd40c66d-3b2c-4c33-98e5-fec88b14bd69/1773224228199.jpg | 2026-03-11 | 35.9015 | 14.9407 | PT-22 | Not Started | Existed Ø160 PVC pipe | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-03-11 14:20:17 | N/A
uuid:120ab80d-b19b-45d9-9eae-4ee52f76518a | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_120ab80d-b19b-45d9-9eae-4ee52f76518a/1773216218133.jpg | 2026-03-11 | 35.898 | 14.9406 | PT-13 | Not Started | Existed 3 in PVC exposed | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-03-11 14:18:16 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_120ab80d-b19b-45d9-9eae-4ee52f76518a/1773216229169.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_120ab80d-b19b-45d9-9eae-4ee52f76518a/1773216238232.jpg
uuid:08b7ee0e-1d40-48d6-ba58-e2188580bc78 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_08b7ee0e-1d40-48d6-ba58-e2188580bc78/1773045316149.jpg | 2026-03-09 | 35.9022 | 14.9463 | PT-22 | Not Started | Existed 6 in PVC pipe exposed | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-03-09 18:09:49 | N/A
uuid:ca5c6ec5-11fb-431c-86e9-cf4697dde116 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_ca5c6ec5-11fb-431c-86e9-cf4697dde116/1773045543757.jpg | 2026-03-09 | 35.9029 | 14.9476 | PT-22 | Not Started | Existed 4 in HDPE pipe exposed | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-03-09 17:57:23 | N/A
uuid:a6be9f2e-4ad7-4a3d-8149-c2a802b713f6 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_a6be9f2e-4ad7-4a3d-8149-c2a802b713f6/1773044881361.jpg | 2026-03-09 | 35.9014 | 14.9409 | PT-22 | Not Started | Excavation and trenching works commenced. No pipe installation yet | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-03-09 17:39:38 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_a6be9f2e-4ad7-4a3d-8149-c2a802b713f6/1773077917999.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_a6be9f2e-4ad7-4a3d-8149-c2a802b713f6/1773077925258.jpg
uuid:61a4e97b-d4df-491e-bb9c-3d5cc40af2b6 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_61a4e97b-d4df-491e-bb9c-3d5cc40af2b6/1772980536783.jpg | 2026-03-08 | 35.8922 | 14.9462 | PT-14 | Not Started | Excavation and trenching works commenced on the profile | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-03-08 14:37:23 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_61a4e97b-d4df-491e-bb9c-3d5cc40af2b6/1772980548390.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_61a4e97b-d4df-491e-bb9c-3d5cc40af2b6/1772980557641.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_61a4e97b-d4df-491e-bb9c-3d5cc40af2b6/1772980567879.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_61a4e97b-d4df-491e-bb9c-3d5cc40af2b6/1772980581833.jpg
uuid:daa33fc5-88c5-4d60-a5a9-8495a1fdf964 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_daa33fc5-88c5-4d60-a5a9-8495a1fdf964/1771305134114.jpg | 2026-02-16 | 35.8924 | 14.9464 | PT-27 | Not Started | Trenching works ongoing along PT-27. Pipe installation not yet commenced. | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-17 11:49:39 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_daa33fc5-88c5-4d60-a5a9-8495a1fdf964/1771305144887.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_daa33fc5-88c5-4d60-a5a9-8495a1fdf964/1771305170659.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_daa33fc5-88c5-4d60-a5a9-8495a1fdf964/1771305189068.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_daa33fc5-88c5-4d60-a5a9-8495a1fdf964/1771305211923.jpg
uuid:877ec2a7-6a83-47d3-b892-90da6ba4b9ca | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_877ec2a7-6a83-47d3-b892-90da6ba4b9ca/1770122445023.jpg | 2026-02-03 | 35.8903 | 14.9525 | PT-17 | Not Started | Existed Ø100 PVC pipe | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-11 12:43:50 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_877ec2a7-6a83-47d3-b892-90da6ba4b9ca/1770122454440.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_877ec2a7-6a83-47d3-b892-90da6ba4b9ca/1770122462149.jpg
uuid:cd30d239-ba54-437f-a784-d40e51dd6400 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_cd30d239-ba54-437f-a784-d40e51dd6400/1770122227950.jpg | 2026-02-03 | 35.8912 | 14.9541 | PT-17 | Completed | Existed Ø100 PVC pipe | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-11 12:42:33 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_cd30d239-ba54-437f-a784-d40e51dd6400/1770122238201.jpg
uuid:ecf1eea9-f69d-41e4-b760-e88ebc266be5 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_ecf1eea9-f69d-41e4-b760-e88ebc266be5/1770121559374.jpg | 2026-02-03 | 35.8982 | 14.9609 | PT-29 | Not Started | Same existed Ø100 PVC pipe in the same track | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-11 12:38:28 | N/A
uuid:473beb4f-ebb9-44f8-a73d-75b1a12f2cdc | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_473beb4f-ebb9-44f8-a73d-75b1a12f2cdc/1770121223481.jpg | 2026-02-03 | 35.897 | 14.9608 | PT-29 | Not Started | Existed Ø100 PVC pipe | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-11 12:35:49 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_473beb4f-ebb9-44f8-a73d-75b1a12f2cdc/1770121235783.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_473beb4f-ebb9-44f8-a73d-75b1a12f2cdc/1770121250644.jpg
uuid:05328a1e-6abf-49c8-ada9-686b9d3d156d | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_05328a1e-6abf-49c8-ada9-686b9d3d156d/1770725441015.jpg | 2026-02-10 | 35.9035 | 14.9549 | PT-24 | Not Started | Existed Ø160 PVC pipe | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-11 06:12:07 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_05328a1e-6abf-49c8-ada9-686b9d3d156d/1770725452678.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_05328a1e-6abf-49c8-ada9-686b9d3d156d/1770725463327.jpg
uuid:e5f7746f-9b46-48b9-b71f-918d4a78b6a0 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_e5f7746f-9b46-48b9-b71f-918d4a78b6a0/1770724972070.jpg | 2026-02-10 | 35.9046 | 14.9587 | PT-24 | Not Started | Existed Ø160 PVC pipe | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-11 06:09:55 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_e5f7746f-9b46-48b9-b71f-918d4a78b6a0/1770724984323.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_e5f7746f-9b46-48b9-b71f-918d4a78b6a0/1770724998589.jpg
uuid:b1f657af-10d5-4cb7-ad1d-8a06f0b1dc4d | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b1f657af-10d5-4cb7-ad1d-8a06f0b1dc4d/1770644573372.jpg | 2026-02-09 | 35.9084 | 14.9824 | PC-44 | Not Started | Not detected yet | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-10 10:20:40 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b1f657af-10d5-4cb7-ad1d-8a06f0b1dc4d/1770644583831.jpg
uuid:3a078361-2f6a-4143-b554-19a2c19540cb | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_3a078361-2f6a-4143-b554-19a2c19540cb/1770644219673.jpg | 2026-02-09 | 35.9082 | 14.9816 | PC-44 | Not Started | Existed Ø50 PVC | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-10 10:18:40 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_3a078361-2f6a-4143-b554-19a2c19540cb/1770644233052.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_3a078361-2f6a-4143-b554-19a2c19540cb/1770644245646.jpg
uuid:eee17863-f901-48d7-8cbc-fb8aff9a2e13 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_eee17863-f901-48d7-8cbc-fb8aff9a2e13/1770643694784.jpg | 2026-02-09 | 35.9098 | 14.9804 | PC-19 | Not Started | Existed Ø100 PVC | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-10 10:16:35 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_eee17863-f901-48d7-8cbc-fb8aff9a2e13/1770643709978.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_eee17863-f901-48d7-8cbc-fb8aff9a2e13/1770643722143.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_eee17863-f901-48d7-8cbc-fb8aff9a2e13/1770643738588.jpg
uuid:80524bee-dccc-4944-8ed4-caef55495d47 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_80524bee-dccc-4944-8ed4-caef55495d47/1770643234133.jpg | 2026-02-09 | 35.9076 | 14.9811 | PC-44 | Not Started | Existed Ø100 PVC | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-10 10:15:00 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_80524bee-dccc-4944-8ed4-caef55495d47/1770643246520.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_80524bee-dccc-4944-8ed4-caef55495d47/1770643276248.jpg
uuid:add676f0-a65c-4eb6-a845-3b43f2dc1ba9 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_add676f0-a65c-4eb6-a845-3b43f2dc1ba9/1770642987692.jpg | 2026-02-09 | 35.9074 | 14.9805 | PC-44 | Not Started | Existed Ø50 PVC pipe | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-10 10:13:28 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_add676f0-a65c-4eb6-a845-3b43f2dc1ba9/1770642998192.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_add676f0-a65c-4eb6-a845-3b43f2dc1ba9/1770643007020.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_add676f0-a65c-4eb6-a845-3b43f2dc1ba9/1770643014655.jpg
uuid:abbd2e56-16c4-4bff-8e6e-f0dc88ff4892 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_abbd2e56-16c4-4bff-8e6e-f0dc88ff4892/1770642814798.jpg | 2026-02-09 | 35.907 | 14.9798 | PC-44 | Not Started | Existed Ø100 PVC | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-10 10:10:23 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_abbd2e56-16c4-4bff-8e6e-f0dc88ff4892/1770642826668.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_abbd2e56-16c4-4bff-8e6e-f0dc88ff4892/1770642839278.jpg
uuid:91c0eed3-dd19-4332-8d8b-28a51be5fb3c | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_91c0eed3-dd19-4332-8d8b-28a51be5fb3c/1770647275343.jpg | 2026-02-09 | 35.9055 | 14.9668 | PT-26 | Not Started | Existed Ø160 PVC | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-10 07:47:45 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_91c0eed3-dd19-4332-8d8b-28a51be5fb3c/1770647286000.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_91c0eed3-dd19-4332-8d8b-28a51be5fb3c/1770647298211.jpg
uuid:a218e48a-e695-4dff-8492-6d8680a8573a | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_a218e48a-e695-4dff-8492-6d8680a8573a/1770647104926.jpg | 2026-02-09 | 35.9052 | 14.9662 | PT-26 | Not Started | Existed Ø100 PVC | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-10 07:45:46 | N/A
uuid:7d0a4a7b-c2d9-4c4e-a4fe-81332bd524e6 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_7d0a4a7b-c2d9-4c4e-a4fe-81332bd524e6/1770642419029.jpg | 2026-02-09 | 35.9069 | 14.9787 | PC-24 | Not Started | Two existed pipes, first with Ø100 and the second with Ø50, both PVC | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-10 07:40:56 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_7d0a4a7b-c2d9-4c4e-a4fe-81332bd524e6/1770642434880.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_7d0a4a7b-c2d9-4c4e-a4fe-81332bd524e6/1770642444810.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_7d0a4a7b-c2d9-4c4e-a4fe-81332bd524e6/1770642511579.jpg
uuid:b822b3f3-57f7-4246-8e2a-e0f15d466b1a | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b822b3f3-57f7-4246-8e2a-e0f15d466b1a/1770642088543.jpg | 2026-02-09 | 35.9068 | 14.9791 | PC-24 | Not Started | Existed Ø100 pvc | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-10 07:33:31 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b822b3f3-57f7-4246-8e2a-e0f15d466b1a/1770642106736.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b822b3f3-57f7-4246-8e2a-e0f15d466b1a/1770642121516.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b822b3f3-57f7-4246-8e2a-e0f15d466b1a/1770642133209.jpg
uuid:0b8da23c-1f98-48c4-a694-debd5c3b2028 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_0b8da23c-1f98-48c4-a694-debd5c3b2028/1770122748790.jpg | 2026-02-03 | 35.8896 | 14.9514 | PT-16 | Not Started | Existed 160 connect between the Ø250 PVC from new WTP and the Ø200 Asbestos from old WTP | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-09 11:09:30 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_0b8da23c-1f98-48c4-a694-debd5c3b2028/1770122760433.jpg
uuid:83c652b4-a50e-48ec-ac20-2c2cccc2db4e | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_83c652b4-a50e-48ec-ac20-2c2cccc2db4e/1770123095736.jpg | 2026-02-03 | 35.8907 | 14.9506 | PT-16 | Not Started | Existed 160 PVC pipe | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-09 11:03:36 | N/A
uuid:d7cb44de-8474-43a1-bc99-2018a8482782 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_d7cb44de-8474-43a1-bc99-2018a8482782/1770123437002.jpg | 2026-02-03 | 35.8923 | 14.9493 | PT-16 | Not Started | Existed 160 PVC | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-09 10:57:59 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_d7cb44de-8474-43a1-bc99-2018a8482782/1770123448346.jpg
uuid:13959563-1513-43ce-804f-dbf325fde258 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_13959563-1513-43ce-804f-dbf325fde258/1770123953917.jpg | 2026-02-02 | 35.8933 | 14.9407 | PT-13 | Not Started | Existed Ø200 Asbestos coming from old WTP | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-09 09:40:36 | N/A
uuid:e58664dc-c327-45ed-ba43-edf2a538bebb | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_e58664dc-c327-45ed-ba43-edf2a538bebb/1770124311980.jpg | 2026-02-02 | 35.8922 | 14.9406 | Joint of PT-13, PT-14, PT-12 | Not Started | Existed Ø200 Asbestos | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-09 09:36:21 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_e58664dc-c327-45ed-ba43-edf2a538bebb/1770124328372.jpg
uuid:6717dfab-968e-4b39-9dd2-67894a1ce05a | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_6717dfab-968e-4b39-9dd2-67894a1ce05a/1770629224867.jpg | 2026-01-28 | 35.8922 | 14.9464 | Joint of PT-14, PT-15,PT-35,PT-27 | Not Started | Existed Ø200 Asbestos coming from old WTP that connect with the Ø200 PVC from new WTP | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-09 09:29:23 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_6717dfab-968e-4b39-9dd2-67894a1ce05a/1770629262796.jpg
uuid:9e6345c1-6e4f-4aee-a001-607eb2d3ffd0 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_9e6345c1-6e4f-4aee-a001-607eb2d3ffd0/1770124763571.jpg | 2026-02-02 | 35.8866 | 14.9469 | Near PT-35 | Not Started | Discovered existed Ø200 PVC Doesn't appear in the existing WDN | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-09 09:19:09 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_9e6345c1-6e4f-4aee-a001-607eb2d3ffd0/1770124769915.jpg
uuid:8f179ad6-044d-4259-9afc-a9f78947ab31 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_8f179ad6-044d-4259-9afc-a9f78947ab31/1770123701401.jpg | 2026-02-02 | 35.8921 | 14.9464 | PT-35 | Not Started | Existed Ø200 pipe PVC | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-09 09:13:25 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_8f179ad6-044d-4259-9afc-a9f78947ab31/1770123711557.jpg
uuid:bf492845-a79c-450d-88d3-94a0f8a6f456 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_bf492845-a79c-450d-88d3-94a0f8a6f456/1770627709448.jpg | 2026-01-26 | 35.879 | 14.9523 | PT-36 | Not Started | Tracking the existed Ø200 pipe from new WTP | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-09 09:03:03 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_bf492845-a79c-450d-88d3-94a0f8a6f456/1770627725947.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_bf492845-a79c-450d-88d3-94a0f8a6f456/1770627744473.jpg
uuid:d7c3d157-ba51-4c34-bcb3-a7267cce2940 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_d7c3d157-ba51-4c34-bcb3-a7267cce2940/1770627391370.jpg | 2026-01-26 | 35.8815 | 14.9506 | PT-36 | Not Started | Tracking the existed Ø200 PVC from new WTP | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-09 08:57:15 | N/A
uuid:18b6585c-c4a2-4144-812b-ef60b93d1c27 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_18b6585c-c4a2-4144-812b-ef60b93d1c27/1770626990788.jpg | 2026-01-26 | 35.8839 | 14.9493 | PT-36 | Not Started | Ø200 existed pipe coming from new WTP | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-09 08:50:26 | N/A
uuid:dad040f5-7195-41df-ba3d-f7e008c5803c | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_dad040f5-7195-41df-ba3d-f7e008c5803c/1770626657903.jpg | 2026-01-26 | 35.8866 | 14.9477 | PT-36 | Not Started | Existed Ø200 pipe coming from new WTP | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-09 08:45:13 | N/A
uuid:972b5e37-e28a-4650-90a8-9ccaa5c675c4 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_972b5e37-e28a-4650-90a8-9ccaa5c675c4/1770626396943.jpg | 2026-01-26 | 35.8866 | 14.9476 | Near PT-36 | Not Started | 250 existed PVC pipe | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-09 08:41:45 | N/A
uuid:6f12323c-ddfa-4f02-bc25-5fd201f50d9e | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_6f12323c-ddfa-4f02-bc25-5fd201f50d9e/1770625963008.jpg | 2026-02-09 | 35.8865 | 14.9475 | Near PT-36 | Not Started | كشف خط200pvc | N/A | N/A | collect:MR4mgpYqgHCWHAO3 | 2026-02-09 08:34:58 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_6f12323c-ddfa-4f02-bc25-5fd201f50d9e/1770626013209.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_6f12323c-ddfa-4f02-bc25-5fd201f50d9e/1770626029171.jpg
uuid:1763b51c-60dc-4430-b44d-298bf74c5cd5 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_1763b51c-60dc-4430-b44d-298bf74c5cd5/1770623606636.jpg | 2026-02-01 | 35.8827 | 14.95 | PT-36 | Not Started | كشف خط200pvc | N/A | N/A | collect:MR4mgpYqgHCWHAO3 | 2026-02-09 07:54:35 | N/A
uuid:27e60314-043d-4f4b-85b3-0cc0a1bfdc60 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_27e60314-043d-4f4b-85b3-0cc0a1bfdc60/1770623188309.jpg | 2026-02-01 | 35.879 | 14.9524 | PT-36 | Not Started | كشف خط 200pvc | N/A | N/A | collect:MR4mgpYqgHCWHAO3 | 2026-02-09 07:49:02 | N/A
uuid:9c983d97-c8b2-4d90-b9e7-86f10545c066 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_9c983d97-c8b2-4d90-b9e7-86f10545c066/1770622998350.jpg | 2026-02-01 | 35.8787 | 14.9526 | PT-37 | Not Started | كشف خط ٢٠٠ Pvc | N/A | N/A | collect:MR4mgpYqgHCWHAO3 | 2026-02-09 07:44:47 | N/A
uuid:5f0493af-2d47-40eb-a012-53bed26c3293 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_5f0493af-2d47-40eb-a012-53bed26c3293/1770300085193.jpg | 2026-02-05 | 35.8935 | 14.9652 | PT-31 | Not Started | لم يتم توريد الأنابيب، فقط أعمال كشف لخطوط الشبكه القديمة خط 250p.v.c | N/A | N/A | collect:MR4mgpYqgHCWHAO3 | 2026-02-09 07:32:41 | N/A
uuid:0fa7d96e-fd3f-4491-b931-e7d56c47086d | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_0fa7d96e-fd3f-4491-b931-e7d56c47086d/1770621513127.jpg | 2026-02-08 | 35.8906 | 14.9705 | PT-07 | Not Started | تم كشف خط ٢٥٠ P. V. C | N/A | N/A | collect:MR4mgpYqgHCWHAO3 | 2026-02-09 07:22:58 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_0fa7d96e-fd3f-4491-b931-e7d56c47086d/1770621654228.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_0fa7d96e-fd3f-4491-b931-e7d56c47086d/1770621694005.jpg
uuid:7af94435-a301-419f-a370-e8bb46335a20 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_7af94435-a301-419f-a370-e8bb46335a20/1770196451490.jpg | 2026-02-04 | 35.8911 | 14.9551 | Profile PT-18 to PT-19 – Trial Pit | Not Started | Two (2) trial pits were conducted, exposing the existing Ø250 mm pipeline for identification purposes only. | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-04 09:59:54 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_7af94435-a301-419f-a370-e8bb46335a20/1770196462952.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_7af94435-a301-419f-a370-e8bb46335a20/1770196474087.jpg
uuid:ddb3e16f-73c8-4c9d-a7af-b88cdb8a3531 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_ddb3e16f-73c8-4c9d-a7af-b88cdb8a3531/1770121014841.jpg | 2026-02-03 | 35.8966 | 14.9608 | Pipes Profiles in Town – PT-13 to PT-36 (Trial Pits) | Not Started | Trial pits were conducted to locate and verify existing pipelines along the proposed new pressure main alignment. A total of twelve (12) trial pits were carried out across the following profiles: PT-13, PT-15, PT-16, PT-17, PT-20, PT-29, PT-35, and PT-36. The works were limited to identification purposes only, and no trenching or pipe installation activities were undertaken. | N/A | N/A | collect:pRiwvOl04AF4nIwN | 2026-02-03 18:25:51 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_ddb3e16f-73c8-4c9d-a7af-b88cdb8a3531/1770121038229.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_ddb3e16f-73c8-4c9d-a7af-b88cdb8a3531/1770142686502.jpg
uuid:d700dc6b-1eea-49de-b3ff-4013bb621447 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_d700dc6b-1eea-49de-b3ff-4013bb621447/1769673300111.jpg | 2026-01-29 | 36.4388 | 15.359 | Drilling for well Forest 2 | In Progress | Drilling at depth 24m | 25 | N/A | collect:Qt2JVFL7mRJpcVUs | 2026-01-30 02:42:13 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_d700dc6b-1eea-49de-b3ff-4013bb621447/1769673309133.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_d700dc6b-1eea-49de-b3ff-4013bb621447/1769673315090.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_d700dc6b-1eea-49de-b3ff-4013bb621447/1769673321232.jpg
uuid:eaab966d-a9c2-458f-b8fd-ff60d42d221d | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_eaab966d-a9c2-458f-b8fd-ff60d42d221d/1769501967065.jpg | 2026-01-27 | 36.433 | 15.367 | 66/2025 | In Progress | Conduction of constant pumping test for well 66/2025 | 80 | N/A | collect:Qt2JVFL7mRJpcVUs | 2026-01-29 02:58:43 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_eaab966d-a9c2-458f-b8fd-ff60d42d221d/1769501973772.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_eaab966d-a9c2-458f-b8fd-ff60d42d221d/1769501980186.jpg
uuid:8404cecc-97cf-46ec-91d2-9a3fac54e683 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_8404cecc-97cf-46ec-91d2-9a3fac54e683/1769420057907.jpg | 2026-01-26 | 36.4344 | 15.3625 | Well 5b | In Progress | Water samples collection for well 5b | 90 | N/A | collect:Qt2JVFL7mRJpcVUs | 2026-01-29 02:50:30 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_8404cecc-97cf-46ec-91d2-9a3fac54e683/1769420065106.jpg
uuid:227db449-92b9-48a9-8067-bddd74be00ee | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_227db449-92b9-48a9-8067-bddd74be00ee/1769417844766.jpg | 2026-01-26 | 36.446 | 15.3408 | Forest 5 | In Progress | Water Quality sample collection | 90 | N/A | collect:Qt2JVFL7mRJpcVUs | 2026-01-28 04:16:16 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_227db449-92b9-48a9-8067-bddd74be00ee/1769417855179.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_227db449-92b9-48a9-8067-bddd74be00ee/1769417865411.jpg
uuid:a8104c55-8246-4841-a529-02a90c4c52cf | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_a8104c55-8246-4841-a529-02a90c4c52cf/1769006700108.jpg | 2026-01-21 | 36.4461 | 15.3408 | Forest 5 | In Progress | Conduction of Step pumping test. | 65 | N/A | collect:Qt2JVFL7mRJpcVUs | 2026-01-28 04:08:31 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_a8104c55-8246-4841-a529-02a90c4c52cf/1769006720421.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_a8104c55-8246-4841-a529-02a90c4c52cf/1769006728100.jpg
uuid:31bc781a-8445-4a23-8ab8-ecf8bf34922b | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_31bc781a-8445-4a23-8ab8-ecf8bf34922b/Girba%202-9_58_12.jpeg | 2026-01-27 | 35.8794 | 14.9457 | Khashm el Girba | Not Started | Inspection of existing pipelines is ongoing. | N/A | N/A | N/A | 2026-01-27 07:01:12 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_31bc781a-8445-4a23-8ab8-ecf8bf34922b/Girba%203-9_58_23.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_31bc781a-8445-4a23-8ab8-ecf8bf34922b/Girba%204-9_58_32.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_31bc781a-8445-4a23-8ab8-ecf8bf34922b/Girba%205-9_58_39.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_31bc781a-8445-4a23-8ab8-ecf8bf34922b/Girba%206-9_58_46.jpeg
uuid:af1885cf-d233-4297-87d7-c835a05e04d7 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_af1885cf-d233-4297-87d7-c835a05e04d7/1768911766322.jpg | 2026-01-20 | 36.4344 | 15.3626 | 5B | In Progress | Pumping test stage and fencing installation | 70 | N/A | collect:FCb5eWMM6uQSJ04H | 2026-01-20 12:25:45 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_af1885cf-d233-4297-87d7-c835a05e04d7/1768911784820.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_af1885cf-d233-4297-87d7-c835a05e04d7/1768911797566.jpg
uuid:1465a401-8309-4730-b7e2-9a316c4ec6c6 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_1465a401-8309-4730-b7e2-9a316c4ec6c6/1768910507283.jpg | 2026-01-20 | 36.4298 | 15.361 | Site 4 | In Progress | Drilling started | 20 | N/A | collect:FCb5eWMM6uQSJ04H | 2026-01-20 12:04:42 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_1465a401-8309-4730-b7e2-9a316c4ec6c6/1768910522807.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_1465a401-8309-4730-b7e2-9a316c4ec6c6/1768910534823.jpg
uuid:233c42fc-edda-4f8b-a331-442b9616afe1 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_233c42fc-edda-4f8b-a331-442b9616afe1/1768901712048.jpg | 2026-01-20 | 36.4456 | 15.3408 | Forest 5 | In Progress | Step pumping test is ongoing | 85 | N/A | collect:FCb5eWMM6uQSJ04H | 2026-01-20 09:37:21 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_233c42fc-edda-4f8b-a331-442b9616afe1/1768901729116.jpg
uuid:ecb4f2ac-6953-4edb-9e6b-dc87ca046aa4 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_ecb4f2ac-6953-4edb-9e6b-dc87ca046aa4/1768806432419.jpg | 2026-01-19 | 36.4436 | 15.3381 | Forest6 | In Progress | Water quality samples collection | 95 | N/A | collect:Qt2JVFL7mRJpcVUs | 2026-01-19 07:15:17 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_ecb4f2ac-6953-4edb-9e6b-dc87ca046aa4/1768806450580.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_ecb4f2ac-6953-4edb-9e6b-dc87ca046aa4/1768806472961.jpg
uuid:14a82155-c5e6-4382-a81d-62fc5ec2dc6a | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_14a82155-c5e6-4382-a81d-62fc5ec2dc6a/1768462659954.jpg | 2026-01-15 | 36.4461 | 15.3409 | Forest 5 | In Progress | Air surging started | 85 | N/A | collect:FCb5eWMM6uQSJ04H | 2026-01-15 07:39:06 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_14a82155-c5e6-4382-a81d-62fc5ec2dc6a/1768462673377.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_14a82155-c5e6-4382-a81d-62fc5ec2dc6a/1768462687820.jpg
uuid:473d9b32-02cb-40f3-9f38-329c19226b3c | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_473d9b32-02cb-40f3-9f38-329c19226b3c/1768297747108.jpg | 2026-01-13 | 36.4436 | 15.3381 | Forest 6 | In Progress | Step test is done, ready for constant rate test | 90 | N/A | collect:FCb5eWMM6uQSJ04H | 2026-01-13 09:50:59 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_473d9b32-02cb-40f3-9f38-329c19226b3c/1768297758771.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_473d9b32-02cb-40f3-9f38-329c19226b3c/1768297772726.jpg
uuid:6a43d81b-3622-4fc9-b423-f57de8a1405a | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_6a43d81b-3622-4fc9-b423-f57de8a1405a/1768295751031.jpg | 2026-01-13 | 36.4461 | 15.3409 | Forest 5 | In Progress | Development stage has been started (washing/ back washing) | 80 | N/A | collect:FCb5eWMM6uQSJ04H | 2026-01-13 09:18:20 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_6a43d81b-3622-4fc9-b423-f57de8a1405a/1768295764613.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_6a43d81b-3622-4fc9-b423-f57de8a1405a/1768295782378.jpg
uuid:99df60ab-9878-48c7-bd2d-81ce303830b3 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_99df60ab-9878-48c7-bd2d-81ce303830b3/1768293198274.jpg | 2026-01-13 | 36.4059 | 15.4514 | Forest 3 | In Progress | Drilling works has been completed. Logging and well development not started yet. Expected to be starter today 13.01.2026 | 60 | N/A | collect:FCb5eWMM6uQSJ04H | 2026-01-13 08:37:55 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_99df60ab-9878-48c7-bd2d-81ce303830b3/1768293228194.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_99df60ab-9878-48c7-bd2d-81ce303830b3/1768293281794.jpg
uuid:b30ce4e1-1f27-46e6-a153-0aac7215e1e9 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b30ce4e1-1f27-46e6-a153-0aac7215e1e9/1768223153886.jpg | 2026-01-12 | 36.4461 | 15.341 | Forest 5 | In Progress | Case installation | 70 | N/A | collect:UDwYmSzhPiZPj5Id | 2026-01-12 13:06:41 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b30ce4e1-1f27-46e6-a153-0aac7215e1e9/1768223158761.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b30ce4e1-1f27-46e6-a153-0aac7215e1e9/1768223164718.jpg
uuid:c328330e-ccad-4021-a55c-4ff562005751 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_c328330e-ccad-4021-a55c-4ff562005751/1768130787177.jpg | 2026-01-11 | 36.4437 | 15.3381 | Forest 6 | In Progress | Step drawdown pumping test | 90 | N/A | collect:UDwYmSzhPiZPj5Id | 2026-01-11 11:27:34 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_c328330e-ccad-4021-a55c-4ff562005751/1768130800006.jpg
uuid:4d48a267-6c6c-473d-ae3d-7b313e49e28c | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_4d48a267-6c6c-473d-ae3d-7b313e49e28c/1767876728913.jpg | 2026-01-08 | 36.4358 | 15.3566 | Forest 3 | Not Started | The rig is centered in site forest 3 | N/A | N/A | collect:UDwYmSzhPiZPj5Id | 2026-01-08 12:53:04 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_4d48a267-6c6c-473d-ae3d-7b313e49e28c/1767876735044.jpg
uuid:a493c3b2-f6ae-4a1f-9fde-91b58cfdc091 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_a493c3b2-f6ae-4a1f-9fde-91b58cfdc091/1767790906954.jpg | 2026-01-07 | 36.4461 | 15.3409 | Forest 5 | In Progress | Geophysical Well logging | 90 | N/A | collect:UDwYmSzhPiZPj5Id | 2026-01-07 13:02:35 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_a493c3b2-f6ae-4a1f-9fde-91b58cfdc091/1767790911663.jpg
uuid:cbbf6c03-050c-4433-9eec-6e242f077232 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_cbbf6c03-050c-4433-9eec-6e242f077232/1767512378766.jpg | 2026-01-04 | 36.4461 | 15.3409 | Forest 5 | In Progress | Surface case installation | 30 | N/A | collect:UDwYmSzhPiZPj5Id | 2026-01-04 07:40:27 | N/A
uuid:939a0bad-f5c8-434b-8242-92eb7878b17b | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_939a0bad-f5c8-434b-8242-92eb7878b17b/1767427840359.jpg | 2026-01-03 | 36.4299 | 15.361 | Site No 4 | In Progress | Step drawdown test | 85 | N/A | collect:UDwYmSzhPiZPj5Id | 2026-01-03 08:11:54 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_939a0bad-f5c8-434b-8242-92eb7878b17b/1767427865426.jpg
uuid:b4537a40-cd8e-47ff-9371-07963c71b0b0 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b4537a40-cd8e-47ff-9371-07963c71b0b0/1767275380668.jpg | 2026-01-01 | 36.4461 | 15.3409 | Forest 5 | Not Started | Rig mobilization and site clearance (forest 5) | N/A | N/A | collect:UDwYmSzhPiZPj5Id | 2026-01-01 13:50:53 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b4537a40-cd8e-47ff-9371-07963c71b0b0/1767275397788.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b4537a40-cd8e-47ff-9371-07963c71b0b0/1767275408782.jpg
uuid:97f5af58-95dd-4cc8-b483-248ccc981f8b | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_97f5af58-95dd-4cc8-b483-248ccc981f8b/1767007899036.jpg | 2025-12-29 | 36.4299 | 15.3611 | Site 4 | In Progress | BH cleaning | 30 | N/A | collect:zrt4bfXMwHGQfG2o | 2025-12-29 11:37:04 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_97f5af58-95dd-4cc8-b483-248ccc981f8b/1767008137673.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_97f5af58-95dd-4cc8-b483-248ccc981f8b/1767008178990.jpg
uuid:f880637b-03f6-4949-8452-da117b0160a6 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f880637b-03f6-4949-8452-da117b0160a6/1767005865754.jpg | 2025-12-29 | 36.43 | 15.3609 | Site 4 | In Progress | Well cleaning from accumulation of gravel by bailing | 60 | N/A | collect:UDwYmSzhPiZPj5Id | 2025-12-29 10:59:16 | N/A
uuid:3d968fe7-f948-421a-9390-5394126fe9d8 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_3d968fe7-f948-421a-9390-5394126fe9d8/1767005508161.jpg | 2025-12-29 | 36.4436 | 15.3381 | Forest 6 | In Progress | Drilling of the bore hole | 25 | N/A | collect:zrt4bfXMwHGQfG2o | 2025-12-29 10:52:56 | N/A
uuid:99e2d970-83ba-43b3-88c3-35223728dc58 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_99e2d970-83ba-43b3-88c3-35223728dc58/1766917666724.jpg | 2025-12-28 | 36.4301 | 15.3609 | Site 4 | In Progress | Starting the provisional pumping test as part of the development | 70 | N/A | collect:UDwYmSzhPiZPj5Id | 2025-12-28 10:30:36 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_99e2d970-83ba-43b3-88c3-35223728dc58/1766917690967.jpg
uuid:67981060-16e4-4f86-9d79-a29e5b90ad4e | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_67981060-16e4-4f86-9d79-a29e5b90ad4e/1766314227803.jpg | 2025-12-21 | 35.8869 | 14.9475 | Site hand over for Khashim Elgirba network rehabilitation | Not Started | Site hand over for the network rehabilitation | N/A | N/A | collect:Qt2JVFL7mRJpcVUs | 2025-12-22 04:01:48 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_67981060-16e4-4f86-9d79-a29e5b90ad4e/1766314235886.jpg
uuid:78198483-cba6-4620-aee8-ca4226df56e7 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_78198483-cba6-4620-aee8-ca4226df56e7/1766309267148.jpg | 2025-12-21 | 35.9105 | 14.9791 | Site hand over for Khashim Elgirba water network camp rehabilitation to the contractor | Not Started | Site hand over for the network in Girba camp | N/A | N/A | collect:Qt2JVFL7mRJpcVUs | 2025-12-22 03:52:28 | N/A
uuid:f5b2aae2-857d-4554-bce8-ac302c38c68a | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f5b2aae2-857d-4554-bce8-ac302c38c68a/1766309189946.jpg | 2025-12-21 | 35.9105 | 14.9792 | Rehabiliraion Elgurba network | In Progress | Site handover to Sudan pile contractor |  | N/A | collect:zrt4bfXMwHGQfG2o | 2025-12-21 09:28:56 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f5b2aae2-857d-4554-bce8-ac302c38c68a/1766309276260.jpg
uuid:e8d1e6ce-deb4-44e4-a95b-e1deeb35f074 | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3Ae8d1e6ce-deb4-44e4-a95b-e1deeb35f074/attachment/WhatsApp%20Image%202025-12-12%20at%2014.37.08_f842ddb4-17_42_39.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-03-03 | 36.4469 | 15.346 | 69/2025 | Not Started | Site handover | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-12-12 15:42:59 | N/A
uuid:fde4af36-1aa8-47f8-af27-00dadcdf0b6d | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3Afde4af36-1aa8-47f8-af27-00dadcdf0b6d/attachment/WhatsApp%20Image%202025-12-12%20at%2014.39.36_0b7b137a-17_41_13.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-03-03 | 36.4472 | 15.3444 | 68/2025 | Not Started | site handover | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-12-12 15:41:27 | N/A
uuid:ae60add8-961a-4fc3-b04b-ce0cc5911943 | Sudan | Girba | Environmental Social Safeguards (ESS) | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_ae60add8-961a-4fc3-b04b-ce0cc5911943/Girba%20locality%20Excuitive%20Diroctoer-11_55_21.jpg | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | almadani.alhassan@ricosco.net | N/A | 2025-12-12 09:56:27 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_ae60add8-961a-4fc3-b04b-ce0cc5911943/Female%20Prticipant-11_55_29.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_ae60add8-961a-4fc3-b04b-ce0cc5911943/Community%20Rep-11_55_35.jpg
uuid:0d67e3f0-5623-43bf-a4c0-d90c4a7538be | Sudan | Wad Sharifey | Environmental Social Safeguards (ESS) | https://odk-middleman.onrender.com/api/submission/uuid%3A0d67e3f0-5623-43bf-a4c0-d90c4a7538be/attachment/WhatsApp%20Image%202025-12-12%20at%2011.19.46_4304c115-11_41_52.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2024-06-13 | N/A | N/A | N/A | N/A | N/A | N/A | almadani.alhassan@ricosco.net | N/A | 2025-12-12 09:45:57 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A0d67e3f0-5623-43bf-a4c0-d90c4a7538be/attachment/WhatsApp%20Image%202025-12-12%20at%2011.19.28_a289eb9d-11_41_58.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3A0d67e3f0-5623-43bf-a4c0-d90c4a7538be/attachment/WhatsApp%20Image%202025-12-12%20at%2011.18.54_364812c0-11_42_3.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:f1c82cd0-fead-4688-8f69-f74153d43762 | Sudan | Wad Sharifey | Environmental Social Safeguards (ESS) | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f1c82cd0-fead-4688-8f69-f74153d43762/Male%20FGD-11_10_17.jpg | 2024-02-10 | N/A | N/A | N/A | N/A | N/A | N/A | almadani.alhassan@ricosco.net | N/A | 2025-12-12 09:11:46 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f1c82cd0-fead-4688-8f69-f74153d43762/Female%20FGD-11_10_26.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f1c82cd0-fead-4688-8f69-f74153d43762/KII-11_10_40.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f1c82cd0-fead-4688-8f69-f74153d43762/Fedyayaeb-11_10_47.jpg
uuid:f8266434-a25c-4c5d-9018-61ee993fc842 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f8266434-a25c-4c5d-9018-61ee993fc842/1765464890707.jpg | 2025-12-11 | 36.4299 | 15.361 | Drilling borehole site4 | In Progress | Mud physical properties completed, Viscosity 42,PH8.6,EC500. Lithology: From 0m to 3m: fine sand , superficial deposits From 3m to 6m: clay. | 10 | N/A | collect:Qt2JVFL7mRJpcVUs | 2025-12-12 02:38:55 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_f8266434-a25c-4c5d-9018-61ee993fc842/1765464945959.jpg
uuid:0f26c327-12be-4c67-a518-93f7bb17ad69 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_0f26c327-12be-4c67-a518-93f7bb17ad69/1765460017816.jpg | 2025-12-11 | 36.4435 | 15.3381 | Starting Drilling for site Forest 6 | In Progress | Drilling stared , measurements for the mud viscosity,PH and EC taken | 5 | N/A | collect:Qt2JVFL7mRJpcVUs | 2025-12-12 02:34:48 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_0f26c327-12be-4c67-a518-93f7bb17ad69/1765460036367.jpg
uuid:55f08daa-828c-4173-8f18-ec14cd7168e3 | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A55f08daa-828c-4173-8f18-ec14cd7168e3/attachment/WhatsApp%20Image%202025-12-11%20at%2012.38.15_1e6085e2-15_10_14.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-06-01 | 36.4344 | 15.3625 | Borehole 2 (site 5b) | Completed | Site clearance | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 13:10:59 | N/A
uuid:50c5a8a7-36aa-401b-8228-7d8944664967 | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A50c5a8a7-36aa-401b-8228-7d8944664967/attachment/WhatsApp%20Image%202025-12-11%20at%2012.38.15_e746ba21-15_7_52.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-05-29 | 36.4344 | 15.3625 | Borehole 2 (site 5b) | In Progress | Development using Air surging | 98 | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 13:08:55 | N/A
uuid:ad27d99d-1443-4339-a734-075508f9a7b3 | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3Aad27d99d-1443-4339-a734-075508f9a7b3/attachment/WhatsApp%20Image%202025-12-11%20at%2012.38.06_b68313c9-15_3_42.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-05-28 | 36.4344 | 15.3625 | Borehole 2 (site 5b) | In Progress | Well head and concrete slab casting | 95 | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 13:05:43 | N/A
uuid:41316f62-362b-4620-98f2-7f101e724d47 | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A41316f62-362b-4620-98f2-7f101e724d47/attachment/WhatsApp%20Image%202025-12-11%20at%2012.37.34_c568d63d-14_59_58.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-05-27 | 36.4344 | 15.3625 | Borehole 2 (site 5b) | In Progress | Development using backwashing | 90 | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 13:01:35 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A41316f62-362b-4620-98f2-7f101e724d47/attachment/WhatsApp%20Image%202025-12-11%20at%2012.37.38_4497253b-15_0_9.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:70f7b029-b514-4b63-a412-c8e0d5eed6c2 | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A70f7b029-b514-4b63-a412-c8e0d5eed6c2/attachment/WhatsApp%20Image%202025-12-11%20at%2012.37.32_db0f48b4-14_55_12.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-05-27 | 36.4344 | 15.3625 | borehole 2 (site 5b) | In Progress | Casing and observation pipe lowering | 80 | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 12:58:45 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A70f7b029-b514-4b63-a412-c8e0d5eed6c2/attachment/WhatsApp%20Image%202025-12-11%20at%2012.37.27_4b4c301f-14_55_23.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:37e398d1-6704-4930-a555-d15dafd98e97 | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A37e398d1-6704-4930-a555-d15dafd98e97/attachment/WhatsApp%20Image%202025-12-11%20at%2012.37.22_fb9ec6ee-14_46_18.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-05-25 | 36.4344 | 15.3625 | Borehole 2 (site 5b) | In Progress | Rig mobilization to site 5b and drilling starting | 20 | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 12:47:26 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A37e398d1-6704-4930-a555-d15dafd98e97/attachment/WhatsApp%20Image%202025-12-11%20at%2012.37.25_64a0a7d0-14_46_26.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:9637e9e2-30aa-4760-9aaf-e9bdc4913a16 | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A9637e9e2-30aa-4760-9aaf-e9bdc4913a16/attachment/WhatsApp%20Image%202025-12-11%20at%2012.38.19_9f4611cb-14_33_10.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-07-07 | 36.433 | 15.3669 | Borehole 1 (site 66/2025) | Completed | Water samples for Chemical and Bio analysis | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 12:37:18 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A9637e9e2-30aa-4760-9aaf-e9bdc4913a16/attachment/WhatsApp%20Image%202025-12-11%20at%2012.38.21_2296f2b5-14_33_15.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:7bd890e0-7c27-45ad-8d62-c0ea59df7287 | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A7bd890e0-7c27-45ad-8d62-c0ea59df7287/attachment/WhatsApp%20Image%202025-12-11%20at%2012.38.17_2b6e923d-14_29_32.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-07-06 | 36.433 | 15.3669 | Borehole 1 (site 66/2025) | Completed | Pumping test | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 12:30:37 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A7bd890e0-7c27-45ad-8d62-c0ea59df7287/attachment/WhatsApp%20Image%202025-12-11%20at%2012.38.16_332e2ed1-14_29_43.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:186c4c0f-b1bc-4141-914b-6c28aeab8d23 | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A186c4c0f-b1bc-4141-914b-6c28aeab8d23/attachment/WhatsApp%20Image%202025-12-11%20at%2012.37.41_3d7d6a44-14_19_47.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-05-28 | 36.433 | 15.3669 | Borehole 1 (site 66/2025) | In Progress | Development using Air surging | 95 | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 12:27:15 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A186c4c0f-b1bc-4141-914b-6c28aeab8d23/attachment/WhatsApp%20Image%202025-12-11%20at%2012.37.48_8f657bdc-14_19_56.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:0b46847a-870c-42b2-b74b-b64ecb37dece | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A0b46847a-870c-42b2-b74b-b64ecb37dece/attachment/WhatsApp%20Image%202025-12-11%20at%2012.37.21_1e36e718-14_10_48.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-05-23 | 36.433 | 15.3669 | Borehole 1 (site 66/2025) | In Progress | Well head and concrete slab casting | 90 | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 12:13:11 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A0b46847a-870c-42b2-b74b-b64ecb37dece/attachment/WhatsApp%20Image%202025-12-11%20at%2012.37.19_b65f2c58-14_10_54.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:3f0ba91a-a1cf-4117-b023-17ac5300ebd0 | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A3f0ba91a-a1cf-4117-b023-17ac5300ebd0/attachment/WhatsApp%20Image%202025-12-11%20at%2012.35.27_cc895f53-13_57_34.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-05-21 | 36.433 | 15.3669 | Borehole 1 (site 66/2025) | In Progress | Casing and observation pipe lowering | 60 | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 11:59:11 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A3f0ba91a-a1cf-4117-b023-17ac5300ebd0/attachment/WhatsApp%20Image%202025-12-11%20at%2012.35.44_10df87c4-13_57_39.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:702c92e7-0ba9-41cc-8c76-cff1ed465e6f | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A702c92e7-0ba9-41cc-8c76-cff1ed465e6f/attachment/WhatsApp%20Image%202025-12-11%20at%2012.35.15_ff2d1d57-13_52_0.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-05-17 | 36.433 | 15.3669 | Borehole 1 (site 66/2025) | In Progress | starting the drilling process | 10 | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 11:53:12 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A702c92e7-0ba9-41cc-8c76-cff1ed465e6f/attachment/WhatsApp%20Image%202025-12-11%20at%2012.35.19_c5fb5de1-13_52_5.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:f5be3a21-3a76-4697-ade0-55be36697520 | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3Af5be3a21-3a76-4697-ade0-55be36697520/attachment/WhatsApp%20Image%202025-12-11%20at%2011.39.41_608d5668-13_46_51.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-05-15 | 36.433 | 15.3669 | borehole 1 (site 66/2025) | Not Started | Rig mobilization to site 66/2025 | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 11:48:43 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3Af5be3a21-3a76-4697-ade0-55be36697520/attachment/WhatsApp%20Image%202025-12-11%20at%2011.39.41_47603aba-13_46_58.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:e098706b-6db1-4954-8137-75aa4a6a8e43 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_e098706b-6db1-4954-8137-75aa4a6a8e43/IMG_5035-11_0_21.JPG | 2025-03-03 | 36.4344 | 15.3625 | borehole 2 (site 5b) | Not Started | site handover | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 09:05:40 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_e098706b-6db1-4954-8137-75aa4a6a8e43/IMG_5033-11_0_35.JPG
uuid:e6c5a63f-0e6b-4cba-9e5b-eb509d50cfe4 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_e6c5a63f-0e6b-4cba-9e5b-eb509d50cfe4/IMG_5009-10_46_36.JPG | 2025-03-03 | 36.433 | 15.3669 | borehole 1 (site 66/2025) | Not Started | Site Handover | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-12-11 08:56:27 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_e6c5a63f-0e6b-4cba-9e5b-eb509d50cfe4/IMG_5014-10_46_55.JPG
uuid:a9eced3f-5274-4272-844c-1cd2cdaf3e33 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_a9eced3f-5274-4272-844c-1cd2cdaf3e33/1765360179046.jpg | 2025-12-10 | 36.4436 | 15.3381 | Site Forest6 | Not Started | Rig2 mobilization for site Forest6 | N/A | N/A | collect:Qt2JVFL7mRJpcVUs | 2025-12-11 04:44:00 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_a9eced3f-5274-4272-844c-1cd2cdaf3e33/1765360208856.jpg
uuid:3f40e9ce-0bde-4aeb-8947-d55629b46b2e | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_3f40e9ce-0bde-4aeb-8947-d55629b46b2e/v2-14_12_54.jpeg | 2025-09-09 | N/A | N/A | UNICEF ESARO field visit 2 | Completed | UNICEF ESARO field visit 2 | N/A | rayan.elhaj@ricosco.net | N/A | 2025-12-10 12:13:26 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_3f40e9ce-0bde-4aeb-8947-d55629b46b2e/v4-14_13_0.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_3f40e9ce-0bde-4aeb-8947-d55629b46b2e/v3-14_13_8.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_3f40e9ce-0bde-4aeb-8947-d55629b46b2e/v5-14_13_13.jpeg
uuid:2b0d5f60-683c-4874-8018-96a585eca36b | Sudan | Girba | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_2b0d5f60-683c-4874-8018-96a585eca36b/F1-13_55_50.jpeg | 2025-03-19 | 35.893 | 14.9385 | Geotechnical survey - Elevated tanks location | Completed | Geotechnical survey - Elevated tanks location | N/A | rayan.elhaj@ricosco.net | N/A | 2025-12-10 11:56:27 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_2b0d5f60-683c-4874-8018-96a585eca36b/F3-13_55_55.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_2b0d5f60-683c-4874-8018-96a585eca36b/F2-13_55_59.jpeg
uuid:b39ce816-9063-4fc8-b577-c050a968bffd | Sudan | Girba | Environmental Social Safeguards (ESS) | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b39ce816-9063-4fc8-b577-c050a968bffd/E7-13_34_30.jpg | 2025-07-07 | N/A | N/A | N/A | N/A | N/A | N/A | rayan.elhaj@ricosco.net | N/A | 2025-12-10 11:35:09 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b39ce816-9063-4fc8-b577-c050a968bffd/E8-13_34_35.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b39ce816-9063-4fc8-b577-c050a968bffd/E1-13_34_45.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b39ce816-9063-4fc8-b577-c050a968bffd/E2-13_34_54.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_b39ce816-9063-4fc8-b577-c050a968bffd/E6-13_35_5.jpg
uuid:94354a1c-caec-4443-a8bd-abe1468dc92b | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_94354a1c-caec-4443-a8bd-abe1468dc92b/s1-13_17_11.jpeg | 2025-09-09 | N/A | N/A | Contractors site visit - Water distribution network | Completed | Contractors site visit - Water distribution network | N/A | rayan.elhaj@ricosco.net | N/A | 2025-12-10 11:18:37 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_94354a1c-caec-4443-a8bd-abe1468dc92b/s6-13_18_7.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_94354a1c-caec-4443-a8bd-abe1468dc92b/s4-13_17_27.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_94354a1c-caec-4443-a8bd-abe1468dc92b/s7-13_17_36.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_94354a1c-caec-4443-a8bd-abe1468dc92b/s2-13_17_51.jpeg
uuid:9b0bc48c-6457-4567-9535-fe52b5431392 | Sudan | Girba | Environmental Social Safeguards (ESS) | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_9b0bc48c-6457-4567-9535-fe52b5431392/k1-13_5_1.jpeg | 2024-06-14 | N/A | N/A | N/A | N/A | N/A | N/A | rayan.elhaj@ricosco.net | N/A | 2025-12-10 11:05:59 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_9b0bc48c-6457-4567-9535-fe52b5431392/k2-13_5_5.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_9b0bc48c-6457-4567-9535-fe52b5431392/k3-13_5_10.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_9b0bc48c-6457-4567-9535-fe52b5431392/k6-13_5_42.jpeg
uuid:894cd169-3653-48a6-9266-fa62f510862f | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_894cd169-3653-48a6-9266-fa62f510862f/b_1-12_13_39.jpeg | 2024-12-11 | N/A | N/A | Lavuun’s visit to Girba - Stakeholders meeting | Completed | Lavuun’s visit to Girba - Stakeholders meeting | N/A | rayan.elhaj@ricosco.net | N/A | 2025-12-10 10:15:56 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_894cd169-3653-48a6-9266-fa62f510862f/b_2-12_13_44.jpeg
uuid:2efffb26-d878-4758-bfd1-0af64bfec773 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_2efffb26-d878-4758-bfd1-0af64bfec773/1765357542427.jpg | 2025-12-10 | 36.43 | 15.361 | Site 4 | Not Started | Rig1 mobilization to site 4 | N/A | N/A | collect:Qt2JVFL7mRJpcVUs | 2025-12-10 09:54:36 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_2efffb26-d878-4758-bfd1-0af64bfec773/1765357552776.jpg
uuid:033c1bcc-3ab5-4e40-b3e5-8a962f4d3f30 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_033c1bcc-3ab5-4e40-b3e5-8a962f4d3f30/Top%20srv_4-11_37_53.jpeg | 2023-10-29 | N/A | N/A | Design phase topographic survey | Completed | Topographic survey was conducted for Girba camp and Girba town | N/A | rayan.elhaj@ricosco.net | N/A | 2025-12-10 09:43:45 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_033c1bcc-3ab5-4e40-b3e5-8a962f4d3f30/Top%20srv_1-11_38_2.jpeg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_033c1bcc-3ab5-4e40-b3e5-8a962f4d3f30/Top%20srv_2-11_38_13.jpeg
uuid:c03aac22-4007-4e03-b06a-db792077afa5 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_c03aac22-4007-4e03-b06a-db792077afa5/1764672906926.jpg | 2025-12-02 | 36.4435 | 15.3382 | Forest 6 | Not Started | Accessibility assessment | N/A | N/A | collect:UDwYmSzhPiZPj5Id | 2025-12-02 10:55:33 | N/A
uuid:2932edd3-3c31-47ee-993b-44eefb770a05 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_2932edd3-3c31-47ee-993b-44eefb770a05/1764672499667.jpg | 2025-12-02 | 36.446 | 15.3408 | Forest 5 | Not Started | Accessibility assessment | N/A | N/A | collect:UDwYmSzhPiZPj5Id | 2025-12-02 10:48:52 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_2932edd3-3c31-47ee-993b-44eefb770a05/1764672507992.jpg
uuid:474b8a08-5544-4051-86bc-34ec5968d1cb | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_474b8a08-5544-4051-86bc-34ec5968d1cb/1764670079887.jpg | 2025-12-02 | 36.4358 | 15.3566 | Forest 3 | Not Started | Accessibility assessment | N/A | N/A | collect:UDwYmSzhPiZPj5Id | 2025-12-02 10:08:46 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_474b8a08-5544-4051-86bc-34ec5968d1cb/1764670092702.jpg
uuid:944b045f-a206-478f-be2f-b07eeadcef0e | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_944b045f-a206-478f-be2f-b07eeadcef0e/1764668604149.jpg | 2025-12-02 | 36.4345 | 15.363 | Site4 | Not Started | Accessibility assessment | N/A | N/A | collect:UDwYmSzhPiZPj5Id | 2025-12-02 09:44:42 | N/A
uuid:37011d4f-0f2f-40b5-8e51-5c3ce9c8180d | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_37011d4f-0f2f-40b5-8e51-5c3ce9c8180d/1000089672-0_25_46.jpg | 2025-11-04 | 36.4405 | 15.3492 | Forest 4 | Not Started | Site handover | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-11-19 22:26:08 | N/A
uuid:3d049cac-1ea8-46d3-820a-47164c792024 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_3d049cac-1ea8-46d3-820a-47164c792024/Forest%203-13_38_17.jpg | 2025-11-04 | 36.436 | 15.3565 | Forest 3 | Not Started | Site Handover | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-11-11 11:40:19 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_3d049cac-1ea8-46d3-820a-47164c792024/Forest%203-001-13_38_23.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_3d049cac-1ea8-46d3-820a-47164c792024/Forest%203-002-13_38_30.jpg
uuid:b0aa5dae-c80d-4dcc-bd4d-69ffbd738558 | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3Ab0aa5dae-c80d-4dcc-bd4d-69ffbd738558/attachment/WhatsApp%20Image%202025-11-04%20at%202.26.35%20PM-10_53_37.jpeg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-11-04 | 36.4475 | 15.3441 | Borehole 68 / 2025 | Not Started | Site handover of borehole 68/2025 located in Fadayaib/ Wad Sharify | N/A | monabdalla@unicef.org | N/A | 2025-11-11 08:53:54 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3Ab0aa5dae-c80d-4dcc-bd4d-69ffbd738558/attachment/WhatsApp%20Image%202025-11-04%20at%202.26.36%20PM-10_53_42.jpeg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
uuid:f1839422-f75b-4cf2-a75e-2572f4ca05a9 | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3Af1839422-f75b-4cf2-a75e-2572f4ca05a9/attachment/WhatsApp%20Image%202025-11-04%20at%202.00.53%20PM-10_50_28.jpeg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-11-04 | 36.4471 | 15.3456 | Borehole 69/2025 | Not Started | Site handover of borehole 69/2025 located in Fadayaib/ Wad Sharify | N/A | monabdalla@unicef.org | N/A | 2025-11-11 08:51:40 | N/A
uuid:459f87e4-ed60-44ef-ad9e-cf8062bbb95a | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A459f87e4-ed60-44ef-ad9e-cf8062bbb95a/attachment/WhatsApp%20Image%202025-11-04%20at%2011.36.53%20AM-10_46_26.jpeg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-11-04 | 36.4344 | 15.3625 | Borehole2- 5B | Stalled | Site handover for Borehole-2 / 5B, the first contractor has been terminated | 30 | monabdalla@unicef.org | N/A | 2025-11-11 08:47:36 | N/A
uuid:971a209a-dfbd-4cac-a00a-59dacab6f17e | Sudan | Wad Sharifey | Source Development | https://odk-middleman.onrender.com/api/submission/uuid%3A971a209a-dfbd-4cac-a00a-59dacab6f17e/attachment/WhatsApp%20Image%202025-11-11%20at%209.30.38%20AM-9_35_31.jpeg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2 | 2025-11-04 | 36.4332 | 15.3669 | Borehole 1- 66/2025 | Stalled | Site handover of Borehole 1 - 66/2025 - The first contractor has been terminated | 30 | N/A | N/A | 2025-11-11 08:19:00 | N/A
uuid:0e431d3b-9a3a-4d6a-979e-fe4811dbbbf5 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_0e431d3b-9a3a-4d6a-979e-fe4811dbbbf5/Forest%206-13_53_1.jpg | 2025-11-04 | 36.4436 | 15.3381 | Forest 6 | Not Started | Site handover | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-11-10 11:53:26 | N/A
uuid:04f2af82-402d-49c2-b174-ebfcb8f964cf | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_04f2af82-402d-49c2-b174-ebfcb8f964cf/Forest%205-13_51_35.jpg | 2025-11-04 | 36.4461 | 15.3409 | Forest 5 | Not Started | Site Handover | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-11-10 11:51:57 | N/A
uuid:e46c1423-1072-4734-a356-86876d8c9cf7 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_e46c1423-1072-4734-a356-86876d8c9cf7/Forest%204-13_49_54.jpg | 2025-11-04 | 36.4405 | 15.3492 | Forest 4 | Not Started | Site handover | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-11-10 11:50:17 | N/A
uuid:75474c77-5a79-4f87-be6b-9c41aa132948 | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_75474c77-5a79-4f87-be6b-9c41aa132948/Forest%202-%20002-13_47_33.jpg | 2025-11-04 | 36.4388 | 15.359 | Forest 2 | Not Started | Site handover | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-11-10 11:47:56 | N/A
uuid:eed996eb-9e03-4d2e-a46c-277e3f74f62a | Sudan | Wad Sharifey | Source Development | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_eed996eb-9e03-4d2e-a46c-277e3f74f62a/Forest%201-13_44_9.jpg | 2025-11-04 | 36.4327 | 15.3611 | forest 1 | Not Started | Site handover | N/A | abdallah.ahmed@ricosco.net | N/A | 2025-11-10 11:45:06 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_eed996eb-9e03-4d2e-a46c-277e3f74f62a/Forest%201-002-13_44_16.jpg
uuid:f3ea383f-dc91-4d88-86ca-140ebf2899cc | Sudan | Wad Sharifey | Other – please specify | N/A | 2025-11-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:FCb5eWMM6uQSJ04H | 2025-11-07 13:29:14 | N/A
uuid:f3396e4a-3087-4064-9e56-5c82df2dd74b | Sudan | Wad Sharifey | Other – please specify | N/A | 2025-11-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:UDwYmSzhPiZPj5Id | 2025-11-04 12:33:37 | N/A
uuid:f1b3b31d-73ac-4aa3-8456-e15454bd0757 | Sudan | Wad Sharifey | Other – please specify | N/A | 2025-11-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:UDwYmSzhPiZPj5Id | 2025-11-04 12:33:36 | N/A
uuid:590f4af4-2707-4474-b801-e8c2bfe96e8b | Sudan | Wad Sharifey | Other – please specify | N/A | 2025-11-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:Qt2JVFL7mRJpcVUs | 2025-11-04 12:09:37 | N/A
uuid:657e8ab4-14b3-4897-a8c4-def06cbb654d | Sudan | Wad Sharifey | Other – please specify | N/A | 2025-11-04 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | collect:Qt2JVFL7mRJpcVUs | 2025-11-04 12:03:45 | N/A
uuid:31c76f07-e58c-47c4-a44d-e53fd75fbe70 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_31c76f07-e58c-47c4-a44d-e53fd75fbe70/1781416234962.jpg | 2026-06-14 | 35.8997 | 14.9866 | PT-35 | In Progress | Current activity: Welding Status: Excavation completed, Pipe welding is ongoing | 20 | N/A | collect:c9hqC63bGpKD0X2x | 2026-06-15 07:11:42 | N/A
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_31c76f07-e58c-47c4-a44d-e53fd75fbe70/1781416244832.jpg
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_31c76f07-e58c-47c4-a44d-e53fd75fbe70/1781416263758.jpg
uuid:3d01c366-d322-467b-b1d1-df3e1ad970a7 | Sudan | Girba | Construction of Water Supply Schemes | http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_3d01c366-d322-467b-b1d1-df3e1ad970a7/1781416316111.jpg | 2026-06-14 | 35.8998 | 14.9867 | PC-36 | In Progress | Current activity: Excavation Status: Ongoing | 20 | N/A | collect:c9hqC63bGpKD0X2x | 2026-06-15 07:11:36 | N/A
https://odk-middleman.onrender.com/api/submission/uuid%3A3d01c366-d322-467b-b1d1-df3e1ad970a7/attachment/1781416323094.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
https://odk-middleman.onrender.com/api/submission/uuid%3A3d01c366-d322-467b-b1d1-df3e1ad970a7/attachment/1781416331013.jpg?project_id=37&form_id=R-WASH%20Activity%20Monitoring%20Questionnaire%20-%20Sudan%20-%20v2
http://rwash.odiousodds.xyz/activity-monitoring/images/37/R-WASH_Activity_Monitoring_Questionnaire_-_Sudan_-_v2/uuid_3d01c366-d322-467b-b1d1-df3e1ad970a7/1781507337746.jpg